## The Offer
Offer A · Remediate and inventory
ipc.gov.in onto the Gov.In CMS Platform and DBIM. Stage 1 scoped to a final cost of INR 2,000,000 inclusive of GST. Basis date 2026-09-01. Generated from the effort model — regenerate rather than edit cells.
THE PRICE
Final cost | INR 2,000,000 inclusive of GST at 18%
Contract value | INR 1,694,915 excluding GST
Effort | 122 person-days at P80, 20 weeks, 20 work packages
Supplier margin | 12.8% — reported, not hidden. Scope was cut until it fit the ceiling; the margin is what fell out. Below about 10% this stops being a viable engagement and the ceiling should move instead of the scope.
WHAT IT BUYS
Included | The live site made lawful and measurable, and one authoritative register of what the estate actually contains. The redirect map is delivered by PATTERN with only the traffic-bearing tail decided by hand.
NOT included | A row-by-row redirect map, a signed PDF disposition, orphan recovery, CSP hardening, the destination status-layer design, and the GIGW policy-page work. Each moves to Stage 2, where it will cost more than it would have here.
Not in either offer | The migration itself. Stage 2 is a separate procurement and is indicatively INR 207 person-days — around INR 27.8 lakh ex-GST — but that figure must be re-derived from this engagement's register before anyone commits to it.
TOOLING
Claude Max 20x | 1 seat x 5 months x USD 200/month at INR 95/USD = INR 95,000. Carried in the cost base and priced into the contract value above.
Price basis | Tier price per aipricing.guru and IntuitionLabs, September 2026. NOTE: claude.com/pricing itself lists Max as 'From $100 per month' without separating the 5x and 20x tiers, so confirm at purchase.
Tax treatment | Imported digital service (OIDAR). 18% IGST applies under reverse charge and is recoverable as input credit by a GST-registered supplier, so it is carried ex-tax in the cost base.
FX basis | USD/INR planning rate, September 2026 (spot band 94.6-95.8). Take a real quote at the day's rate.
What it is for | The analytical core of this engagement — reconciling four inventory sources, fingerprinting templates across the estate, and deciding redirect dispositions — is exactly the work an assistant accelerates. No productivity multiplier has been applied to the unit rates, because there is no evidence base for a specific one. The licence is carried as a cost the supplier bears, not as a discount to IPC.
HOW TO READ IT
Scope | Every package, and every package cut or resized to make the ceiling, shown side by side with the full Stage 1 scope.
Timeline | Gantt by week across 20 weeks. ◆ marks a milestone.
Milestones & Payments | Each paid against an exit criterion that can be failed.
Cash Flow | Cost against cash on a four-week payment lag. The peak negative position is working capital.
Resource Plan | Person-days and FTE by role and four-week period.
Charts | Live Gantt and resource-loading charts, driven by the data block to their right.
Commercials | Price build-up, rate card, and EMD, PBG and LD at IPC's own revealed rates.
SETTLE BEFORE SIGNING
Supplier tier | This price assumes a boutique or specialist supplier. IPC's own last IT tender (GEM/2026/B/7781379, 13-07-2026) demanded ISO 9001, ISO 27000 and CMMI Level 3 — a bar that excludes that tier. At mid-tier rates this scope is roughly 40% more. Resolve the procurement category before bidding, not at evaluation.
Client effort | 40–70 person-days of IPC subject-matter time for triage sign-off, tracked and never billed. 60–80% of a content audit is client-side and cannot be bought.

## Scope
Scope — what fits the ceiling and what does not
Design to cost, shown honestly: the full Stage 1 scope alongside what this offer carries. Anything cut here reappears in Stage 2, usually dearer.
Ref | Phase | Work package | Full O/M/P | This offer O/M/P | Expected PD | Status
0.1 | 0 · Mandate and decisions | Correct the brief; re-issue the objective in writing | 2/3/6 | 2/3/6 | 3.3333 | Full
0.2 | 0 · Mandate and decisions | Gov.In CMS intake via the MoHFW CIO route | 3/5/11 | 2/3/6 | 3.3333 | Reduced depth
0.4 | 0 · Mandate and decisions | registry.gov.in control and DNS readiness | 1/2/4 | 1/2/4 | 2.1667 | Full
0.5 | 0 · Mandate and decisions | Security-audit route settled in writing | 1/2/4 | 1/2/4 | 2.1667 | Full
0.6 | 0 · Mandate and decisions | Redirect-capability determination (pivotal) | 2/3/7 | 2/3/7 | 3.5 | Full
0.8 | 0 · Mandate and decisions | DBIM logo lockup 3A/3B determination | 0.5/1/2 | — |  | CUT — moves to Stage 2
0.9 | 0 · Mandate and decisions | Destination status-code behaviour proven; origin status layer designed | 2/4/9 | — |  | CUT — moves to Stage 2
1.1 | 1 · Emergency remediation | Real HTTP 404: error-document status, not a 302 to a 200 page | 1.5/3/7 | 1.5/3/7 | 3.4167 | Full
1.2 | 1 · Emergency remediation | Charset: header says iso-8859-1 over 389 Hindi pages; header wins | 2/4/9 | 2/4/9 | 4.5 | Full
1.4 | 1 · Emergency remediation | GIGW policy pages and portal links (DBIM mandates no india.gov.in link) | 1/2/4 | — |  | CUT — moves to Stage 2
1.6 | 1 · Emergency remediation | robots.txt and a stopgap sitemap | 0.5/1/2 | 0.5/1/2 | 1.0833 | Full
1.7 | 1 · Emergency remediation | CSP hardening on the live site | 2/4/10 | — |  | CUT — moves to Stage 2
1.8 | 1 · Emergency remediation | lang="hi" across 389 Hindi pages; close the joomla.xml version disclosure | 1/2/5 | 1/2/5 | 2.3333 | Full
2.1 | 2 · Inventory and redirect map | Joomla database extraction and reconciliation | 2/4/10 | 2/4/10 | 4.6667 | Full
2.2 | 2 · Inventory and redirect map | Live crawl with the two-signal validator | 3/5/10 | 3/4/8 | 4.5 | Reduced depth
2.3 | 2 · Inventory and redirect map | Wayback / CommonCrawl orphan recovery | 2/3/7 | — |  | CUT — moves to Stage 2
2.4 | 2 · Inventory and redirect map | Search Console traffic overlay | 1/2/4 | 1/2/4 | 2.1667 | Full
2.5 | 2 · Inventory and redirect map | Union of four sources into one authoritative register | 2/3/7 | 2/3/7 | 3.5 | Full
2.6 | 2 · Inventory and redirect map | Triage facilitation — keep / archive / retire | 6/10/20 | 3/5/10 | 5.5 | Reduced depth
2.7 | 2 · Inventory and redirect map | PDF estate inventory and disposition (~2,758 documents) | 5/8/18 | 2/4/9 | 4.5 | Reduced depth
2.8 | 2 · Inventory and redirect map | Redirect map — ~1,727 distinct source paths; rows exceed paths | 10/16/32 | 4/6/12 | 6.6667 | Reduced depth
2.9 | 2 · Inventory and redirect map | Hindi pairing by hreflang; bilingual gap quantified | 2/3/7 | 2/3/7 | 3.5 | Full
P.1a | P · Programme management | Programme and delivery management — Stage 1 | 8/13/24 | 6/9/17 | 9.8333 | Reduced depth
P.2a | P · Programme management | Business analysis and content governance — Stage 1 | 5/8/15 | 3/5/10 | 5.5 | Reduced depth
P.3a | P · Programme management | Documentation, SOPs and the Stage 2 cost baseline | 4/6/12 | 3/4/8 | 4.5 | Reduced depth
|  | TOTAL | 130.6 PD expected | 80.7 PD expected | 80.6667 | 122 PD at P80

## Timeline
Timeline
20 weeks. Bars are scheduled weeks; ◆ marks a milestone. Phase 2 runs alongside Phase 1 rather than after it — the 302-to-404 behaviour is a usable existence oracle, so the inventory is not blocked on the 404 fix.
Ref | Work package | Phase | PD | Start | End | W1 | A1 | W3 | W4 | W5 | W6 | A2 | W8 | W9 | W10 | A3 | W12 | W13 | W14 | W15 | A4 | W17 | W18 | W19 | A5
0.1 | Correct the brief; re-issue the objective in writing | 0 · Mandate and decisions | 5 | 1 | 2
0.2 | Gov.In CMS intake via the MoHFW CIO route | 0 · Mandate and decisions | 5 | 2 | 10
0.4 | registry.gov.in control and DNS readiness | 0 · Mandate and decisions | 3.3 | 3 | 6
0.5 | Security-audit route settled in writing | 0 · Mandate and decisions | 3.3 | 4 | 8
0.6 | Redirect-capability determination (pivotal) | 0 · Mandate and decisions | 5.3 | 2 | 6
1.1 | Real HTTP 404: error-document status, not a 302 to a 200 page | 1 · Emergency remediation | 5.2 | 2 | 5
1.2 | Charset: header says iso-8859-1 over 389 Hindi pages; header wins | 1 · Emergency remediation | 6.8 | 2 | 6
1.6 | robots.txt and a stopgap sitemap | 1 · Emergency remediation | 1.6 | 5 | 6
1.8 | lang="hi" across 389 Hindi pages; close the joomla.xml version disclosure | 1 · Emergency remediation | 3.5 | 4 | 7
2.1 | Joomla database extraction and reconciliation | 2 · Inventory and redirect map | 7.1 | 2 | 6
2.2 | Live crawl with the two-signal validator | 2 · Inventory and redirect map | 6.8 | 2 | 5
2.4 | Search Console traffic overlay | 2 · Inventory and redirect map | 3.3 | 5 | 8
2.5 | Union of four sources into one authoritative register | 2 · Inventory and redirect map | 5.3 | 7 | 9
2.6 | Triage facilitation — keep / archive / retire | 2 · Inventory and redirect map | 8.3 | 8 | 16
2.7 | PDF estate inventory and disposition (~2,758 documents) | 2 · Inventory and redirect map | 6.8 | 9 | 15
2.8 | Redirect map — ~1,727 distinct source paths; rows exceed paths | 2 · Inventory and redirect map | 10.1 | 11 | 17
2.9 | Hindi pairing by hreflang; bilingual gap quantified | 2 · Inventory and redirect map | 5.3 | 8 | 11
P.1a | Programme and delivery management — Stage 1 | P · Programme management | 14.9 | 1 | 20
P.2a | Business analysis and content governance — Stage 1 | P · Programme management | 8.3 | 2 | 18
P.3a | Documentation, SOPs and the Stage 2 cost baseline | P · Programme management | 6.8 | 15 | 20

## Milestones & Payments
Milestones and payment schedule
Contract value INR 1,694,915 ex-GST, INR 2,000,000 inclusive. Every milestone is paid against a checkable exit criterion, not a date.
Ref | Week | Milestone | Share | Ex-GST (INR) | Payable inc-GST (INR) | Cumulative ex-GST (INR)
A1 | 2 | Mobilisation and inception report | 10% | 169491.5254 | 200000 | 169491.5254
A2 | 7 | Live site remediated | 25% | 423728.8136 | 500000 | 593220.339
A3 | 11 | Platform and audit decision note | 15% | 254237.2881 | 300000 | 847457.6271
A4 | 16 | Authoritative URL register | 30% | 508474.5763 | 600000 | 1355932.2034
A5 | 20 | Pattern redirect map and handover | 20% | 338983.0508 | 400000 | 1694915.2542
|  | TOTAL | 100% | 1694915.2542 | 2000000
EXIT CRITERIA — what must be true before each invoice is raised
A1 · Week 2 · Mobilisation and inception report
Exit criterion | Team named. Inception report accepted: scope, RACI, access list, and the written re-statement of the objective as adopting DBIM and the Gov.In CMS Platform rather than moving to india.gov.in. Claude Max 20x provisioned to the named analyst.
Evidence | Signed inception report; access requests lodged for the Joomla database, Search Console and registry.gov.in.
A2 · Week 7 · Live site remediated
Exit criterion | A missing path returns a genuine HTTP 404 under both a browser and a bare user agent. Header charset is UTF-8 and Devanagari renders. All 389 Hindi pages declare lang="hi". robots.txt published. joomla.xml no longer publicly readable.
Evidence | Automated assertion suite run in front of the client, with before-and-after captures. Every item destination-independent, so none of it is wasted whichever target wins.
A3 · Week 11 · Platform and audit decision note
Exit criterion | Written intake position from the MoHFW CIO or a signed decision to take the DBIM-aligned rebuild. Audit route settled in writing. S3WaaS ruled in or out on the record. registry.gov.in control confirmed.
Evidence | Decision note with one signed page per question, each with a named owner and a date.
A4 · Week 16 · Authoritative URL register
Exit criterion | One register unioning the Joomla database, a live two-signal crawl and Search Console traffic. Every URL appears exactly once, live-validated, with language tree, template and title. Triage dispositions captured for the traffic-bearing head of the estate.
Evidence | Register delivered as a checked-in dataset with the crawl and validation code that produced it, so IPC can re-run it without the supplier.
A5 · Week 20 · Pattern redirect map and handover
Exit criterion | Redirect rules by URL pattern covering the estate, with the traffic-bearing tail decided row by row. Documented gap list naming every path still undecided, so Stage 2 starts from a known position rather than a fresh crawl.
Evidence | Rule set plus a gap register. An automated check that every pattern resolves and no rule shadows another.

## Cash Flow
Cash flow
Cost is incurred as effort is spent; cash arrives four weeks after a milestone is certified. The licence is paid monthly from week 1 whatever the billing schedule does.
Period | Weeks | PD spent | Cost incurred (INR) | Billed inc-GST (INR) | Cash received (INR) | Cumulative cost (INR) | Net position (INR)
P1 | W1–W4 | 34.9 | 456559.7275 | 200000 | 0 | 456559.7275 | -456559.7275
P2 | W5–W8 | 35.5 | 403202.6954 | 500000 | 200000 | 859762.4228 | -659762.4228
P3 | W9–W12 | 22.3 | 260335.4302 | 300000 | 500000 | 1120097.853 | -420097.853
P4 | W13–W16 | 19.6 | 231295.7366 | 600000 | 300000 | 1351393.5896 | -351393.5896
P5 | W17–W20 | 9.9 | 126696.9412 | 400000 | 600000 | 1478090.5308 | 121909.4692
P6 | W21–W24 | 0 | 0 | 0 | 400000 | 1478090.5308 | 521909.4692
Blended rate |  |  | 10830.9793 | INR/PD — an output of the role mix, not an input
Licence in the cost base |  |  | 95000 | Claude Max 20x, 5 months
Peak negative position |  |  | -659762.4228 | Working capital, not margin
Peak as share of contract |  |  | -38.93% | Ask for a mobilisation advance if uncomfortable

## Resource Plan
Resource plan
Person-days by role and four-week period, derived from each package's own role mix. One period = 20 working days.
Ref | Role | INR/PD | Total PD | P1 | P2 | P3 | P4 | P5
ME | Migration Engineer | 8640 | 44.6861 | 16.0351 | 14.7189 | 4.7378 | 6.0574 | 3.1369
BA | Content Strategist / Business Analyst | 9360 | 35.234 | 2.7419 | 7.7252 | 11.1138 | 9.8248 | 3.8283
EL | Engagement Lead / Programme Manager | 15840 | 23.0939 | 7.0451 | 5.0725 | 4.2795 | 3.7186 | 2.9782
SA | Solution Architect — Gov.In CMS / DBIM | 17280 | 7.7232 | 4.7685 | 2.3938 | 0.56087
QA | QA Engineer | 6840 | 4.2781 | 2.7997 | 1.4784
SE | Security Engineer | 14400 | 3.6092 | 1.1156 | 2.4936
CO | Content Operations / Editorial support | 5400 | 2.1201 |  | 0.53002 | 1.5901
AX | Accessibility Specialist | 10800 | 1.4134 | 0.35335 | 1.06
| TOTAL PD |  | 122.158 | 34.8592 | 35.4726 | 22.282 | 19.6008 | 9.9434
| FTE |  |  | 1.743 | 1.7736 | 1.1141 | 0.98004 | 0.49717

## Charts
Charts
Live Excel charts driven by the data block in column T. A Gantt here is a stacked bar whose first series is invisible and carries the start week.
| Item | Start-1 | Duration
| 0.1 Correct the brief; re-issue the objective | 0 | 2
| P.1a Programme and delivery management — Stage | 0 | 20
| 0.2 Gov.In CMS intake via the MoHFW CIO route | 1 | 9
| 0.6 Redirect-capability determination (pivotal | 1 | 5
| 1.1 Real HTTP 404: error-document status, not | 1 | 4
| 1.2 Charset: header says iso-8859-1 over 389 H | 1 | 5
| 2.1 Joomla database extraction and reconciliat | 1 | 5
| 2.2 Live crawl with the two-signal validator | 1 | 4
| P.2a Business analysis and content governance — | 1 | 17
| 0.4 registry.gov.in control and DNS readiness | 2 | 4
| 0.5 Security-audit route settled in writing | 3 | 5
| 1.8 lang="hi" across 389 Hindi pages; close th | 3 | 4
| 1.6 robots.txt and a stopgap sitemap | 4 | 2
| 2.4 Search Console traffic overlay | 4 | 4
| 2.5 Union of four sources into one authoritati | 6 | 3
| 2.6 Triage facilitation — keep / archive / ret | 7 | 9
| 2.9 Hindi pairing by hreflang; bilingual gap q | 7 | 4
| 2.7 PDF estate inventory and disposition (~2,7 | 8 | 7
| 2.8 Redirect map — ~1,727 distinct source path | 10 | 7
| P.3a Documentation, SOPs and the Stage 2 cost b | 14 | 6
| Role | P1 | P2 | P3 | P4 | P5
| Migration Engineer | 16.04 | 14.72 | 4.74 | 6.06 | 3.14
| Content Strategist / Business Analyst | 2.74 | 7.73 | 11.11 | 9.82 | 3.83
| Engagement Lead / Programme Manager | 7.05 | 5.07 | 4.28 | 3.72 | 2.98
| Solution Architect — Gov.In CMS / DBIM | 4.77 | 2.39 | 0.56 | 0 | 0
| QA Engineer | 2.8 | 1.48 | 0 | 0 | 0
| Security Engineer | 1.12 | 2.49 | 0 | 0 | 0
| Content Operations / Editorial support | 0 | 0.53 | 1.59 | 0 | 0
| Accessibility Specialist | 0.35 | 1.06 | 0 | 0 | 0

## Commercials
Commercials
Price built up from the bottom, so every rupee is traceable. Rates are boutique tier; commercial terms are IPC's own revealed rates from GEM/2026/B/7781379.
PRICE BUILD-UP
Effort at P80 |  | 122.158 |  | person-days, 20 packages
Blended rate |  | 10830.9793 |  | INR/PD, boutique tier, output of the role mix
Effort cost |  | 1323090.5308
Claude Max 20x licence |  | 95000 |  | 5 months x USD 200 at INR 95/USD
Tooling and data |  | 60000 |  | Crawl and validation tooling, commercial traffic data
Total cost |  | 1478090.5308
Margin |  | 12.79% |  | Solved so the contract lands exactly on the ceiling
Contract value ex-GST |  | 1694915.2542
GST at 18% |  | 305084.7458 |  | Verify whether IPC can claim input credit
FINAL COST INC-GST |  | 2000000 |  | The stated ceiling
RATE CARD — boutique tier
Ref | Role | INR/PD | PD | Note
ME | Migration Engineer | 8640 | 44.6861 | Crawler, two-signal validator, transforms, redirect map, cut-over.
BA | Content Strategist / Business Analyst | 9360 | 35.234 | Owns the inventory, the triage facilitation and the disposition register.
EL | Engagement Lead / Programme Manager | 15840 | 23.0939 | Client-facing; owns the CIO route and the decision gates.
SA | Solution Architect — Gov.In CMS / DBIM | 17280 | 7.7232 | Scarce skill; the platform-specific knowledge is the whole reason to hire outside.
QA | QA Engineer | 6840 | 4.2781 | Assertion suites; every redirect row is a test.
SE | Security Engineer | 14400 | 3.6092 | CSP, patching, pre-audit clearance, CERT-In liaison.
CO | Content Operations / Editorial support | 5400 | 2.1201 | Bulk load, alt text, metadata. The line most safely moved to IPC's own team.
AX | Accessibility Specialist | 10800 | 1.4134 | WCAG 2.1 AA; 50 of GIGW 3.0's 88 guidelines.
COMMERCIAL TERMS
Item | Rate | Value (INR) |  | Note
Earnest money deposit | 4% | 67796.6102 |  | IPC's own revealed rate on GEM/2026/B/7781379 (13-07-2026), against a GeM recommendation of 1%. Refundable, but it blocks working capital through evaluation.
Performance bank guarantee | 5% | 84745.7627 |  | IPC's revealed rate, held 60 months on its last IT bid. For a 5.5-month assignment, negotiate the term down — a 60-month PBG on a 24-week engagement is a real and avoidable carrying cost.
PBG carrying cost per annum | 1.5% | 1271.1864 |  | Bank commission. Routinely forgotten in pricing.
Liquidated damages cap | 10% | 169491.5254 |  | Convention is 0.5% per week of delay capped at 10%. This is the schedule risk expressed in rupees.
Retention against M6 | 10% | 169491.5254 |  | M6 is itself 10% and is the natural retention. Do not stack a further retention on top of it.