## The Offer
Offer B · Remediate, inventory and decide
ipc.gov.in onto the Gov.In CMS Platform and DBIM. Stage 1 scoped to a final cost of INR 3,000,000 inclusive of GST. Basis date 2026-09-01. Generated from the effort model — regenerate rather than edit cells.
THE PRICE
Final cost | INR 3,000,000 inclusive of GST at 18%
Contract value | INR 2,542,373 excluding GST
Effort | 179 person-days at P80, 24 weeks, 25 work packages
Supplier margin | 15.7% — reported, not hidden. Scope was cut until it fit the ceiling; the margin is what fell out. Below about 10% this stops being a viable engagement and the ceiling should move instead of the scope.
WHAT IT BUYS
Included | Everything in Offer A, plus a hand-decided redirect map covering every surviving path, a signed PDF disposition across ~2,758 documents, orphan recovery, CSP hardening, and the Stage 2 cost baseline as a contracted deliverable.
NOT included | The migration itself. Stage 2 remains a separate procurement and its figure here is indicative until this engagement re-derives it.
Not in either offer | The migration itself. Stage 2 is a separate procurement and is indicatively INR 207 person-days — around INR 27.8 lakh ex-GST — but that figure must be re-derived from this engagement's register before anyone commits to it.
TOOLING
Claude Max 20x | 1 seat x 6 months x USD 200/month at INR 95/USD = INR 114,000. Carried in the cost base and priced into the contract value above.
Price basis | Tier price per aipricing.guru and IntuitionLabs, September 2026. NOTE: claude.com/pricing itself lists Max as 'From $100 per month' without separating the 5x and 20x tiers, so confirm at purchase.
Tax treatment | Imported digital service (OIDAR). 18% IGST applies under reverse charge and is recoverable as input credit by a GST-registered supplier, so it is carried ex-tax in the cost base.
FX basis | USD/INR planning rate, September 2026 (spot band 94.6-95.8). Take a real quote at the day's rate.
What it is for | The analytical core of this engagement — reconciling four inventory sources, fingerprinting templates across the estate, and deciding redirect dispositions — is exactly the work an assistant accelerates. No productivity multiplier has been applied to the unit rates, because there is no evidence base for a specific one. The licence is carried as a cost the supplier bears, not as a discount to IPC.
HOW TO READ IT
Scope | Every package, and every package cut or resized to make the ceiling, shown side by side with the full Stage 1 scope.
Timeline | Gantt by week across 24 weeks. ◆ marks a milestone.
Milestones & Payments | Each paid against an exit criterion that can be failed.
Cash Flow | Cost against cash on a four-week payment lag. The peak negative position is working capital.
Resource Plan | Person-days and FTE by role and four-week period.
Charts | Live Gantt and resource-loading charts, driven by the data block to their right.
Commercials | Price build-up, rate card, and EMD, PBG and LD at IPC's own revealed rates.
SETTLE BEFORE SIGNING
Supplier tier | This price assumes a boutique or specialist supplier. IPC's own last IT tender (GEM/2026/B/7781379, 13-07-2026) demanded ISO 9001, ISO 27000 and CMMI Level 3 — a bar that excludes that tier. At mid-tier rates this scope is roughly 40% more. Resolve the procurement category before bidding, not at evaluation.
Client effort | 40–70 person-days of IPC subject-matter time for triage sign-off, tracked and never billed. 60–80% of a content audit is client-side and cannot be bought.

## Scope
Scope — what fits the ceiling and what does not
Design to cost, shown honestly: the full Stage 1 scope alongside what this offer carries. Anything cut here reappears in Stage 2, usually dearer.
Ref | Phase | Work package | Full O/M/P | This offer O/M/P | Expected PD | Status
0.1 | 0 · Mandate and decisions | Correct the brief; re-issue the objective in writing | 2/3/6 | 2/3/6 | 3.3333 | Full
0.2 | 0 · Mandate and decisions | Gov.In CMS intake via the MoHFW CIO route | 3/5/11 | 3/5/11 | 5.6667 | Full
0.4 | 0 · Mandate and decisions | registry.gov.in control and DNS readiness | 1/2/4 | 1/2/4 | 2.1667 | Full
0.5 | 0 · Mandate and decisions | Security-audit route settled in writing | 1/2/4 | 1/2/4 | 2.1667 | Full
0.6 | 0 · Mandate and decisions | Redirect-capability determination (pivotal) | 2/3/7 | 2/3/7 | 3.5 | Full
0.8 | 0 · Mandate and decisions | DBIM logo lockup 3A/3B determination | 0.5/1/2 | 0.5/1/2 | 1.0833 | Full
0.9 | 0 · Mandate and decisions | Destination status-code behaviour proven; origin status layer designed | 2/4/9 | 2/4/9 | 4.5 | Full
1.1 | 1 · Emergency remediation | Real HTTP 404: error-document status, not a 302 to a 200 page | 1.5/3/7 | 1.5/3/7 | 3.4167 | Full
1.2 | 1 · Emergency remediation | Charset: header says iso-8859-1 over 389 Hindi pages; header wins | 2/4/9 | 2/4/9 | 4.5 | Full
1.4 | 1 · Emergency remediation | GIGW policy pages and portal links (DBIM mandates no india.gov.in link) | 1/2/4 | 1/2/4 | 2.1667 | Full
1.6 | 1 · Emergency remediation | robots.txt and a stopgap sitemap | 0.5/1/2 | 0.5/1/2 | 1.0833 | Full
1.7 | 1 · Emergency remediation | CSP hardening on the live site | 2/4/10 | 2/4/10 | 4.6667 | Full
1.8 | 1 · Emergency remediation | lang="hi" across 389 Hindi pages; close the joomla.xml version disclosure | 1/2/5 | 1/2/5 | 2.3333 | Full
2.1 | 2 · Inventory and redirect map | Joomla database extraction and reconciliation | 2/4/10 | 2/4/10 | 4.6667 | Full
2.2 | 2 · Inventory and redirect map | Live crawl with the two-signal validator | 3/5/10 | 3/5/10 | 5.5 | Full
2.3 | 2 · Inventory and redirect map | Wayback / CommonCrawl orphan recovery | 2/3/7 | 2/3/7 | 3.5 | Full
2.4 | 2 · Inventory and redirect map | Search Console traffic overlay | 1/2/4 | 1/2/4 | 2.1667 | Full
2.5 | 2 · Inventory and redirect map | Union of four sources into one authoritative register | 2/3/7 | 2/3/7 | 3.5 | Full
2.6 | 2 · Inventory and redirect map | Triage facilitation — keep / archive / retire | 6/10/20 | 6/10/20 | 11 | Full
2.7 | 2 · Inventory and redirect map | PDF estate inventory and disposition (~2,758 documents) | 5/8/18 | 5/8/18 | 9.1667 | Full
2.8 | 2 · Inventory and redirect map | Redirect map — ~1,727 distinct source paths; rows exceed paths | 10/16/32 | 10/16/32 | 17.6667 | Full
2.9 | 2 · Inventory and redirect map | Hindi pairing by hreflang; bilingual gap quantified | 2/3/7 | 2/3/7 | 3.5 | Full
P.1a | P · Programme management | Programme and delivery management — Stage 1 | 8/13/24 | 8/13/24 | 14 | Full
P.2a | P · Programme management | Business analysis and content governance — Stage 1 | 5/8/15 | 5/8/15 | 8.6667 | Full
P.3a | P · Programme management | Documentation, SOPs and the Stage 2 cost baseline | 4/6/12 | 4/6/12 | 6.6667 | Full
|  | TOTAL | 130.6 PD expected | 130.6 PD expected | 130.5833 | 179 PD at P80

## Timeline
Timeline
24 weeks. Bars are scheduled weeks; ◆ marks a milestone. Phase 2 runs alongside Phase 1 rather than after it — the 302-to-404 behaviour is a usable existence oracle, so the inventory is not blocked on the 404 fix.
Ref | Work package | Phase | PD | Start | End | W1 | M1 | W3 | W4 | W5 | W6 | W7 | M2 | W9 | W10 | W11 | M3 | W13 | W14 | W15 | M4 | W17 | W18 | W19 | M5 | W21 | W22 | W23 | M6
0.1 | Correct the brief; re-issue the objective in writing | 0 · Mandate and decisions | 4.6 | 1 | 3
0.2 | Gov.In CMS intake via the MoHFW CIO route | 0 · Mandate and decisions | 7.8 | 2 | 12
0.4 | registry.gov.in control and DNS readiness | 0 · Mandate and decisions | 3 | 4 | 7
0.5 | Security-audit route settled in writing | 0 · Mandate and decisions | 3 | 5 | 9
0.6 | Redirect-capability determination (pivotal) | 0 · Mandate and decisions | 4.8 | 3 | 7
0.8 | DBIM logo lockup 3A/3B determination | 0 · Mandate and decisions | 1.5 | 6 | 10
0.9 | Destination status-code behaviour proven; origin status layer designed | 0 · Mandate and decisions | 6.2 | 4 | 9
1.1 | Real HTTP 404: error-document status, not a 302 to a 200 page | 1 · Emergency remediation | 4.7 | 3 | 6
1.2 | Charset: header says iso-8859-1 over 389 Hindi pages; header wins | 1 · Emergency remediation | 6.2 | 3 | 7
1.4 | GIGW policy pages and portal links (DBIM mandates no india.gov.in link) | 1 · Emergency remediation | 3 | 5 | 8
1.6 | robots.txt and a stopgap sitemap | 1 · Emergency remediation | 1.5 | 6 | 7
1.7 | CSP hardening on the live site | 1 · Emergency remediation | 6.4 | 4 | 8
1.8 | lang="hi" across 389 Hindi pages; close the joomla.xml version disclosure | 1 · Emergency remediation | 3.2 | 5 | 8
2.1 | Joomla database extraction and reconciliation | 2 · Inventory and redirect map | 6.4 | 3 | 7
2.2 | Live crawl with the two-signal validator | 2 · Inventory and redirect map | 7.5 | 3 | 6
2.3 | Wayback / CommonCrawl orphan recovery | 2 · Inventory and redirect map | 4.8 | 5 | 8
2.4 | Search Console traffic overlay | 2 · Inventory and redirect map | 3 | 6 | 9
2.5 | Union of four sources into one authoritative register | 2 · Inventory and redirect map | 4.8 | 8 | 11
2.6 | Triage facilitation — keep / archive / retire | 2 · Inventory and redirect map | 15.1 | 10 | 19
2.7 | PDF estate inventory and disposition (~2,758 documents) | 2 · Inventory and redirect map | 12.5 | 11 | 18
2.8 | Redirect map — ~1,727 distinct source paths; rows exceed paths | 2 · Inventory and redirect map | 24.2 | 13 | 20
2.9 | Hindi pairing by hreflang; bilingual gap quantified | 2 · Inventory and redirect map | 4.8 | 9 | 13
P.1a | Programme and delivery management — Stage 1 | P · Programme management | 19.2 | 1 | 24
P.2a | Business analysis and content governance — Stage 1 | P · Programme management | 11.9 | 2 | 22
P.3a | Documentation, SOPs and the Stage 2 cost baseline | P · Programme management | 9.1 | 18 | 24

## Milestones & Payments
Milestones and payment schedule
Contract value INR 2,542,373 ex-GST, INR 3,000,000 inclusive. Every milestone is paid against a checkable exit criterion, not a date.
Ref | Week | Milestone | Share | Ex-GST (INR) | Payable inc-GST (INR) | Cumulative ex-GST (INR)
M1 | 2 | Mobilisation and inception report | 10% | 254237.2881 | 300000 | 254237.2881
M2 | 8 | Live site remediated | 20% | 508474.5763 | 600000 | 762711.8644
M3 | 12 | Platform decision pack | 15% | 381355.9322 | 450000 | 1144067.7966
M4 | 16 | Draft inventory: the union register | 20% | 508474.5763 | 600000 | 1652542.3729
M5 | 20 | Signed disposition register and redirect map | 25% | 635593.2203 | 750000 | 2288135.5932
M6 | 24 | Stage 2 cost baseline and handover | 10% | 254237.2881 | 300000 | 2542372.8814
|  | TOTAL | 100% | 2542372.8814 | 3000000
EXIT CRITERIA — what must be true before each invoice is raised
M1 · Week 2 · Mobilisation and inception report
Exit criterion | Team named and on site. Inception report accepted: scope, RACI, access list, and the written re-statement of the objective as adopting DBIM and the Gov.In CMS Platform rather than 'moving to india.gov.in'.
Evidence | Signed inception report; access requests lodged for the Joomla database, Search Console and registry.gov.in.
M2 · Week 8 · Live site remediated
Exit criterion | A missing path returns a genuine HTTP 404 under both a browser and a bare user agent. Header charset is UTF-8 and Devanagari renders. All 389 Hindi pages declare lang="hi". CSP no longer carries a wildcard with unsafe-inline and unsafe-eval. robots.txt published. joomla.xml no longer publicly readable.
Evidence | Automated assertion suite, run in front of the client, with before-and-after captures. Every item destination-independent.
M3 · Week 12 · Platform decision pack
Exit criterion | Written intake position from the MoHFW CIO, or a signed decision to take the DBIM-aligned rebuild instead. Redirect capability and destination status-code behaviour proven and documented, with the origin status-layer design if needed. Audit route settled in writing. S3WaaS ruled in or out on the record. DBIM logo lockup determined. registry.gov.in control confirmed.
Evidence | Decision pack with one signed page per question, each with a named owner and a date.
M4 · Week 16 · Draft inventory: the union register
Exit criterion | One register unioning the Joomla database, a live two-signal crawl, Wayback and Common Crawl orphans, and Search Console traffic. Every URL appears exactly once, live-validated, with language tree, template and title. Hindi paired by hreflang, never by URL transformation.
Evidence | Register delivered as a checked-in dataset with the crawl and validation code that produced it, so the client can re-run it.
M5 · Week 20 · Signed disposition register and redirect map
Exit criterion | Every verified URL carries a keep / archive / retire disposition signed by a named IPC content owner, including explicit dispositions for PvPI, the news archive, the legacy paths and the PDF estate. Redirect map complete: one decided row per surviving source path, with Hindi rows byte-verified through the real toolchain.
Evidence | Signed CSV. Automated check that every source path resolves to exactly one row and no destination is unreachable.
M6 · Week 24 · Stage 2 cost baseline and handover
Exit criterion | Stage 2 re-costed from the delivered register rather than from estimate, with quantities, rates and a three-point spread. Operating documentation and SOPs handed over. Recurring obligations listed with named owners.
Evidence | Stage 2 baseline document plus the re-runnable model. This is the deliverable that makes Stage 2 procurable.

## Cash Flow
Cash flow
Cost is incurred as effort is spent; cash arrives four weeks after a milestone is certified. The licence is paid monthly from week 1 whatever the billing schedule does.
Period | Weeks | PD spent | Cost incurred (INR) | Billed inc-GST (INR) | Cash received (INR) | Cumulative cost (INR) | Net position (INR)
P1 | W1–W4 | 27.6 | 417573.5085 | 300000 | 0 | 417573.5085 | -417573.5085
P2 | W5–W8 | 55.3 | 616555.4593 | 600000 | 300000 | 1034128.9677 | -734128.9677
P3 | W9–W12 | 26.3 | 303081.2692 | 450000 | 600000 | 1337210.2369 | -437210.2369
P4 | W13–W16 | 30.8 | 351577.6692 | 600000 | 450000 | 1688787.9061 | -338787.9061
P5 | W17–W20 | 29.1 | 333330.5327 | 750000 | 600000 | 2022118.4388 | -72118.4388
P6 | W21–W24 | 9.5 | 121995.7298 | 300000 | 750000 | 2144114.1686 | 555885.8314
P7 | W25–W28 | 0 | 0 | 0 | 300000 | 2144114.1686 | 855885.8314
Blended rate |  |  | 10800.4825 | INR/PD — an output of the role mix, not an input
Licence in the cost base |  |  | 114000 | Claude Max 20x, 6 months
Peak negative position |  |  | -734128.9677 | Working capital, not margin
Peak as share of contract |  |  | -28.88% | Ask for a mobilisation advance if uncomfortable

## Resource Plan
Resource plan
Person-days by role and four-week period, derived from each package's own role mix. One period = 20 working days.
Ref | Role | INR/PD | Total PD | P1 | P2 | P3 | P4 | P5 | P6
ME | Migration Engineer | 8640 | 65.883 | 10.9014 | 26.6759 | 4.5332 | 10.3894 | 10.7763 | 2.6067
BA | Content Strategist / Business Analyst | 9360 | 55.1173 | 2.4607 | 7.1493 | 11.9175 | 15.6228 | 14.2306 | 3.7363
EL | Engagement Lead / Programme Manager | 15840 | 29.6741 | 6.9878 | 5.3148 | 5.6843 | 4.3975 | 4.0964 | 3.1932
SA | Solution Architect — Gov.In CMS / DBIM | 17280 | 12.3965 | P1: 4.5449; P2: 5.6319; P3: 2.2197
SE | Security Engineer | 14400 | 7.0935 | P1: 1.0629; P2: 5.6155; P3: 0.41512
QA | QA Engineer | 6840 | 3.8661 | P1: 1.6867; P2: 2.1794
CO | Content Operations / Editorial support | 5400 | 3.3985 | P2: 1.4826; P3: 1.5327; P4: 0.38319
AX | Accessibility Specialist | 10800 | 1.2773 | P2: 1.2773
| TOTAL PD |  | 178.7063 | 27.6445 | 55.3267 | 26.3026 | 30.7929 | 29.1034 | 9.5362
| FTE |  |  | 1.3822 | 2.7663 | 1.3151 | 1.5396 | 1.4552 | 0.47681

## Charts
Charts
Live Excel charts driven by the data block in column T. A Gantt here is a stacked bar whose first series is invisible and carries the start week.
| Item | Start-1 | Duration
| 0.1 Correct the brief; re-issue the objective | 0 | 3
| P.1a Programme and delivery management — Stage | 0 | 24
| 0.2 Gov.In CMS intake via the MoHFW CIO route | 1 | 11
| P.2a Business analysis and content governance — | 1 | 21
| 0.6 Redirect-capability determination (pivotal | 2 | 5
| 1.1 Real HTTP 404: error-document status, not | 2 | 4
| 1.2 Charset: header says iso-8859-1 over 389 H | 2 | 5
| 2.1 Joomla database extraction and reconciliat | 2 | 5
| 2.2 Live crawl with the two-signal validator | 2 | 4
| 0.4 registry.gov.in control and DNS readiness | 3 | 4
| 0.9 Destination status-code behaviour proven; | 3 | 6
| 1.7 CSP hardening on the live site | 3 | 5
| 0.5 Security-audit route settled in writing | 4 | 5
| 1.4 GIGW policy pages and portal links (DBIM m | 4 | 4
| 1.8 lang="hi" across 389 Hindi pages; close th | 4 | 4
| 2.3 Wayback / CommonCrawl orphan recovery | 4 | 4
| 0.8 DBIM logo lockup 3A/3B determination | 5 | 5
| 1.6 robots.txt and a stopgap sitemap | 5 | 2
| 2.4 Search Console traffic overlay | 5 | 4
| 2.5 Union of four sources into one authoritati | 7 | 4
| 2.9 Hindi pairing by hreflang; bilingual gap q | 8 | 5
| 2.6 Triage facilitation — keep / archive / ret | 9 | 10
| 2.7 PDF estate inventory and disposition (~2,7 | 10 | 8
| 2.8 Redirect map — ~1,727 distinct source path | 12 | 8
| P.3a Documentation, SOPs and the Stage 2 cost b | 17 | 7
| Role | P1 | P2 | P3 | P4 | P5 | P6
| Migration Engineer | 10.9 | 26.68 | 4.53 | 10.39 | 10.78 | 2.61
| Content Strategist / Business Analyst | 2.46 | 7.15 | 11.92 | 15.62 | 14.23 | 3.74
| Engagement Lead / Programme Manager | 6.99 | 5.31 | 5.68 | 4.4 | 4.1 | 3.19
| Solution Architect — Gov.In CMS / DBIM | 4.54 | 5.63 | 2.22 | 0 | 0 | 0
| Security Engineer | 1.06 | 5.62 | 0.42 | 0 | 0 | 0
| QA Engineer | 1.69 | 2.18 | 0 | 0 | 0 | 0
| Content Operations / Editorial support | 0 | 1.48 | 1.53 | 0.38 | 0 | 0
| Accessibility Specialist | 0 | 1.28 | 0 | 0 | 0 | 0

## Commercials
Commercials
Price built up from the bottom, so every rupee is traceable. Rates are boutique tier; commercial terms are IPC's own revealed rates from GEM/2026/B/7781379.
PRICE BUILD-UP
Effort at P80 |  | 178.7063 |  | person-days, 25 packages
Blended rate |  | 10800.4825 |  | INR/PD, boutique tier, output of the role mix
Effort cost |  | 1930114.1686
Claude Max 20x licence |  | 114000 |  | 6 months x USD 200 at INR 95/USD
Tooling and data |  | 100000 |  | Crawl and validation tooling, commercial traffic data
Total cost |  | 2144114.1686
Margin |  | 15.66% |  | Solved so the contract lands exactly on the ceiling
Contract value ex-GST |  | 2542372.8814
GST at 18% |  | 457627.1186 |  | Verify whether IPC can claim input credit
FINAL COST INC-GST |  | 3000000 |  | The stated ceiling
RATE CARD — boutique tier
Ref | Role | INR/PD | PD | Note
ME | Migration Engineer | 8640 | 65.883 | Crawler, two-signal validator, transforms, redirect map, cut-over.
BA | Content Strategist / Business Analyst | 9360 | 55.1173 | Owns the inventory, the triage facilitation and the disposition register.
EL | Engagement Lead / Programme Manager | 15840 | 29.6741 | Client-facing; owns the CIO route and the decision gates.
SA | Solution Architect — Gov.In CMS / DBIM | 17280 | 12.3965 | Scarce skill; the platform-specific knowledge is the whole reason to hire outside.
SE | Security Engineer | 14400 | 7.0935 | CSP, patching, pre-audit clearance, CERT-In liaison.
QA | QA Engineer | 6840 | 3.8661 | Assertion suites; every redirect row is a test.
CO | Content Operations / Editorial support | 5400 | 3.3985 | Bulk load, alt text, metadata. The line most safely moved to IPC's own team.
AX | Accessibility Specialist | 10800 | 1.2773 | WCAG 2.1 AA; 50 of GIGW 3.0's 88 guidelines.
COMMERCIAL TERMS
Item | Rate | Value (INR) |  | Note
Earnest money deposit | 4% | 101694.9153 |  | IPC's own revealed rate on GEM/2026/B/7781379 (13-07-2026), against a GeM recommendation of 1%. Refundable, but it blocks working capital through evaluation.
Performance bank guarantee | 5% | 127118.6441 |  | IPC's revealed rate, held 60 months on its last IT bid. For a 5.5-month assignment, negotiate the term down — a 60-month PBG on a 24-week engagement is a real and avoidable carrying cost.
PBG carrying cost per annum | 1.5% | 1906.7797 |  | Bank commission. Routinely forgotten in pricing.
Liquidated damages cap | 10% | 254237.2881 |  | Convention is 0.5% per week of delay capped at 10%. This is the schedule risk expressed in rupees.
Retention against M6 | 10% | 254237.2881 |  | M6 is itself 10% and is the natural retention. Do not stack a further retention on top of it.