## Read Me
IPC website migration — programme estimate
ipc.gov.in onto the Gov.In CMS Platform and DBIM. Basis date 2026-09-01. Generated from the effort model by Estimation/model/build_programme.py — regenerate rather than edit cells, or this workbook and the model will drift apart.
THE ANSWER
Stage 1 — the recommendation | Remediate the live site and produce the signed inventory and redirect map. 179 PD at P80 over 24 weeks. INR 2,388,290 ex-GST. This is what a 20-30 lakh budget buys.
Stage 2 — indicative only | Migrate, audit and cut over. 207 PD at P80 over 40 weeks. INR 2,775,579 ex-GST. Do not commit to this figure: it must be re-derived from Stage 1's register, which is what milestone M6 delivers.
Options — none included | 621 PD at P80, INR 5,698,132 ex-GST if all were taken. Dominated by hand-keying, because the destination has no bulk import. Each is a separate sponsor decision.
Programme elapsed | 76 weeks (17.5 months): 24 weeks of Stage 1, 12 weeks to procure Stage 2, 40 weeks of Stage 2.
HOW TO READ IT
Programme Summary | All three stages side by side — effort, cost, price, duration, and what each one buys.
Programme Timeline | Master Gantt across all 76 weeks. Bar colour is the phase; the grey band is the procurement gap between stages.
Milestones & Payments | Twelve milestones across both stages, each with an exit criterion that can be failed and the evidence that closes it.
Cash Flow | Cost incurred against cash received on a four-week payment lag, across the whole programme.
Resource Plan | Person-days and FTE by role and four-week period, derived from each package's own role mix.
Work Packages | All packages with three-point estimates and scheduled weeks, including the four handed back to IPC and NIC.
Options & Exclusions | The priced options, and the statutory costs that genuinely cannot be priced yet.
Confidence | Percentiles, the correlation assumption and its sensitivity, and where the uncertainty actually lives.
Rate Card & Commercials | Roles and rates, the supplier-tier envelope test, and EMD, PBG and LD at IPC's own revealed rates.
Charts | Four live Excel charts: a phase-level Gantt, a package-level Gantt across all 49 packages, resource loading stacked by role, and team size in FTE. Their backing data sits to the right in column AD — edit it and the charts move.
UNITS
PD — person-day | One person for one day. 21 PD make a person-month; 20 PD make one four-week period at five days a week.
P80 | Four engagements in five finish at or below this effort. The standard basis for a fixed-price government contract. P50 is even odds and should never be bid.
INR lakh | One hundred thousand rupees. Payment values are given in full rupees so they can be transcribed into a purchase order.
Ex-GST / inc-GST | Contract value before and after GST at 18%. Verify whether IPC can claim input credit as an autonomous body — if not, GST is a real cost to the buyer.
THREE THINGS TO SETTLE BEFORE SIGNING
Supplier tier | This price assumes a boutique or specialist supplier. IPC's own last IT tender (GEM/2026/B/7781379, 13-07-2026) demanded ISO 9001, ISO 27000 and CMMI Level 3 — a bar that excludes that tier. At mid-tier rates Stage 1 is roughly INR 33 lakh. Resolve the procurement category before bidding, not at evaluation.
How much content survives | The destination has no bulk import, and MoHFW — IPC's own ministry — carried across 28 pages and no documents at all. Against IPC's 1,084 items and 2,758 PDFs, triage is the whole project rather than a tidying step. This single answer swings the options by hundreds of person-days.
Performance guarantee term | IPC's revealed ePBG was 5% held for 60 months. On a 24-week assignment that is a five-year guarantee against a six-month job. Negotiate the term, not only the rate.
WHAT MOVED IN THE SCHEDULE | Phase 2 starts in week 3, in parallel with Phase 1 rather than after it. The 302-to-404 behaviour measured on 2026-09-01 is a usable existence oracle, so the inventory is not blocked on the 404 fix — which removes roughly six weeks from the plan's original sequencing.
THE GAP BETWEEN STAGES | Stage 2 cannot be procured until Stage 1 delivers the baseline that makes it costable. Twelve weeks is the planning figure for that gap: IPC's last bid ran 11 days from publication to close, but carried 180 days of bid validity, and the governance chain — Secretary, then Chairman of the Governing Body, then the Governing Body — is the long pole. Range 8 to 16 weeks. This gap is where programmes lose time, so it is drawn rather than hidden.

## Programme Summary
Programme summary
Boutique tier, 15% margin, P80. Stage 2 is indicative and must be re-derived from Stage 1's register before it is committed to.
Stage | What it buys | Packages | PD (P80) | Weeks | Blended INR/PD | Ex-GST (INR) | Inc-GST (INR)
Stage 1 · Remediate and baseline | Real 404s, UTF-8, CSP, lang. One signed inventory. One decided redirect map. A Stage 2 cost baseline. | 25 | 178.7 | 24 | 10800.4825 | 2388289.6634 | 2818181.8028
Procurement gap | Stage 2 cannot be procured until Stage 1 makes it costable. Range 8–16 weeks. |  |  | 12
Stage 2 · Migrate and cut over | Platform tenancy, IA, content load, accessibility, audit clearance, cut-over, hypercare. | 24 | 206.8 | 40 | 10924.7682 | 2775578.9014 | 3275183.1037
Options · not included | Hand authoring, document loading, PDF remediation, translation, applications replatform, STQC, IAAP. | 9 | 621.2 |  | 7796.864 | 5698131.6814 | 6723795.3841
Stage 1 + Stage 2, as two contracts |  | 49 | 385.5 | 76 |  | 5163868.5649 | 6093364.9065
Everything, options included |  | 58 | 1006.7 | 76 |  | 10862000.2463 | 12817160.2906
Not in any figure above
STQC Certified Quality Website fee | No GIGW 3.0 tariff is published — The circulating INR 40,000 is real but its own section 6.1 scopes it to GIGW version 2009 and 87 test points. Obtain a written quote from the assigned STQC IT Laboratory, payable via Bharatkosh.
CERT-In empanelled security audit | Bimodal: zero or lakhs — GIGW 3.0 accepts clearance from NIC, STQC or a CERT-In empanelled vendor. If NIC performs it the line is zero. If procured, no Indian government body publishes a VAPT rate card and it goes to quotation.
IAAP Certified Auditor Review Report | Unpriced, and newly mandatory — STQC OM F.No. STQC/IT&eGov/WQC/2022 dated 30.06.2025 makes it a pre-requisite for GIGW evaluation. Commencement language is equivocal - confirm before relying on the date.
…and four more | See the Options & Exclusions sheet.
Client effort | 40–70 person-days of IPC subject-matter time for Stage 1 triage sign-off, and a content-authoring commitment in Stage 2. Tracked, never billed, and not purchasable: 60–80% of a content audit is client-side. An under-resourced client is a schedule risk that first presents itself as a cost saving.

## Programme Timeline
Programme timeline
76 weeks. Stage 1 W1–W24; procurement gap W25–W36; Stage 2 W37–W76. ◆ marks a milestone.
Ref | Work package | Phase | PD | Start | End | 1 | M1 | 3 | 4 | 5 | 6 | 7 | M2 | 9 | 10 | 11 | M3 | 13 | 14 | 15 | M4 | 17 | 18 | 19 | M5 | 21 | 22 | 23 | M6 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | N1 | 41 | 42 | 43 | 44 | 45 | N2 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | N3 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | N4 | 71 | 72 | N5 | 74 | 75 | N6
STAGE 1 · Remediate and baseline · W1–W24 · 179 PD
0.1 | Correct the brief; re-issue the objective in writing | 0 · Mandate and decisions | 4.6 | 1 | 3
0.2 | Gov.In CMS intake via the MoHFW CIO route | 0 · Mandate and decisions | 7.8 | 2 | 12
0.4 | registry.gov.in control and DNS readiness | 0 · Mandate and decisions | 3 | 4 | 7
0.5 | Security-audit route settled in writing | 0 · Mandate and decisions | 3 | 5 | 9
0.6 | Redirect-capability determination (pivotal) | 0 · Mandate and decisions | 4.8 | 3 | 7
0.8 | DBIM logo lockup 3A/3B determination | 0 · Mandate and decisions | 1.5 | 6 | 10
0.9 | Destination status-code behaviour proven; origin status layer designed | 0 · Mandate and decisions | 6.2 | 4 | 9
1.1 | Real HTTP 404: error-document status, not a 302 to a 200 page | 1 · Emergency remediation | 4.7 | 3 | 6
1.2 | Charset: header says iso-8859-1 over 389 Hindi pages; header wins | 1 · Emergency remediation | 6.2 | 3 | 7
1.4 | GIGW policy pages and portal links (DBIM mandates no india.gov.in link) | 1 · Emergency remediation | 3 | 5 | 8
1.6 | robots.txt and a stopgap sitemap | 1 · Emergency remediation | 1.5 | 6 | 7
1.7 | CSP hardening on the live site | 1 · Emergency remediation | 6.4 | 4 | 8
1.8 | lang="hi" across 389 Hindi pages; close the joomla.xml version disclosure | 1 · Emergency remediation | 3.2 | 5 | 8
2.1 | Joomla database extraction and reconciliation | 2 · Inventory and redirect map | 6.4 | 3 | 7
2.2 | Live crawl with the two-signal validator | 2 · Inventory and redirect map | 7.5 | 3 | 6
2.3 | Wayback / CommonCrawl orphan recovery | 2 · Inventory and redirect map | 4.8 | 5 | 8
2.4 | Search Console traffic overlay | 2 · Inventory and redirect map | 3 | 6 | 9
2.5 | Union of four sources into one authoritative register | 2 · Inventory and redirect map | 4.8 | 8 | 11
2.6 | Triage facilitation — keep / archive / retire | 2 · Inventory and redirect map | 15.1 | 10 | 19
2.7 | PDF estate inventory and disposition (~2,758 documents) | 2 · Inventory and redirect map | 12.5 | 11 | 18
2.8 | Redirect map — ~1,727 distinct source paths; rows exceed paths | 2 · Inventory and redirect map | 24.2 | 13 | 20
2.9 | Hindi pairing by hreflang; bilingual gap quantified | 2 · Inventory and redirect map | 4.8 | 9 | 13
P.1a | Programme and delivery management — Stage 1 | P · Programme management | 19.2 | 1 | 24
P.2a | Business analysis and content governance — Stage 1 | P · Programme management | 11.9 | 2 | 22
P.3a | Documentation, SOPs and the Stage 2 cost baseline | P · Programme management | 9.1 | 18 | 24
PROCUREMENT GAP · W25–W36 · Stage 2 is re-costed from Stage 1's register, then procured
STAGE 2 · Migrate and cut over · W37–W76 · 207 PD
3.1 | IA re-expression into the platform's flat structure | 3 · Build and content load | 10.5 | 37 | 42
3.10 | Search configuration and relevance | 3 · Build and content load | 4.6 | 50 | 54
3.11 | Applications disposition — scoping only | 3 · Build and content load | 8 | 40 | 46
3.12 | .सरकार.भारत IDN registration and configuration (registry fee nil) | 3 · Build and content load | 3 | 52 | 55
3.14 | Editorial training and standard operating procedures | 3 · Build and content load | 7.5 | 52 | 58
3.2 | Template mapping and the CCPS banner slot | 3 · Build and content load | 7.8 | 39 | 44
3.3 | Platform configuration, roles, editorial workflow | 3 · Build and content load | 7.5 | 38 | 43
3.4 | Content mapping, authoring supervision and QA — no bulk import exists | 3 · Build and content load | 15.5 | 42 | 56
3.5 | Content load — Hindi, byte-verified | 3 · Build and content load | 6.2 | 48 | 54
3.7 | Document register: categorisation scheme, priority tiers, bilingual flags | 3 · Build and content load | 9.4 | 43 | 50
3.9 | Accessibility conformance — 9 templates, one covering 83% of pages | 3 · Build and content load | 13.9 | 46 | 58
4.1 | Pre-audit hardening and pre-clearance of the obvious | 4 · Audit and clearance | 7.8 | 57 | 61
4.2 | Auditor procurement and pre-audit paperwork | 4 · Audit and clearance | 4.8 | 54 | 62
4.3 | VAPT cycle 1 and remediation | 4 · Audit and clearance | 11 | 62 | 67
4.4 | Retest and closure | 4 · Audit and clearance | 5 | 67 | 69
4.5 | Audit clearance documentation | 4 · Audit and clearance | 4.6 | 68 | 70
5.1 | Cut-over runbook: one A-record, MX untouchable | 5 · Cut-over and hypercare | 6.2 | 66 | 71
5.2 | Redirect layer live; every row asserted automatically | 5 · Cut-over and hypercare | 7.8 | 69 | 72
5.3 | Sitemap, robots and Search Console submission | 5 · Cut-over and hypercare | 3 | 71 | 73
5.4 | IGOD refresh and India Portal depository records | 5 · Cut-over and hypercare | 4.8 | 70 | 74
5.5 | Hypercare and 404-log review | 5 · Cut-over and hypercare | 12.1 | 72 | 76
P.1b | Programme and delivery management — Stage 2 | P · Programme management | 23.7 | 37 | 76
P.2b | Business analysis and content governance — Stage 2 | P · Programme management | 14.8 | 37 | 74
P.3b | Documentation, SOPs and handover — Stage 2 | P · Programme management | 7.5 | 68 | 76
Phase key
Mandate and decisions
Emergency remediation
Inventory and redirect map
Build and content load
Audit and clearance
Cut-over and hypercare
Programme management
Procurement gap — no supplier effort

## Milestones & Payments
Milestones and payment schedule
Twelve milestones across two separately contracted stages. Every one is paid against a checkable exit criterion, not a date — a milestone that cannot be failed is not a milestone.
Ref | Prog. week | Milestone | Share of stage | Ex-GST (INR) | GST (INR) | Payable inc-GST (INR) | Cumulative programme (INR)
STAGE 1 · contract value INR 2,388,290 ex-GST
M1 | 2 | Mobilisation and inception report | 10% | 238828.9663 | 42989.2139 | 281818.1803 | 238828.9663
M2 | 8 | Live site remediated | 20% | 477657.9327 | 85978.4279 | 563636.3606 | 716486.899
M3 | 12 | Platform decision pack | 15% | 358243.4495 | 64483.8209 | 422727.2704 | 1074730.3485
M4 | 16 | Draft inventory: the union register | 20% | 477657.9327 | 85978.4279 | 563636.3606 | 1552388.2812
M5 | 20 | Signed disposition register and redirect map | 25% | 597072.4159 | 107473.0349 | 704545.4507 | 2149460.6971
M6 | 24 | Stage 2 cost baseline and handover | 10% | 238828.9663 | 42989.2139 | 281818.1803 | 2388289.6634
STAGE 2 · contract value INR 2,775,579 ex-GST
N1 | 40 | Mobilisation and platform tenancy live | 10% | 277557.8901 | 49960.4202 | 327518.3104 | 2665847.5536
N2 | 46 | Information architecture and templates approved | 15% | 416336.8352 | 74940.6303 | 491277.4656 | 3082184.3888
N3 | 58 | Content loaded and staging frozen | 25% | 693894.7254 | 124901.0506 | 818795.7759 | 3776079.1141
N4 | 70 | Audit clearance certificate issued | 20% | 555115.7803 | 99920.8405 | 655036.6207 | 4331194.8944
N5 | 73 | Cut-over complete and redirects asserted | 20% | 555115.7803 | 99920.8405 | 655036.6207 | 4886310.6747
N6 | 76 | Hypercare complete and handover | 10% | 277557.8901 | 49960.4202 | 327518.3104 | 5163868.5649
|  | PROGRAMME TOTAL |  | 5163868.5649 | 929496.3417 | 6093364.9065
EXIT CRITERIA — what has to be true before each invoice is raised
M1 · programme week 2 · Mobilisation and inception report
Exit criterion | Team named and on site. Inception report accepted: scope, RACI, access list, and the written re-statement of the objective as adopting DBIM and the Gov.In CMS Platform rather than 'moving to india.gov.in'.
Evidence | Signed inception report; access requests lodged for the Joomla database, Search Console and registry.gov.in.
M2 · programme week 8 · Live site remediated
Exit criterion | A missing path returns a genuine HTTP 404 under both a browser and a bare user agent. Header charset is UTF-8 and Devanagari renders. All 389 Hindi pages declare lang="hi". CSP no longer carries a wildcard with unsafe-inline and unsafe-eval. robots.txt published. joomla.xml no longer publicly readable.
Evidence | Automated assertion suite, run in front of the client, with before-and-after captures. Every item destination-independent.
M3 · programme week 12 · Platform decision pack
Exit criterion | Written intake position from the MoHFW CIO, or a signed decision to take the DBIM-aligned rebuild instead. Redirect capability and destination status-code behaviour proven and documented, with the origin status-layer design if needed. Audit route settled in writing. S3WaaS ruled in or out on the record. DBIM logo lockup determined. registry.gov.in control confirmed.
Evidence | Decision pack with one signed page per question, each with a named owner and a date.
M4 · programme week 16 · Draft inventory: the union register
Exit criterion | One register unioning the Joomla database, a live two-signal crawl, Wayback and Common Crawl orphans, and Search Console traffic. Every URL appears exactly once, live-validated, with language tree, template and title. Hindi paired by hreflang, never by URL transformation.
Evidence | Register delivered as a checked-in dataset with the crawl and validation code that produced it, so the client can re-run it.
M5 · programme week 20 · Signed disposition register and redirect map
Exit criterion | Every verified URL carries a keep / archive / retire disposition signed by a named IPC content owner, including explicit dispositions for PvPI, the news archive, the legacy paths and the PDF estate. Redirect map complete: one decided row per surviving source path, with Hindi rows byte-verified through the real toolchain.
Evidence | Signed CSV. Automated check that every source path resolves to exactly one row and no destination is unreachable.
M6 · programme week 24 · Stage 2 cost baseline and handover
Exit criterion | Stage 2 re-costed from the delivered register rather than from estimate, with quantities, rates and a three-point spread. Operating documentation and SOPs handed over. Recurring obligations listed with named owners.
Evidence | Stage 2 baseline document plus the re-runnable model. This is the deliverable that makes Stage 2 procurable.
N1 · programme week 40 · Mobilisation and platform tenancy live
Exit criterion | Gov.In CMS tenancy provisioned at cms-ipc.digifootprint.gov.in with named editor accounts and roles. Stage 1's signed register loaded as the working backlog. DBIM logo lockup applied.
Evidence | Tenancy reachable, roles demonstrated, register imported and row-counted against the Stage 1 sign-off.
N2 · programme week 46 · Information architecture and templates approved
Exit criterion | IPC's deep Joomla trees re-expressed in the platform's flat structure and signed off. Template mapping complete across the nine source templates. CCPS banner slot reserved in the first wireframe, not retrofitted. Applications boundary decided in writing for /shop, /e-services, PvPI, iponline and onlinestore.
Evidence | Approved IA document; wireframes showing the CCPS slot; a signed applications scope decision.
N3 · programme week 58 · Content loaded and staging frozen
Exit criterion | Every item with a keep disposition is live on staging with alt text and heading structure present at import, not retrofitted. Hindi byte-verified through the real toolchain. WCAG 2.1 AA passes on a stratified sample covering every template plus 10% of pages. Staging frozen — GIGW 5.3.1 requires audit clearance before production hosting and the auditor must test a frozen instance.
Evidence | Freeze declared in writing with a build identifier. Accessibility report against the stratified sample.
N4 · programme week 70 · Audit clearance certificate issued
Exit criterion | Audit clearance certificate naming the specific frozen instance, from NIC, STQC or a CERT-In empanelled vendor. Every finding closed or formally accepted by the Web Information Manager. Zero code changes after retest — any change reopens the obligation.
Evidence | The certificate itself, plus a findings register with a disposition against every row.
N5 · programme week 73 · Cut-over complete and redirects asserted
Exit criterion | One A-record changed at registry.gov.in; MX records untouched and a post-cut-over mail delivery test passed. 100% of redirect rows return a 301 to a 200, asserted automatically. Retired paths return 404 or 410, never 200 — via the origin status layer if the destination still answers 200 at shallow depths. Sitemap and robots.txt published and accepted in Search Console.
Evidence | Automated redirect assertion run over every row; mail test transcript; Search Console acceptance.
N6 · programme week 76 · Hypercare complete and handover
Exit criterion | Four to six weeks of hypercare with the 404 log reviewed weekly and fixes applied. IGOD entry refreshed and India Portal depository records contributed. Every recurring obligation — security re-audit cadence, content review cycle, surveillance — carries a named owner and a calendar entry.
Evidence | 404-log review record; IGOD entry; a signed obligations register with owners.

## Cash Flow
Cash flow
Cost is incurred as effort is spent; cash arrives four weeks after a milestone is certified. The peak negative position is working capital, not margin — and on engagements this size it decides whether a small supplier can take the work at all.
Period | Weeks | Stage | PD spent | Cost incurred (INR) | Billed inc-GST (INR) | Cash received (INR) | Cumulative cost (INR) | Net position (INR)
P1 | W1–W4 | Stage 1 | 27.6 | 398562.9964 | 281818.1803 | 0 | 398562.9964 | -398562.9964
P2 | W5–W8 | Stage 1 | 55.3 | 597534.4208 | 563636.3606 | 281818.1803 | 996097.4172 | -714279.2369
P3 | W9–W12 | Stage 1 | 26.3 | 284071.2674 | 422727.2704 | 563636.3606 | 1280168.6845 | -434714.1437
P4 | W13–W16 | Stage 1 | 30.8 | 332565.9599 | 563636.3606 | 422727.2704 | 1612734.6444 | -344552.8332
P5 | W17–W20 | Stage 1 | 29.1 | 314319.4659 | 704545.4507 | 563636.3606 | 1927054.1104 | -95235.9385
P6 | W21–W24 | Stage 1 | 9.5 | 102992.1036 | 281818.1803 | 704545.4507 | 2030046.2139 | 506317.4086
P7 | W25–W28 | Gap | 0 | 0 | 0 | 281818.1803 | 2030046.2139 | 788135.5889
P8 | W29–W32 | Gap | 0 | 0 | 0 | 0 | 2030046.2139 | 788135.5889
P9 | W33–W36 | Gap | 0 | 0 | 0 | 0 | 2030046.2139 | 788135.5889
P10 | W37–W40 | Stage 2 | 18.4 | 301342.12 | 327518.3104 | 0 | 2331388.3339 | 486793.4689
P11 | W41–W44 | Stage 2 | 26.4 | 288245.6366 | 0 | 327518.3104 | 2619633.9705 | 526066.1427
P12 | W45–W48 | Stage 2 | 19.1 | 208991.1238 | 491277.4656 | 0 | 2828625.0943 | 317075.0189
P13 | W49–W52 | Stage 2 | 22.8 | 248834.6331 | 0 | 491277.4656 | 3077459.7274 | 559517.8514
P14 | W53–W56 | Stage 2 | 24.1 | 262994.9724 | 0 | 0 | 3340454.6998 | 296522.8789
P15 | W57–W60 | Stage 2 | 16.6 | 181010.2385 | 818795.7759 | 0 | 3521464.9383 | 115512.6405
P16 | W61–W64 | Stage 2 | 12 | 131436.9479 | 0 | 818795.7759 | 3652901.8862 | 802871.4685
P17 | W65–W68 | Stage 2 | 18.2 | 198848.4753 | 0 | 0 | 3851750.3615 | 604022.9931
P18 | W69–W72 | Stage 2 | 30.1 | 329016.7268 | 655036.6207 | 0 | 4180767.0884 | 275006.2663
P19 | W73–W76 | Stage 2 | 19.1 | 208521.1918 | 982554.9311 | 655036.6207 | 4389288.2801 | 721521.6953
P20 | W77–W80 | Stage 2 | 0 | 0 | 0 | 982554.9311 | 4389288.2801 | 1704076.6264
Stage 1 blended rate |  |  |  | 10800.4825 | INR/PD — an output of the role mix, not an input
Stage 2 blended rate |  |  |  | 10924.7682 | Higher: security and accessibility rise from cameo to substantial
Peak negative position |  |  |  | -714279.2369 | The working capital carried across the whole programme
Peak as share of Stage 1 |  |  |  | -29.91% | Ask for a mobilisation advance if this is uncomfortable

## Resource Plan
Resource plan
Person-days by role and four-week period, derived from each package's own role mix. One period = 20 working days. The gap periods are empty by design.
Ref | Role | INR/PD | Total PD | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19
ME | Migration Engineer | 12000 | 116.5992 | 10.901 | 26.675 | 4.5331 | 10.389 | 10.7759 | 2.6066 |  |  |  | 1.8831 | 4.839 | 5.3173 | 7.3455 | 6.0885 | 1.2417 | 2.5017 | 4.1505 | 10.8171 | 6.5342
BA | Content Strategist / Business Analyst | 13000 | 95.7677 | 2.4606 | 7.1491 | 11.9171 | 15.6222 | 14.2301 | 3.7362 |  |  |  | 6.2182 | 5.4878 | 2.4748 | 2.0998 | 3.7139 | 2.6378 | 1.5618 | 2.7411 | 7.2088 | 6.5086
EL | Engagement Lead / Programme Manager | 22000 | 57.041 | 6.9875 | 5.3147 | 5.6841 | 4.3974 | 4.0963 | 3.1931 |  |  |  | 2.3739 | 2.3739 | 2.3739 | 2.3739 | 3.1728 | 3.4391 | 2.9065 | 2.9902 | 2.9902 | 2.3739
SA | Solution Architect — Gov.In CMS / DBIM | 24000 | 33.1674 | 4.5448 | 5.6317 | 2.2196 | [6 empty] | 6.6613 | 8.6091 | 1.3695 | 1.3695 | 0.91302 |  |  | 0.92444 | 0.92444
SE | Security Engineer | 20000 | 28.07 | 1.0628 | 5.6153 | 0.4151 | [10 empty] | 0.7989 | 6.032 | 5.0612 | 6.3912 | 2.6934
CO | Content Operations / Editorial support | 7500 | 20.5632 |  | 1.4825 | 1.5327 | 0.38317 | [6 empty] | 1.8671 | 3.5536 | 4.4764 | 4.2743 | 1.0761 |  |  | 1.1504 | 0.76694
QA | QA Engineer | 9500 | 19.3874 | 1.6866 | 2.1793 | [8 empty] | 0.62086 | 1.7918 | 2.1131 | 2.1131 | 0.64263 |  | 1.0043 | 4.3323 | 2.9034
AX | Accessibility Specialist | 15000 | 14.9041 |  | 1.2772 | [7 empty] | 1.2935 | 2.5869 | 2.2492 | 2.9989 | 2.9989 | 1.4995
| TOTAL PD |  | 385.5 | 27.6435 | 55.3248 | 26.3017 | 30.7918 | 29.1024 | 9.5359 | 0 | 0 | 0 | 18.4299 | 26.3846 | 19.13 | 22.7771 | 24.0733 | 16.5688 | 12.0311 | 18.2016 | 30.1166 | 19.087
| FTE |  |  | 1.3822 | 2.7662 | 1.3151 | 1.5396 | 1.4551 | 0.47679 | 0 | 0 | 0 | 0.92149 | 1.3192 | 0.9565 | 1.1389 | 1.2037 | 0.82844 | 0.60155 | 0.91008 | 1.5058 | 0.95435
| Peak FTE in any period |  | 2.7662
| Average FTE while working (gap excluded) |  | 1.2047
Eight named people across both stages, but never eight at once. Stage 1 is front-loaded on purpose — three people for weeks 5–8 on the remediation sprint, because that work is destination-independent and every week it waits is another week of indexed junk. Stage 2 is longer and thinner. A boutique can staff this shape; a large firm's bench cannot, which is another reason the tier question matters.

## Work Packages
Work packages
Three-point estimates. Expected = (O + 4M + P) / 6. The P80 column scales expected to the bid basis, which is where the risk reserve lives.
Stage | Ref | Phase | Work package | O | M | P | Expected | P80 | Weeks
Stage 1 | 0.1 | 0 · Mandate and decisions | Correct the brief; re-issue the objective in writing | 2 | 3 | 6 | 3.3333 | 4.5616 | W1–W3
Stage 1 | 0.2 | 0 · Mandate and decisions | Gov.In CMS intake via the MoHFW CIO route | 3 | 5 | 11 | 5.6667 | 7.7547 | W2–W12
Stage 1 | 0.4 | 0 · Mandate and decisions | registry.gov.in control and DNS readiness | 1 | 2 | 4 | 2.1667 | 2.965 | W4–W7
Stage 1 | 0.5 | 0 · Mandate and decisions | Security-audit route settled in writing | 1 | 2 | 4 | 2.1667 | 2.965 | W5–W9
Stage 1 | 0.6 | 0 · Mandate and decisions | Redirect-capability determination (pivotal) | 2 | 3 | 7 | 3.5 | 4.7897 | W3–W7
Stage 1 | 0.8 | 0 · Mandate and decisions | DBIM logo lockup 3A/3B determination | 0.5 | 1 | 2 | 1.0833 | 1.4825 | W6–W10
Stage 1 | 0.9 | 0 · Mandate and decisions | Destination status-code behaviour proven; origin status layer designed | 2 | 4 | 9 | 4.5 | 6.1581 | W4–W9
Stage 1 | 1.1 | 1 · Emergency remediation | Real HTTP 404: error-document status, not a 302 to a 200 page | 1.5 | 3 | 7 | 3.4167 | 4.6756 | W3–W6
Stage 1 | 1.2 | 1 · Emergency remediation | Charset: header says iso-8859-1 over 389 Hindi pages; header wins | 2 | 4 | 9 | 4.5 | 6.1581 | W3–W7
Stage 1 | 1.4 | 1 · Emergency remediation | GIGW policy pages and portal links (DBIM mandates no india.gov.in link) | 1 | 2 | 4 | 2.1667 | 2.965 | W5–W8
Stage 1 | 1.6 | 1 · Emergency remediation | robots.txt and a stopgap sitemap | 0.5 | 1 | 2 | 1.0833 | 1.4825 | W6–W7
Stage 1 | 1.7 | 1 · Emergency remediation | CSP hardening on the live site | 2 | 4 | 10 | 4.6667 | 6.3862 | W4–W8
Stage 1 | 1.8 | 1 · Emergency remediation | lang="hi" across 389 Hindi pages; close the joomla.xml version disclosure | 1 | 2 | 5 | 2.3333 | 3.1931 | W5–W8
Stage 1 | 2.1 | 2 · Inventory and redirect map | Joomla database extraction and reconciliation | 2 | 4 | 10 | 4.6667 | 6.3862 | W3–W7
Stage 1 | 2.2 | 2 · Inventory and redirect map | Live crawl with the two-signal validator | 3 | 5 | 10 | 5.5 | 7.5266 | W3–W6
Stage 1 | 2.3 | 2 · Inventory and redirect map | Wayback / CommonCrawl orphan recovery | 2 | 3 | 7 | 3.5 | 4.7897 | W5–W8
Stage 1 | 2.4 | 2 · Inventory and redirect map | Search Console traffic overlay | 1 | 2 | 4 | 2.1667 | 2.965 | W6–W9
Stage 1 | 2.5 | 2 · Inventory and redirect map | Union of four sources into one authoritative register | 2 | 3 | 7 | 3.5 | 4.7897 | W8–W11
Stage 1 | 2.6 | 2 · Inventory and redirect map | Triage facilitation — keep / archive / retire | 6 | 10 | 20 | 11 | 15.0532 | W10–W19
Stage 1 | 2.7 | 2 · Inventory and redirect map | PDF estate inventory and disposition (~2,758 documents) | 5 | 8 | 18 | 9.1667 | 12.5444 | W11–W18
Stage 1 | 2.8 | 2 · Inventory and redirect map | Redirect map — ~1,727 distinct source paths; rows exceed paths | 10 | 16 | 32 | 17.6667 | 24.1764 | W13–W20
Stage 1 | 2.9 | 2 · Inventory and redirect map | Hindi pairing by hreflang; bilingual gap quantified | 2 | 3 | 7 | 3.5 | 4.7897 | W9–W13
Stage 1 | P.1a | P · Programme management | Programme and delivery management — Stage 1 | 8 | 13 | 24 | 14 | 19.1586 | W1–W24
Stage 1 | P.2a | P · Programme management | Business analysis and content governance — Stage 1 | 5 | 8 | 15 | 8.6667 | 11.8601 | W2–W22
Stage 1 | P.3a | P · Programme management | Documentation, SOPs and the Stage 2 cost baseline | 4 | 6 | 12 | 6.6667 | 9.1232 | W18–W24
Stage 2 | 3.1 | 3 · Build and content load | IA re-expression into the platform's flat structure | 4 | 7 | 14 | 7.6667 | 10.4998 | W37–W42
Stage 2 | 3.10 | 3 · Build and content load | Search configuration and relevance | 2 | 3 | 6 | 3.3333 | 4.5651 | W50–W54
Stage 2 | 3.11 | 3 · Build and content load | Applications disposition — scoping only | 3 | 5 | 12 | 5.8333 | 7.989 | W40–W46
Stage 2 | 3.12 | 3 · Build and content load | .सरकार.भारत IDN registration and configuration (registry fee nil) | 1 | 2 | 4 | 2.1667 | 2.9673 | W52–W55
Stage 2 | 3.14 | 3 · Build and content load | Editorial training and standard operating procedures | 3 | 5 | 10 | 5.5 | 7.5325 | W52–W58
Stage 2 | 3.2 | 3 · Build and content load | Template mapping and the CCPS banner slot | 3 | 5 | 11 | 5.6667 | 7.7607 | W39–W44
Stage 2 | 3.3 | 3 · Build and content load | Platform configuration, roles, editorial workflow | 3 | 5 | 10 | 5.5 | 7.5325 | W38–W43
Stage 2 | 3.4 | 3 · Build and content load | Content mapping, authoring supervision and QA — no bulk import exists | 6 | 10 | 22 | 11.3333 | 15.5214 | W42–W56
Stage 2 | 3.5 | 3 · Build and content load | Content load — Hindi, byte-verified | 2 | 4 | 9 | 4.5 | 6.1629 | W48–W54
Stage 2 | 3.7 | 3 · Build and content load | Document register: categorisation scheme, priority tiers, bilingual flags | 4 | 6 | 13 | 6.8333 | 9.3585 | W43–W50
Stage 2 | 3.9 | 3 · Build and content load | Accessibility conformance — 9 templates, one covering 83% of pages | 5 | 9 | 20 | 10.1667 | 13.9236 | W46–W58
Stage 2 | 4.1 | 4 · Audit and clearance | Pre-audit hardening and pre-clearance of the obvious | 3 | 5 | 11 | 5.6667 | 7.7607 | W57–W61
Stage 2 | 4.2 | 4 · Audit and clearance | Auditor procurement and pre-audit paperwork | 2 | 3 | 7 | 3.5 | 4.7934 | W54–W62
Stage 2 | 4.3 | 4 · Audit and clearance | VAPT cycle 1 and remediation | 4 | 7 | 16 | 8 | 10.9563 | W62–W67
Stage 2 | 4.4 | 4 · Audit and clearance | Retest and closure | 2 | 3 | 8 | 3.6667 | 5.0216 | W67–W69
Stage 2 | 4.5 | 4 · Audit and clearance | Audit clearance documentation | 2 | 3 | 6 | 3.3333 | 4.5651 | W68–W70
Stage 2 | 5.1 | 5 · Cut-over and hypercare | Cut-over runbook: one A-record, MX untouchable | 2 | 4 | 9 | 4.5 | 6.1629 | W66–W71
Stage 2 | 5.2 | 5 · Cut-over and hypercare | Redirect layer live; every row asserted automatically | 3 | 5 | 11 | 5.6667 | 7.7607 | W69–W72
Stage 2 | 5.3 | 5 · Cut-over and hypercare | Sitemap, robots and Search Console submission | 1 | 2 | 4 | 2.1667 | 2.9673 | W71–W73
Stage 2 | 5.4 | 5 · Cut-over and hypercare | IGOD refresh and India Portal depository records | 2 | 3 | 7 | 3.5 | 4.7934 | W70–W74
Stage 2 | 5.5 | 5 · Cut-over and hypercare | Hypercare and 404-log review | 5 | 8 | 16 | 8.8333 | 12.0976 | W72–W76
Stage 2 | P.1b | P · Programme management | Programme and delivery management — Stage 2 | 10 | 16 | 30 | 17.3333 | 23.7386 | W37–W76
Stage 2 | P.2b | P · Programme management | Business analysis and content governance — Stage 2 | 6 | 10 | 19 | 10.8333 | 14.8366 | W37–W74
Stage 2 | P.3b | P · Programme management | Documentation, SOPs and handover — Stage 2 | 3 | 5 | 10 | 5.5 | 7.5325 | W68–W76
Options | 3.13 | X · Priced options, excluded from both stages | DBIM Annexure G KPI feed — Option 4 (bespoke) branch only | 2 | 3 | 7 | 3.5 | 4.0779 | on trigger
Options | X.1 | X · Priced options, excluded from both stages | Hindi coverage completion — Option 4 branch only; Option 3 uses runtime Bhashini | 40 | 75 | 160 | 83.3333 | 97.0928 | on trigger
Options | X.2 | X · Priced options, excluded from both stages | Alt text and metadata enrichment across the asset estate | 12 | 22 | 48 | 24.6667 | 28.7395 | on trigger
Options | X.3 | X · Priced options, excluded from both stages | PDF accessibility remediation, priority tier | 20 | 38 | 85 | 42.8333 | 49.9057 | on trigger
Options | X.4 | X · Priced options, excluded from both stages | STQC Certified Quality Website: manual, application, assessment | 12 | 20 | 42 | 22.3333 | 26.0209 | on trigger
Options | X.5 | X · Priced options, excluded from both stages | Applications replatform — e-services, shop, PvPI, iponline | 60 | 120 | 280 | 136.6667 | 159.2323 | on trigger
Options | X.6 | X · Priced options, excluded from both stages | IAAP Certified Auditor Review Report — mandatory gate before STQC evaluation | 5 | 9 | 18 | 9.8333 | 11.457 | on trigger
Options | X.7 | X · Priced options, excluded from both stages | Supplier-side manual authoring of surviving content items (if IPC cannot staff it) | 60 | 95 | 190 | 105 | 122.337 | on trigger
Options | X.8 | X · Priced options, excluded from both stages | Document repository loading — ~2,758 PDFs, one hand-made post each, 6 mandatory fields | 60 | 95 | 190 | 105 | 122.337 | on trigger
Not bought | 0.3 | 0 · Mandate and decisions | Governance: WIM, CIO/Tech SPOC, RACI (Appointing a Web Information Manager and a Tech SPOC is an i…) | 1 | 2 | 4 | 2.1667 |  | IPC / NIC
Not bought | 0.7 | 0 · Mandate and decisions | S3WaaS eligibility ruled in or out on the record (Asking NIC whether S3WaaS is available to IPC is a letter fr…) | 0.5 | 1 | 2 | 1.0833 |  | IPC / NIC
Not bought | 1.3 | 1 · Emergency remediation | Stale branding removal and content review sweep (Removing a stale G20 banner and reviewing content currency i…) | 1 | 2 | 5 | 2.3333 |  | IPC / NIC
Not bought | 1.5 | 1 · Emergency remediation | Joomla 3.8.10 (Jun 2018) on PHP 7.4.33 — both EOL: patch path or upgrade (NIC hosts the server and owns the runtime; an EOL Joomla/PHP…) | 4 | 8 | 20 | 9.3333 |  | IPC / NIC

## Options & Exclusions
Options and exclusions
None of this is in the Stage 1 or Stage 2 figures. Each option is a separate sponsor decision; each exclusion is a cost that genuinely cannot be priced yet.
Ref | Option | PD (P80) | Ex-GST (INR) | What triggers it
3.13 | DBIM Annexure G KPI feed — Option 4 (bespoke) branch only | 4.0779 | 37405.6784 | Only if Option 4 is taken. Annexure G binds bodies NOT onboarded to the Gov.In CMS Platform.
X.1 | Hindi coverage completion — Option 4 branch only; Option 3 uses runtime Bhashini | 97.0928 | 890611.3913 | Only if Option 4 (bespoke rebuild) is taken. Under Option 3 the platform serves Hindi as runtime Bhashini machine translation.
X.2 | Alt text and metadata enrichment across the asset estate | 28.7395 | 263620.9718 | If alt text and metadata are not made required fields at import. Retrofitting across thousands of assets is the expensive path.
X.3 | PDF accessibility remediation, priority tier | 49.9057 | 457774.2551 | If the PDF estate is remediated rather than tiered or declared. Rate deliberately unpriced — sample 30-50 documents first.
X.4 | STQC Certified Quality Website: manual, application, assessment | 26.0209 | 238683.8529 | If STQC Certified Quality Website certification is in scope rather than deferred. The IAAP review (X.6) gates it.
X.5 | Applications replatform — e-services, shop, PvPI, iponline | 159.2323 | 1460602.6817 | If /shop, /e-services, PvPI, iponline or onlinestore come into scope. /shop is a live OpenCart storefront, re-verified 01-09-2026.
X.6 | IAAP Certified Auditor Review Report — mandatory gate before STQC evaluation | 11.457 | 105092.1442 | Mandatory ahead of any STQC GIGW evaluation, per STQC OM dated 30.06.2025. Take it if X.4 is taken.
X.7 | Supplier-side manual authoring of surviving content items (if IPC cannot staff it) | 122.337 | 1122170.353 | If IPC cannot staff content authoring. There is no bulk import, so every surviving item is hand-keyed.
X.8 | Document repository loading — ~2,758 PDFs, one hand-made post each, 6 mandatory fields | 122.337 | 1122170.353 | If the document estate is loaded into the platform. One hand-made post per PDF, six mandatory fields.
| TOTAL if all were taken | 621.2 | 5698131.6814
EXCLUDED AND UNPRICED — costs that are real but cannot be quoted yet
Item | Position |  |  | Why it cannot be priced
STQC Certified Quality Website fee | No GIGW 3.0 tariff is published |  |  | The circulating INR 40,000 is real but its own section 6.1 scopes it to GIGW version 2009 and 87 test points. Obtain a written quote from the assigned STQC IT Laboratory, payable via Bharatkosh.
CERT-In empanelled security audit | Bimodal: zero or lakhs |  |  | GIGW 3.0 accepts clearance from NIC, STQC or a CERT-In empanelled vendor. If NIC performs it the line is zero. If procured, no Indian government body publishes a VAPT rate card and it goes to quotation.
IAAP Certified Auditor Review Report | Unpriced, and newly mandatory |  |  | STQC OM F.No. STQC/IT&eGov/WQC/2022 dated 30.06.2025 makes it a pre-requisite for GIGW evaluation. Commencement language is equivocal - confirm before relying on the date.
Third-party accessibility audit | Vendor marketing ranges only |  |  | No Indian government rate card exists. Priced per template and per sampled page, so the Phase 3 exit criterion drives it.
Bhashini production use | Unpublished |  |  | Official documentation states API usage shall be for proof-of-concept only. bhashini.ai is a separate commercial site and its prices are not the platform's.
Gov.In CMS Platform and NIC hosting | Unpriced in both directions |  |  | No published tariff, and no published statement that it is free. A genuine void, not a gap in searching.
Hindi translation | Rate known, volume not |  |  | Carry INR 1.00 / 2.50 / 6.00 per word. The National Translation Mission schedule of INR 0.50-1.00 is a scholar honorarium at roughly a quarter of market and will under-price a procured programme.

## Confidence
Confidence
100,000 iterations, Beta-PERT marginals, single-factor Gaussian copula at rho 0.5, exogenous risks sampled inside each iteration rather than added to a percentile. Seed 20260901 — every figure here is reproducible.
View | Packages | PERT expected PD | Risk EMV PD | P50 | P70 | P80 | P90
Stage 1 (recommended) | 25 | 130.6 | 26.8 | 156 | 170.1 | 178.7 | 191
Stage 1 (full scope) | 29 | 145.5 | 32.8 | 176.7 | 192.6 | 202.5 | 216.1
Stage 2 | 24 | 151 | 29.6 | 179 | 196.1 | 206.8 | 221.5
Stage 1 + 2, joint run | 49 | 281.6 | 56.4 | 334.8 | 364 | 382.5 | 407.9
Options | 9 | 533.2 | 0 | 525.3 | 584.3 | 621.2 | 672.9
CORRELATION SENSITIVITY — Stage 1 recommended scope. The assumption is visible, not buried
rho | P50 | P80 | P90 | Reading
rho=0.0 | 157.1 | 168.5 | 174.5 | Independent packages. Unrealistic — one team, one client.
rho=0.3 | 156.5 | 175.2 | 185.3 | Weak common cause. A portfolio of unrelated projects.
rho=0.5 | 156 | 178.7 | 191 | RECOMMENDED. One accountable team, shared requirement risk.
rho=0.7 | 155.4 | 181.9 | 196.1 | Strong common cause. Use if requirements are unfrozen at award.
Percentiles do not add. Stage 1 at P80 (179 PD) plus Stage 2 at P80 (207 PD) is 386 PD, but a single joint contract sampling both in the same iterations is 382 PD — the two stages diversify against each other. They are priced as two contracts here because that is how they would be procured.
WHERE THE UNCERTAINTY LIVES — share of Stage 1 variance
2.8 | 23.2% | Redirect map — ~1,727 distinct source paths; rows exceed paths
P.1a | 12.6% | Programme and delivery management — Stage 1
1.5 | 12% | Joomla 3.8.10 (Jun 2018) on PHP 7.4.33 — both EOL: patch path or upgrade
2.6 | 9.5% | Triage facilitation — keep / archive / retire
2.7 | 7.8% | PDF estate inventory and disposition (~2,758 documents)
P.2a | 4.9% | Business analysis and content governance — Stage 1
Nearly a quarter of the spread is one package — the redirect map. A day spent agreeing the redirect convention at kickoff is worth more than a week of estimating discipline anywhere else.

## Rate Card & Commercials
Rate card and commercial terms
Role rates are the mid-tier reference. The blended rate is an OUTPUT of the role mix in the packages, not an input — change the mix and it moves.
Ref | Role | INR/PD | Stage 1 PD | Stage 2 PD | Note
ME | Migration Engineer | 12000 | 65.8807 | 50.7185 | Crawler, two-signal validator, transforms, redirect map, cut-over.
BA | Content Strategist / Business Analyst | 13000 | 55.1153 | 40.6524 | Owns the inventory, the triage facilitation and the disposition register.
EL | Engagement Lead / Programme Manager | 22000 | 29.6731 | 27.3679 | Client-facing; owns the CIO route and the decision gates.
SA | Solution Architect — Gov.In CMS / DBIM | 24000 | 12.3961 | 20.7713 | Scarce skill; the platform-specific knowledge is the whole reason to hire outside.
SE | Security Engineer | 20000 | 7.0933 | 20.9767 | CSP, patching, pre-audit clearance, CERT-In liaison.
CO | Content Operations / Editorial support | 7500 | 3.3984 | 17.1649 | Bulk load, alt text, metadata. The line most safely moved to IPC's own team.
QA | QA Engineer | 9500 | 3.8659 | 15.5214 | Assertion suites; every redirect row is a test.
AX | Accessibility Specialist | 15000 | 1.2772 | 13.6269 | WCAG 2.1 AA; 50 of GIGW 3.0's 88 guidelines.
| TOTAL |  | 178.7 | 206.8
SUPPLIER TIER — the envelope test. Stage 1 ex-GST, INR lakh
Tier | Multiplier | Blended INR/PD | P50 | P80 | P90
T1 · Boutique / specialist | 0.72 | 10800.4825 | 20.9985 | 23.8829 | 25.4458
T2 · Mid-tier SI | 1 | 15000.6701 | 28.7071 | 32.7132 | 34.8839
T3 · Tier-1 SI | 1.4 | 21000.9381 | 39.7194 | 45.3279 | 48.3668
Green cells fall inside the stated INR 20–30 lakh envelope. T1 is the only tier that fits at the bid percentile — but IPC's own last IT tender demanded ISO 9001, ISO 27000 and CMMI Level 3, a bar that excludes it. Resolve the procurement category before bidding.
COMMERCIAL TERMS — IPC's own revealed rates, not convention
Item | Rate | On Stage 1 (INR) | On both stages (INR) |  | Note
Earnest money deposit | 4% | 95531.5865 | 206554.7426 |  | IPC's own revealed rate on GEM/2026/B/7781379 (13-07-2026), against a GeM recommendation of 1%. Refundable, but it blocks working capital through evaluation.
Performance bank guarantee | 5% | 119414.4832 | 258193.4282 |  | IPC's revealed rate, held 60 months on its last IT bid. For a 5.5-month assignment, negotiate the term down — a 60-month PBG on a 24-week engagement is a real and avoidable carrying cost.
PBG carrying cost per annum | 1.5% | 1791.2172 | 3872.9014 |  | Bank commission. Routinely forgotten in pricing.
Liquidated damages cap | 10% | 238828.9663 | 516386.8565 |  | Convention is 0.5% per week of delay capped at 10%. This is the schedule risk expressed in rupees.
Retention against M6 | 10% | 238828.9663 | 516386.8565 |  | M6 is itself 10% and is the natural retention. Do not stack a further retention on top of it.

## Charts
Charts
Live Excel charts driven by the data blocks below them. The Gantt is a stacked bar whose first series is invisible — that series carries the start week, the second carries the duration. Edit a number in the block and the chart moves.
| Chart data → | Item | Start-1 | Duration
|  | Stage 1 · 0 · Mandate and decisions | 0 | 12
|  | Stage 1 · 1 · Emergency remediation | 2 | 6
|  | Stage 1 · 2 · Inventory and redirect map | 2 | 18
|  | Stage 1 · P · Programme management | 0 | 24
|  | Procurement gap | 24 | 12
|  | Stage 2 · 3 · Build and content load | 36 | 22
|  | Stage 2 · 4 · Audit and clearance | 53 | 17
|  | Stage 2 · 5 · Cut-over and hypercare | 65 | 11
|  | Stage 2 · P · Programme management | 36 | 40
|  | Item | Start-1 | Duration
|  | 0.1 Correct the brief; re-issue the objective in | 0 | 3
|  | P.1a Programme and delivery management — Stage 1 | 0 | 24
|  | 0.2 Gov.In CMS intake via the MoHFW CIO route | 1 | 11
|  | P.2a Business analysis and content governance — S | 1 | 21
|  | 0.6 Redirect-capability determination (pivotal) | 2 | 5
|  | 1.1 Real HTTP 404: error-document status, not a | 2 | 4
|  | 1.2 Charset: header says iso-8859-1 over 389 Hin | 2 | 5
|  | 2.1 Joomla database extraction and reconciliatio | 2 | 5
|  | 2.2 Live crawl with the two-signal validator | 2 | 4
|  | 0.4 registry.gov.in control and DNS readiness | 3 | 4
|  | 0.9 Destination status-code behaviour proven; or | 3 | 6
|  | 1.7 CSP hardening on the live site | 3 | 5
|  | 0.5 Security-audit route settled in writing | 4 | 5
|  | 1.4 GIGW policy pages and portal links (DBIM man | 4 | 4
|  | 1.8 lang="hi" across 389 Hindi pages; close the | 4 | 4
|  | 2.3 Wayback / CommonCrawl orphan recovery | 4 | 4
|  | 0.8 DBIM logo lockup 3A/3B determination | 5 | 5
|  | 1.6 robots.txt and a stopgap sitemap | 5 | 2
|  | 2.4 Search Console traffic overlay | 5 | 4
|  | 2.5 Union of four sources into one authoritative | 7 | 4
|  | 2.9 Hindi pairing by hreflang; bilingual gap qua | 8 | 5
|  | 2.6 Triage facilitation — keep / archive / retir | 9 | 10
|  | 2.7 PDF estate inventory and disposition (~2,758 | 10 | 8
|  | 2.8 Redirect map — ~1,727 distinct source paths; | 12 | 8
|  | P.3a Documentation, SOPs and the Stage 2 cost bas | 17 | 7
|  | 3.1 IA re-expression into the platform's flat st | 36 | 6
|  | P.1b Programme and delivery management — Stage 2 | 36 | 40
|  | P.2b Business analysis and content governance — S | 36 | 38
|  | 3.3 Platform configuration, roles, editorial wor | 37 | 6
|  | 3.2 Template mapping and the CCPS banner slot | 38 | 6
|  | 3.11 Applications disposition — scoping only | 39 | 7
|  | 3.4 Content mapping, authoring supervision and Q | 41 | 15
|  | 3.7 Document register: categorisation scheme, pr | 42 | 8
|  | 3.9 Accessibility conformance — 9 templates, one | 45 | 13
|  | 3.5 Content load — Hindi, byte-verified | 47 | 7
|  | 3.10 Search configuration and relevance | 49 | 5
|  | 3.12 .सरकार.भारत IDN registration and configurati | 51 | 4
|  | 3.14 Editorial training and standard operating pr | 51 | 7
|  | 4.2 Auditor procurement and pre-audit paperwork | 53 | 9
|  | 4.1 Pre-audit hardening and pre-clearance of the | 56 | 5
|  | 4.3 VAPT cycle 1 and remediation | 61 | 6
|  | 5.1 Cut-over runbook: one A-record, MX untouchab | 65 | 6
|  | 4.4 Retest and closure | 66 | 3
|  | 4.5 Audit clearance documentation | 67 | 3
|  | P.3b Documentation, SOPs and handover — Stage 2 | 67 | 9
|  | 5.2 Redirect layer live; every row asserted auto | 68 | 4
|  | 5.4 IGOD refresh and India Portal depository rec | 69 | 5
|  | 5.3 Sitemap, robots and Search Console submissio | 70 | 3
|  | 5.5 Hypercare and 404-log review | 71 | 5
|  | Role | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19
|  | Migration Engineer | 10.9 | 26.67 | 4.53 | 10.39 | 10.78 | 2.61 | 0 | 0 | 0 | 1.88 | 4.84 | 5.32 | 7.35 | 6.09 | 1.24 | 2.5 | 4.15 | 10.82 | 6.53
|  | Content Strategist / Business Analyst | 2.46 | 7.15 | 11.92 | 15.62 | 14.23 | 3.74 | 0 | 0 | 0 | 6.22 | 5.49 | 2.47 | 2.1 | 3.71 | 2.64 | 1.56 | 2.74 | 7.21 | 6.51
|  | Engagement Lead / Programme Manager | 6.99 | 5.31 | 5.68 | 4.4 | 4.1 | 3.19 | 0 | 0 | 0 | 2.37 | 2.37 | 2.37 | 2.37 | 3.17 | 3.44 | 2.91 | 2.99 | 2.99 | 2.37
|  | Solution Architect — Gov.In CMS / DBIM | 4.54 | 5.63 | 2.22 | 0 | 0 | 0 | 0 | 0 | 0 | 6.66 | 8.61 | 1.37 | 1.37 | 0.91 | 0 | 0 | 0.92 | 0.92 | 0
|  | Security Engineer | 1.06 | 5.62 | 0.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 6.03 | 5.06 | 6.39 | 2.69 | 0
|  | Content Operations / Editorial support | 0 | 1.48 | 1.53 | 0.38 | 0 | 0 | 0 | 0 | 0 | 0 | 1.87 | 3.55 | 4.48 | 4.27 | 1.08 | 0 | 0 | 1.15 | 0.77
|  | QA Engineer | 1.69 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62 | 1.79 | 2.11 | 2.11 | 0.64 | 0 | 1 | 4.33 | 2.9
|  | Accessibility Specialist | 0 | 1.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 2.59 | 2.25 | 3 | 3 | 1.5 | 0 | 0 | 0 | 0
|  | Total FTE | 1.382 | 2.766 | 1.315 | 1.54 | 1.455 | 0.477 | 0 | 0 | 0 | 0.921 | 1.319 | 0.957 | 1.139 | 1.204 | 0.828 | 0.602 | 0.91 | 1.506 | 0.954