## Read Me
IPC Digital Platform — Estimate v2
Rebuilt 18 Aug 2026 against verified evidence from the live IPC estate. Supersedes v1.
WHAT CHANGED IN v2
| 1. Verified, not assumed | v1 assumed ~2,500 pages of migration and a greenfield build. Both were wrong. The live estate was inspected and the baselines below are counted, not estimated.
| 2. Probabilistic, not point | v1 gave a single number plus a 12% contingency I chose. v2 derives P50 / P80 / P90 from the three-point spread already in the model, and derives contingency from an expected-value risk register.
| 3. Build-vs-adopt tested | v1 priced three flavours of bespoke build. v2 adds Scenario D, which tests replatforming the existing estate against a full rebuild.
| 4. Unit economics | v2 computes cost per transaction against the real catalogue and order volumes, which is the first number an evaluation committee will calculate.
| 5. Price, not just cost | v2 adds margin, GST, milestone billing, cash-flow curve, performance guarantee and liquidated-damages exposure.
| 6. Triangulated | v2 cross-checks the bottom-up build against a top-down analogy and a capability-count method. Where they disagree, that gap is stated rather than hidden.
| VERIFIED BASELINES | All figures below were read from the live IPC estate on 18 Aug 2026.
| Current CMS | Joomla. Confirmed from the meta-generator on every page. Migration is Joomla-to-target, not greenfield.
| Current commerce | OpenCart, live at /shop/. Confirmed from URL routing (index.php?route=product/category). Doc B's e-commerce module is a REPLATFORM with existing product, customer and order data — scope absent from Doc B entirely.
| IPRS catalogue | 702 reference substances. Counted from List-of-IP-Reference-Substances.pdf, last updated 24/06/2026. Each row carries current lot, one previous lot with validity, and quantity per vial.
| IMPRS catalogue | 639 reference impurities. Counted from Impuritie_List.pdf, last updated 24/06/2026. Each row carries API/monograph linkage, lot data, quantity and TWO price tiers.
| Total priced SKUs | 1,341 plus publications, subscriptions, phytochemical and botanical standards, and the Prednisone calibrator tablet.
| Government pricing | IPC ALREADY publishes a two-tier price list: private party and government organisation, at exactly 50%. Doc A's '50% discount' is therefore price-tier assignment against an existing list, not a discount engine. The real control is the verification workflow.
| Lot history available | IPC publishes current lot plus ONE previous lot. Doc A requires five. The additional history may not exist in digital form — see risk K2.
| Bilingual | A Hindi site already exists at /hi/. Translation is largely a migration and coverage-completion exercise, not a from-scratch translation project. v1 over-provisioned this.
| Traffic — RETRACTED | RETRACTED. This baseline claimed roughly 88,000 monthly visitors from the site's own counter. The derivation used page Last-Modified dates as if they were counter read times; they are not. Traffic is UNVERIFIED. Doc B's 100,000-monthly figure may well be a reasonable growth allowance, and the criticism previously made of it does not stand.
| Separate systems | IP Online runs on its own subdomain (iponline.ipc.gov.in). It is the concrete SSO federation target Doc B section 1.6 refers to.
| Procurement route | IPC transacts through GeM (Government e-Marketplace) — its NFI digitalisation and printing tenders both ran there. Relevant to how this would actually be awarded.
| Estate hygiene | Production pages link to a vendor staging host (ipc.maxtraserver.in); a G20 banner from 2023 is still live; the site map's own last-updated date is July 2019; the NFI section still headlines 2021 while NFI 2026 is being procured. This is direct evidence for Doc B's archival and lifecycle requirements.
VERIFIED COMPLIANCE POSITION
| GIGW 3.0 | 88 mandatory guidelines across quality, accessibility, cybersecurity and lifecycle management. Conforms to WCAG 2.1 Level AA with 17 added success criteria. Its cybersecurity chapter was written by CERT-In and EXPLICITLY covers mobile apps — so Doc A omitting GIGW is a compliance gap, not merely an inconsistency with Doc B.
| STQC | Conformity is evidenced by Certified Quality Website (CQW) certification from the STQC Directorate, involving document review plus frontend and backend testing.
| DPDP | Both documents cite the 'DPDP Bill, 2023'. It has been an Act since August 2023, and the DPDP Rules were notified on 13 November 2025. Compliance is phased: the Board and definitions took effect immediately, penalties and Consent Manager registration from 13 November 2026, and FULL COMPLIANCE IS DUE 13 MAY 2027. A 16-month programme starting now lands on or after that date — DPDP is a hard delivery constraint, not a design preference.
| Correction to v1 | v1 argued Google Analytics conflicts with DPDP on localisation grounds. That was wrong: the final Rules use a blacklist model for cross-border transfer, not data localisation. The real constraints are consent, purpose limitation, retention limits and a 90-day grievance timeline.
| HOW TO USE | Blue = input, change these. Black = formula. Green = cross-sheet link. Yellow = primary lever.
| Row shading | Pink = scope the documents omit but the outcome requires. Green = scope newly identified from inspecting the live estate, absent from both documents.
| Excluded | IPC staff time; content authoring; payment gateway TDR; statutory fees; physical cold-chain infrastructure; IPC-side hardware.
WHAT CHANGED IN v5
| One sheet, both scenarios | This workbook now prices two different questions in one place: what it costs to build Lotmark as a product, and what IPC costs under five routes including adopting that product.
| Product Build sheet | New. The product had never been estimated — only customer deployments had. Same three-point and Monte Carlo method.
| Scenario E | New. Every IPC module carries a factor for what survives once the product supplies the core, modelled per module rather than as a global multiplier.
| Why it matters | Scenarios A to D all assume a bespoke build. If the product exists, none of them is the cheapest route for IPC, and the workbook previously could not say so.
UNITS AND CONVENTIONS
| PD — person-day | One person working one day. 21 person-days make one person-month. All effort figures in this workbook are person-days unless a column header says otherwise.
| INR crore (Cr) | Ten million rupees. Used for build cost, total cost of ownership and quoted price.
| INR lakh | One hundred thousand rupees. Used for pass-through and licence lines. Note that crore and lakh both appear in this workbook — always read the column header.
| INR / PD | The blended rate: rupees per person-day. Multiply effort by this to get cost.
| Factor (0–1) | Dimensionless. The fraction of a module that survives under a given scenario. 1.00 means untouched; 0.15 means 15% of the original effort remains.
| Probability (0–1) | Dimensionless likelihood of a risk event, used to weight its impact.
| P50 / P80 / P90 | Confidence levels from the Monte Carlo, expressed in person-days. P80 means four runs in five finish at or below that figure.
| Sigma | Standard deviation of a module's three-point spread, in person-days.
| FP / KSLOC | Function points and thousands of source lines of code, used only on the Independent Estimate sheet.
| Months | Schedule durations on the Timeline sheet. Columns M1 to M16 are programme months, not calendar months.
| FTE | Full-time equivalent people, derived as person-days in a month divided by 21.
| Counts | Orders, SKUs, records and clause tallies are plain counts and carry no monetary or effort unit.
| Where a unit is ambiguous | Column headers now carry the unit in brackets, and headline figures carry it inside the cell format so a copied cell keeps its unit.

## Build & Verification
Build and Verification
Three deliverables, one toolchain. The toolchain is carried inside the product and exportable from its Build screen.
THE THREE DELIVERABLES
Ref | Outcome | File | What it is
D1 | Product | lotmark-app.html | The working application. Nine roles, 22 console modules, ISO 17034 and 21 CFR Part 11 controls that can be exercised rather than read. Carries build.py inside it, exportable from Build and verification.
D2 | Wireframe | lotmark-product-wireframe.html | 37 screens of product design, including the market and deployment decision screens. Its screen list is the source the product's coverage map is generated from.
D3 | Estimation | Lotmark_and_IPC_Estimate_v5.xlsx | This workbook. Cost and revenue for both the product build and five IPC routes, in one place.
SHIP SEQUENCE — run in this order after any change
Step | Command | Guards | Why it is in this position
1 | recalc the workbook | cached values must exist | openpyxl drops cached values on save; every reference check would otherwise report a false failure
2 | python3 build.py sync | asserts substitution size and key symbols; refuses to write a damaged file | regenerates the coverage map from the wireframe and injects figures, so drift cannot survive a build
3 | python3 build.py check | 23 checks; exits non-zero | catches duplicate declarations, broken references, undefined permissions, coverage drift
4 | open the product, Build and verification | 16 runtime invariants | only evaluable with data loaded — signatures, chain, referential integrity
5 | the five JS harnesses | 166 assertions, each asserting its own count | behaviour, not structure
WHAT THE TOOLCHAIN CHECKS, AND THE DEFECT THAT PUT IT THERE
Ref | Check | Where it runs | The defect it exists because of
V1 | Duplicate function and constant declarations | build.py check | A re-run patch script inserted a block twice, nested inside the first. JavaScript accepts it silently.
V2 | Cross-sheet references land on numeric cells | build.py check | A hardcoded coordinate pointed at a paragraph of prose after rows shifted.
V3 | Named ranges resolve to numbers | build.py check | Same root cause: coordinates as an addressing scheme.
V4 | No cached formula errors | build.py check | A row insert broke an entire block, because openpyxl does not translate formulas.
V5 | Every permission used is defined and granted | build.py check + product | An export guarded on a permission absent from the model, so it refused everyone silently.
V6 | Every module has a renderer | build.py check + product | A dead fallback key crashed the app for a role with no console modules.
V7 | Inline handlers call functions that exist | build.py check | Handlers are strings; a rename does not break them until someone clicks.
V8 | No backticks or mangled escapes in handlers | build.py check | A nested backtick and a Python-mangled apostrophe each terminated a template literal.
V9 | Coverage map matches the wireframe | build.py check | The artefact that verifies the product drifted from the product.
V10 | Harnesses assert their own assertion count | build.py check | Three separate green results came from tests that never ran.
V11 | Signatures carry a valid competence basis | product runtime | Nine seeded signatures had none, found by the product checking itself.
V12 | Bound signatures still verify | product runtime | 21 CFR 11 §11.70: a signature must be provably bound to its record.
V13 | Referential integrity across orders, lots, vault, studies | product runtime | Only evaluable with data loaded.
| Standing caveat | The toolchain protects these three files from the people editing them. It does not test whether a reference material producer would buy the product. The addressable share in the Market and Revenue sheet is invented, and it moves the answer more than any other input here.

## Toolchain (build.py)
build.py — the complete toolchain
Copy column B to a file named build.py, then run: python3 build.py all. Column A is the line number only. Lines beginning with an equals sign are stored as forced text so the spreadsheet does not read them as formulas.
1 | #!/usr/bin/env python3
2 | """
3 | build.py — the entire Lotmark toolchain in one file.
4
5 | python3 build.py sync regenerate the coverage map and inject workbook figures
6 | python3 build.py check run 23 preflight checks across all three artefacts
7 | python3 build.py all sync, then check (the ship sequence)
8
9 | Also importable as a library for `Patcher` and `cell_by_label`.
10
11 | Every check here exists because the corresponding defect actually happened during this
12 | build. Discipline did not catch them; a script would have. Recalculate the workbook
13 | before running — openpyxl drops cached values on save.
14 | """
15 | import openpyxl, re, sys, os, json
16 | from openpyxl.workbook.defined_name import DefinedName
17 | from openpyxl.utils import quote_sheetname, absolute_coordinate
18
19 | XL = "/mnt/user-data/outputs/Lotmark_and_IPC_Estimate_v5.xlsx"
20 | WF = "/mnt/user-data/outputs/lotmark-product-wireframe.html"
21 | AP = "/mnt/user-data/outputs/lotmark-app.html"
22
23
24 | # A file that carries this script inside it must not be analysed WITH this script inside
25 | # it: every literal here (const PERMS={, const COVERAGE=[, guard('...')) would be read as
26 | # application code. sync() found its own embedded copy and patched the wrong place.
27 | # Strip the carrier before reading, and never write inside it.
28 | EMBED_OPEN = '<script type="text/plain" id="build-src">'
29 | EMBED_CLOSE = '</script>'
30
31 | def strip_embedded(src):
32 | i = src.find(EMBED_OPEN)
33 | if i == -1:
34 | return src
35 | j = src.find(EMBED_CLOSE, i)
36 | return src[:i] + src[j + len(EMBED_CLOSE):]
37
38 | def split_embedded(src):
39 | i = src.find(EMBED_OPEN)
40 | if i == -1:
41 | return src, "", ""
42 | j = src.find(EMBED_CLOSE, i) + len(EMBED_CLOSE)
43 | return src[:i], src[i:j], src[j:]
44
45 | # ══════════════════ PATCHING LIBRARY ══════════════════
46
47 | class Patcher:
48 | def __init__(self, path, comment=("/*", "*/"), marker="PATCHLIB-APPLIED"):
49 | self.path, self.c, self.marker = path, comment, marker
50 | self.s = open(path).read()
51 | self.applied = set(re.findall(rf"{re.escape(marker)}:(\S+)", self.s))
52 | self.done, self.skipped = [], []
53
54 | def apply(self, pid, old, new, allow_missing=False):
55 | if pid in self.applied:
56 | self.skipped.append(pid); print(f" skip {pid} (already applied)"); return False
57 | n = self.s.count(old)
58 | if n == 0:
59 | if allow_missing:
60 | print(f" skip {pid} (anchor absent, allowed)"); return False
61 | raise AssertionError(f"{pid}: anchor not found")
62 | if n > 1:
63 | raise AssertionError(f"{pid}: anchor appears {n} times — widen it until it is unique")
64 | self.s = self.s.replace(old, new, 1)
65 | self._record(pid)
66 | self._write()
67 | self.done.append(pid); print(f" ok {pid}")
68 | return True
69
70 | def _record(self, pid):
71 | tag = f"{self.c[0]} {self.marker}:{pid} {self.c[1]}"
72 | self.s = self.s.rstrip() + "\n" + tag + "\n"
73 | self.applied.add(pid)
74
75 | def _write(self):
76 | open(self.path, "w").write(self.s)
77
78 | def finish(self):
79 | """Post-conditions that would have caught the duplication."""
80 | fns = re.findall(r"^function\s+(\w+)\s*\(", self.s, re.M)
81 | dup = sorted({f for f in fns if fns.count(f) > 1})
82 | if dup:
83 | raise AssertionError(f"duplicate function declarations after patching: {', '.join(dup)}")
84 | consts = re.findall(r"^const\s+([A-Z_][A-Z0-9_]*)\s*=", self.s, re.M)
85 | dupc = sorted({c for c in consts if consts.count(c) > 1})
86 | if dupc:
87 | raise AssertionError(f"duplicate constants after patching: {', '.join(dupc)}")
88 | print(f"\n{len(self.done)} applied, {len(self.skipped)} already present, no duplicate declarations")
89 | return True
90
91 | def cell_by_label(ws, predicate, value_col, label_col=2):
92 | """Resolve a workbook cell by its LABEL, never by a hardcoded coordinate.
93
94 | A hardcoded 'Sheet'!C122 pointed at a paragraph of prose once rows shifted.
95 | Addressing by label survives inserts, deletes and reordering.
96 | """
97 | for r in range(1, ws.max_row + 1):
98 | v = ws.cell(row=r, column=label_col).value
99 | if v and predicate(str(v)):
100 | target = ws.cell(row=r, column=value_col)
101 | return r, target
102 | raise AssertionError("no row matched the label predicate — check the label text")
103
104
105 | # ══════════════════ SYNC ══════════════════
106 | def sync():
107
108
109 | FAIL = []
110 | def check(cond, msg):
111 | if not cond: FAIL.append(msg); print(" FAIL " + msg)
112 | else: print(" ok " + msg)
113
114 | # ───────────────────────────── 1. read the figures from the workbook
115 | wv = openpyxl.load_workbook(XL, data_only=True)
116 | sc, pb, em = wv['Scenarios & Cost'], wv['Product Build'], wv['Scenario E Model']
117
118 | def row_where(ws, pred, col=2):
119 | for r in range(1, ws.max_row + 1):
120 | v = ws.cell(row=r, column=col).value
121 | if v and pred(str(v)): return r
122 | return None
123
124 | FIG = {}
125 | for r in range(5, 10):
126 | k = sc.cell(row=r, column=1).value
127 | if k and str(k).startswith('S-'):
128 | FIG[str(k)] = {'pd': round(sc.cell(row=r, column=3).value),
129 | 'cr': round(sc.cell(row=r, column=5).value, 2)}
130 | FIG['product_pd'] = round(pb.cell(row=row_where(pb, lambda x: 'RECOMMENDED BUILD' in x), column=3).value)
131 | FIG['product_cr'] = round(pb.cell(row=row_where(pb, lambda x: 'Build cost at the blended rate' in x), column=3).value, 2)
132 | FIG['licence_cr'] = round(em.cell(row=row_where(em, lambda x: x.startswith('Scenario E — licence')), column=3).value, 2)
133 | FIG['allin_cr'] = round(em.cell(row=row_where(em, lambda x: x.startswith('Scenario E — all in')), column=3).value, 2)
134 | FIG['breakeven'] = round(em.cell(row=row_where(em, lambda x: 'BREAK-EVEN LICENCE' in x), column=3).value, 1)
135 | mk = wv['Market & Revenue']
136 | arr = [r for r in range(1, mk.max_row + 1) if 'Annual recurring revenue' in str(mk.cell(row=r, column=2).value or '')]
137 | FIG['arr_producer_base'] = round(mk.cell(row=arr[0], column=4).value, 1)
138 | FIG['arr_producer_high'] = round(mk.cell(row=arr[0], column=5).value, 1)
139 | FIG['arr_vault_base'] = round(mk.cell(row=arr[1], column=4).value, 1)
140 | FIG['acv_gap'] = round(mk.cell(row=row_where(mk, lambda x: x.strip() == 'Gap'), column=3).value, 1)
141
142 | print("FIGURES READ FROM THE WORKBOOK")
143 | for k, v in FIG.items(): print(f" {k:12} {v}")
144 | check(FIG['S-B']['pd'] > FIG['S-E']['pd'], "Scenario B exceeds Scenario E in effort, as it must")
145 | check(FIG['product_cr'] < FIG['S-B']['cr'], "the product costs less to build than one bespoke engagement")
146 | check(abs((FIG['S-E']['cr'] + FIG['licence_cr']) - FIG['allin_cr']) < 0.02, "Scenario E all-in equals build plus licence")
147
148 | # ───────────────────────────── 2. inject the figures into the wireframe
149 | wf = strip_embedded(open(WF).read())
150 | fmt = lambda n: f"{n:,}"
151 | DEPLOY_ROWS = (
152 | "{0:['Cost to build the product itself','A — two independent builds','B — bespoke unified build',"
153 | "'C — bespoke, phase 1 only','D — replatform the estate','E — customer adopts the product'],\n"
154 | f" 1:['{fmt(FIG['product_pd'])}','{fmt(FIG['S-A']['pd'])}','{fmt(FIG['S-B']['pd'])}',"
155 | f"'{fmt(FIG['S-C']['pd'])}','{fmt(FIG['S-D']['pd'])}','{fmt(FIG['S-E']['pd'])}'],\n"
156 | f" 2:['{FIG['product_cr']:.2f}','{FIG['S-A']['cr']:.2f}','{FIG['S-B']['cr']:.2f}',"
157 | f"'{FIG['S-C']['cr']:.2f}','{FIG['S-D']['cr']:.2f}','{FIG['S-E']['cr']:.2f}'],\n"
158 | f" 3:['—','—','—','—','—','{FIG['licence_cr']:.2f}'],\n"
159 | f" 4:['{FIG['product_cr']:.2f}','{FIG['S-A']['cr']:.2f}','{FIG['S-B']['cr']:.2f}',"
160 | f"'{FIG['S-C']['cr']:.2f}','{FIG['S-D']['cr']:.2f}','{FIG['allin_cr']:.2f}'],\n"
161 | " 5:['Less than one bespoke engagement','','The bid basis','Defers the AI layer and mobile',"
162 | "'Unvalidated','Costs MORE at the assumed licence']}"
163 | )
164 | pat = re.compile(r"(\$\{tbl\(\['Route','Effort PD','Build INR Cr','Licence 5yr','All in 5yr','Reading'\],6,\n\s*)\{[\s\S]*?\}(\)\})")
165 | m = pat.search(wf)
166 | check(m is not None, "wireframe deployment table located")
167 | if m:
168 | before = len(wf)
169 | wf = wf[:m.start()] + m.group(1) + DEPLOY_ROWS + m.group(2) + wf[m.end():]
170 | check(abs(len(wf) - before) < 900, f"deployment substitution is proportionate ({len(wf)-before:+d} chars)")
171
172 | wf2, k = re.subn(r"Roughly ₹[\d.]+ lakh a year\.",
173 | f"Roughly ₹{FIG['breakeven']:.0f} lakh a year.", wf)
174 | check(k == 1, f"break-even injected into the wireframe ({k} site)")
175 | wf = wf2
176 | wf2, k = re.subn(r"about ₹[\d.]+ lakh a year, roughly \$[\d,]+",
177 | f"about ₹{FIG['breakeven']:.0f} lakh a year, roughly ${round(FIG['breakeven']*100000/83/1000)*1000:,}", wf)
178 | check(k >= 0, f"break-even dollar equivalent updated ({k} site)")
179 | wf = wf2
180 | wf2, k = re.subn(r"tops out around \$?[\d.]+M", f"tops out around ₹{FIG['arr_producer_high']:.0f} crore", wf)
181 | check(k >= 0, f"producer ceiling injected ({k} site)")
182 | wf = wf2
183 | for sym in ["SCREENS", "renderMap", "function paint"]:
184 | check(sym in wf, f"wireframe still contains {sym} after substitution")
185
186 | # ───────────────────────────── 3. regenerate the app's coverage map FROM the wireframe
187 | screens = re.findall(r"\{id:'([a-z-]+)',g:'(\w+)',n:'([^']*)'", wf)
188 | check(len(screens) >= 30, f"parsed {len(screens)} screens from the wireframe")
189
190 | # implementation status, keyed by wireframe screen id — the only hand-maintained part,
191 | # and it now fails loudly if a screen id appears that nobody has classified.
192 | STATUS = {
193 | 'map':('n/a','Navigation artefact, not an application screen'),
194 | 'boundary':('n/a','Decision artefact'),
195 | 'market':('n/a','Decision artefact'),
196 | 'schema':('built','Traceability explorer, plus the three closures as live queries'),
197 | 'deploy':('n/a','Decision artefact — priced in the estimate workbook'),
198 | 'proj-list':('built','Console › Projects'),
199 | 'proj-detail':('built','Console › Projects › detail'),
200 | 'material':('partial','Material fields on the project; processing steps not modelled'),
201 | 'homogeneity':('built','Console › Studies — u(bb) feeds the budget'),
202 | 'stability':('built','Console › Studies — shelf life, storage and transport class derived'),
203 | 'characterisation':('built','Console › Studies — u(char) feeds the budget'),
204 | 'values':('built','Console › Property values — budget derived, signature bound'),
205 | 'authorise':('built','Console › Value authorisation — SoD, competence and step-up enforced'),
206 | 'lots':('built','Console › Lot register — release supersedes the previous lot'),
207 | 'cert-build':('built','Issue from the lot register, step-up gated and §11.70 bound'),
208 | 'cert-template':('not built','Multi-tenant templating deferred'),
209 | 'cert-registry':('built','Console › Certificates — issue diff, holder list, per-issue verification'),
210 | 'catalogue':('built','Console › Catalogue — listable only with a current certificate'),
211 | 'entitlement':('built','Console › Entitlement — SoD enforced, revalidation set'),
212 | 'orders':('built','Console › Orders — allocation at the line, break-glass PII reveal'),
213 | 'order-detail':('partial','Line-level allocation shown; full linked-record view deferred'),
214 | 'dispatch':('built','Console › Dispatch — pack instruction from the storage class'),
215 | 'storefront':('built','Customer › Catalogue'),
216 | 'cust-account':('built','Customer › My vault'),
217 | 'vault':('built','Customer › My vault with a CSV audit pack'),
218 | 'conformance':('built','Console › Conformance — recomputes live, exports an assessment pack'),
219 | 'audit':('built','Console › Audit ledger — verify, tamper, CSV export'),
220 | 'subcontract':('built','Console › Subcontractors — five forbidden activities blocked'),
221 | 'capa':('partial','Register with computed impact; investigation workflow deferred'),
222 | 'equipment':('built','Console › Equipment — dated intervals, impact trace'),
223 | 'competence':('built','Console › Competence — dated, checked at signing, snapshotted'),
224 | 'users':('built','Console › Users and roles, with the SoD rules table'),
225 | 'tenant':('built','Console › Tenant configuration — IPC is a profile, not a fork'),
226 | 'integrations':('not built','No external systems in a single-file prototype'),
227 | 'analytics':('not built','Deferred'),
228 | 'mobile-cust':('not built','QR scan stubbed in the vault'),
229 | 'mobile-dispatch':('not built','Deferred'),
230 | }
231 | missing = [i for i, g, nm in screens if i not in STATUS]
232 | check(not missing, f"every wireframe screen has a classification (unclassified: {missing})")
233 | if missing:
234 | print("\nA screen was added to the wireframe without a status. Add it to STATUS in this script.")
235 | raise SystemExit(1)
236
237 | rows = []
238 | for sid, grp, name in screens:
239 | st, where = STATUS[sid]
240 | esc = lambda x: x.replace("\\", "\\\\").replace("'", "\\'")
241 | rows.append(f" ['{grp}','{esc(name)}','{st}','{esc(where)}']")
242 | COVERAGE = "const COVERAGE=[\n" + ",\n".join(rows) + "];"
243
244 | ap_head, ap_embed, ap_tail = split_embedded(open(AP).read())
245 | ap = ap_head + ap_tail
246 | pat2 = re.compile(r"const COVERAGE=\[[\s\S]*?\];")
247 | m2 = pat2.search(ap)
248 | check(m2 is not None, "app coverage block located")
249 | if m2:
250 | before = len(ap)
251 | ap = ap[:m2.start()] + COVERAGE + ap[m2.end():]
252 | check(abs(len(ap) - before) < 4000, f"coverage substitution is proportionate ({len(ap)-before:+d} chars)")
253 | for sym in ["function vCoverage", "function cSecurity", "function render", "SOD_RULES", "bindSignature"]:
254 | check(sym in ap, f"app still contains {sym} after substitution")
255
256 | ap2, k = re.subn(r"break-even licence of roughly ₹[\d.]+ lakh a year",
257 | f"break-even licence of roughly ₹{FIG['breakeven']:.0f} lakh a year", ap)
258 | check(k == 1, f"break-even injected into the app ({k} site)")
259 | ap = ap2
260
261 | # ───────────────────────────── 4. write only if everything held
262 | if FAIL:
263 | print(f"\n{len(FAIL)} check(s) failed — NOTHING WRITTEN")
264 | for f in FAIL: print(" " + f)
265 | raise SystemExit(1)
266 | open(WF, "w").write(wf)
267 | if ap_embed:
268 | ap = ap[:len(ap_head)] + ap_embed + ap[len(ap_head):]
269 | open(AP, "w").write(ap)
270 | built = sum(1 for _, _, n in screens if STATUS[_ if False else _][0] == 'built') if False else sum(1 for i, g, n in screens if STATUS[i][0] == 'built')
271 | print(f"\nSYNCED. {len(screens)} wireframe screens -> {len(rows)} coverage rows "
272 | f"({built} built). Figures injected from the workbook. Both files written.")
273
274
275 | # ══════════════════ CHECK ══════════════════
276 | def check_all():
277
278
279 | RESULTS = []
280 | def check(name, ok, detail=""):
281 | RESULTS.append((name, ok, detail))
282 | print(f" {'PASS' if ok else 'FAIL'} {name}{'' if ok else ' — ' + detail}")
283 | return ok
284
285 | app = strip_embedded(open(AP).read())
286 | wfm = strip_embedded(open(WF).read())
287
288 | # ══════════════════════════════════════════════════════════════════
289 | # 1. DUPLICATE DECLARATIONS
290 | # Cause: re-running a patch script after a mid-script assert re-applied an
291 | # insertion, nested inside the first copy. JS allows it, so nothing complained.
292 | # ══════════════════════════════════════════════════════════════════
293 | print("\n1. Duplicate declarations (re-run patch scripts)")
294 | for label, src in (("app", app), ("wireframe", wfm)):
295 | fns = re.findall(r"^function\s+(\w+)\s*\(", src, re.M)
296 | consts = re.findall(r"^const\s+([A-Z_][A-Z0-9_]*)\s*=", src, re.M)
297 | dup_f = sorted({f for f in fns if fns.count(f) > 1})
298 | dup_c = sorted({c for c in consts if consts.count(c) > 1})
299 | check(f"{label}: no duplicate function declarations", not dup_f, ", ".join(dup_f))
300 | check(f"{label}: no duplicate top-level constants", not dup_c, ", ".join(dup_c))
301
302 | # ══════════════════════════════════════════════════════════════════
303 | # 2. CROSS-SHEET REFERENCES POINT AT NUMBERS
304 | # Cause: a hardcoded 'Scenario E Model'!C122 that pointed at a paragraph of prose
305 | # after rows shifted. Recalc reported an error, but only because the arithmetic
306 | # happened to fail — a reference landing on the wrong NUMBER would be silent.
307 | # ══════════════════════════════════════════════════════════════════
308 | print("\n2. Cross-sheet references resolve to numbers")
309 | wb = openpyxl.load_workbook(XL)
310 | wv = openpyxl.load_workbook(XL, data_only=True)
311 | # openpyxl drops cached values on save, so an un-recalculated workbook makes EVERY
312 | # reference look non-numeric. Distinguish that from a genuinely broken reference.
313 | cached = sum(1 for ws in wv.worksheets for row in ws.iter_rows() for c in row
314 | if isinstance(c.value, (int, float)))
315 | if not check("workbook has been recalculated (cached values present)", cached > 200,
316 | f"only {cached} numeric cells — run recalc.py before this linter"):
317 | print(" skipping reference checks: they cannot be meaningful without cached values")
318 | ref_re = re.compile(r"'([^']+)'!\$?([A-Z]{1,3})\$?(\d+)")
319 | bad, total = [], 0
320 | for ws in wb.worksheets:
321 | for row in ws.iter_rows():
322 | for c in row:
323 | if not (isinstance(c.value, str) and c.value.startswith("=")):
324 | continue
325 | for sheet, col, rownum in ref_re.findall(c.value):
326 | total += 1
327 | if sheet not in wv.sheetnames:
328 | bad.append(f"{ws.title}!{c.coordinate} -> missing sheet '{sheet}'"); continue
329 | tgt = wv[sheet][f"{col}{rownum}"].value
330 | if not isinstance(tgt, (int, float)):
331 | bad.append(f"{ws.title}!{c.coordinate} -> '{sheet}'!{col}{rownum} is {type(tgt).__name__}")
332 | check(f"all {total} cross-sheet references land on numeric cells", not bad, "; ".join(bad[:4]))
333
334 | print("\n3. Named ranges resolve to numbers")
335 | nbad = []
336 | for nm in wb.defined_names:
337 | dn = wb.defined_names[nm]
338 | m = ref_re.search(dn.attr_text or "")
339 | if not m:
340 | nbad.append(f"{nm} unparseable"); continue
341 | sheet, col, rownum = m.groups()
342 | tgt = wv[sheet][f"{col}{rownum}"].value if sheet in wv.sheetnames else None
343 | if not isinstance(tgt, (int, float)):
344 | nbad.append(f"{nm} -> {sheet}!{col}{rownum} is {type(tgt).__name__}")
345 | check(f"all {len(wb.defined_names)} named ranges point at numeric cells", not nbad, "; ".join(nbad))
346
347 | print("\n4. Formula errors after recalculation")
348 | errs = []
349 | SOURCE_SHEETS = {"Toolchain (build.py)"} # holds script text, not formulas
350 | for ws in wv.worksheets:
351 | if ws.title in SOURCE_SHEETS:
352 | continue
353 | for row in ws.iter_rows():
354 | for c in row:
355 | if isinstance(c.value, str) and c.value.startswith("#"):
356 | errs.append(f"{ws.title}!{c.coordinate}={c.value}")
357 | check("no cached formula errors", not errs, "; ".join(errs[:5]))
358
359 | # ══════════════════════════════════════════════════════════════════
360 | # 5. PERMISSIONS REFERENCED BUT NEVER DEFINED
361 | # Cause: exportLedger guarded on 'audit:export', absent from PERMS, so it 403'd
362 | # for every role — silently, because a denial looks like a working control.
363 | # ══════════════════════════════════════════════════════════════════
364 | print("\n5. Permissions and roles")
365 | perms_block = app[app.index("const PERMS={"):app.index("const ROLES={")]
366 | defined = set(re.findall(r"'([a-z_]+:[a-z_]+)'\s*:", perms_block))
367 | used = set(re.findall(r"guard\('([a-z_]+:[a-z_]+)'", app)) ¦ set(re.findall(r"can\('([a-z_]+:[a-z_]+)'", app))
368 | check(f"every permission used ({len(used)}) is defined ({len(defined)})",
369 | not (used - defined), ", ".join(sorted(used - defined)))
370 | roles_block = app[app.index("const ROLES={"):app.index("const USERS=")]
371 | granted = set(re.findall(r"'([a-z_]+:[a-z_]+)'", roles_block))
372 | if "Object.keys(PERMS)" in roles_block:
373 | granted ¦= defined # a role that grants every permission programmatically
374 | check("no role grants an undefined permission", not (granted - defined), ", ".join(sorted(granted - defined)))
375 | orphan = defined - granted
376 | check("every defined permission is granted to at least one role", not orphan, ", ".join(sorted(orphan)))
377
378 | # ══════════════════════════════════════════════════════════════════
379 | # 6. EVERY MODULE HAS A RENDERER
380 | # Cause: a dead 'dash' fallback crashed the app for a role with no console modules.
381 | # ══════════════════════════════════════════════════════════════════
382 | print("\n6. Routing")
383 | mods = set(re.findall(r"\['([a-z]+)','[^']+',(?:'[a-z_:]+'¦null)\]", app))
384 | route_map = re.search(r"const body=\{([\s\S]*?)\}\[S\.sub\]\(\);", app)
385 | routed = set(re.findall(r"(\w+):c\w+", route_map.group(1))) if route_map else set()
386 | check(f"every sidebar module ({len(mods)}) has a renderer", not (mods - routed), ", ".join(sorted(mods - routed)))
387 | check("no renderer without a module", not (routed - mods), ", ".join(sorted(routed - mods)))
388
389 | # ══════════════════════════════════════════════════════════════════
390 | # 7. INLINE HANDLERS CALL FUNCTIONS THAT EXIST
391 | # ══════════════════════════════════════════════════════════════════
392 | print("\n7. Inline handlers")
393 | defined_fns = set(re.findall(r"function\s+(\w+)\s*\(", app)) ¦ set(re.findall(r"(?:const¦let)\s+(\w+)\s*=\s*(?:\([^)]*\)¦\w+)\s*=>", app))
394 | BUILTINS = {"if","for","while","switch","return","typeof","parseInt","parseFloat","Math","JSON","Number",
395 | "String","Array","Object","Date","alert","console","document","window","setTimeout","URL","Blob"}
396 | called = set()
397 | for h in re.findall(r'onclick="([^"]*)"', app) + re.findall(r'onchange="([^"]*)"', app) + re.findall(r"oninput=\"([^\"]*)\"", app):
398 | # a name preceded by a dot is a method call, not a global function
399 | called ¦= set(re.findall(r"(?<![.\w])([a-zA-Z_]\w*)\s*\(", h))
400 | missing = sorted(called - defined_fns - BUILTINS)
401 | check(f"every function called from an inline handler ({len(called)}) is defined", not missing, ", ".join(missing))
402
403 | # ══════════════════════════════════════════════════════════════════
404 | # 8. TEMPLATE-LITERAL AND ESCAPING HAZARDS
405 | # ══════════════════════════════════════════════════════════════════
406 | print("\n8. Escaping hazards")
407 | backticked = [h[:60] for h in re.findall(r'on(?:click¦input¦change)="([^"]*)"', app) if "`" in h]
408 | check("no backticks inside inline handlers", not backticked, "; ".join(backticked[:2]))
409 | check("no double-backslash escapes in either HTML file",
410 | "\\\\'" not in app and "\\\\'" not in wfm, "found a Python-mangled escape")
411
412 | # ══════════════════════════════════════════════════════════════════
413 | # 9. DRIFT — the coverage map must match the wireframe
414 | # ══════════════════════════════════════════════════════════════════
415 | print("\n9. Cross-file drift")
416 | wf_screens = re.findall(r"\{id:'([a-z-]+)',g:'(\w+)',n:'([^']*)'", wfm)
417 | cov_rows = re.findall(r"^ \['(\w+)','([^']*)','([^']*)','", app, re.M)
418 | check("coverage row count equals wireframe screen count",
419 | len(cov_rows) == len(wf_screens), f"{len(cov_rows)} rows vs {len(wf_screens)} screens")
420 | wf_names = {n.replace("\\'", "'") for _, _, n in wf_screens}
421 | cov_names = {n.replace("\\'", "'") for _, n, _ in cov_rows}
422 | check("no wireframe screen missing from coverage", not (wf_names - cov_names), ", ".join(sorted(wf_names - cov_names)))
423 | check("no orphan coverage rows", not (cov_names - wf_names), ", ".join(sorted(cov_names - wf_names)))
424
425 | # ══════════════════════════════════════════════════════════════════
426 | # 10. HARNESSES MUST ASSERT THEIR OWN ASSERTION COUNT
427 | # Cause: three separate green results came from tests that never ran.
428 | # ══════════════════════════════════════════════════════════════════
429 | print("\n10. Harness self-checks")
430 | hs = [f for f in os.listdir("/home/claude") if f.startswith(("verify", "vsec", "vfinal", "vall")) and f.endswith(".js")]
431 | for h in sorted(hs):
432 | src = open(f"/home/claude/{h}").read()
433 | check(f"{h} prints and guards its assertion count",
434 | "assertions ran" in src and re.search(r"RAN\s*<\s*\d+", src) is not None,
435 | "no count guard")
436
437 | # ══════════════════════════════════════════════════════════════════
438 | print("\n" + "=" * 70)
439 | failed = [r for r in RESULTS if not r[1]]
440 | print(f"{len(RESULTS)} checks ran — {len(RESULTS) - len(failed)} passed, {len(failed)} failed")
441 | assert len(RESULTS) >= 20, "the linter itself did not run enough checks — investigate"
442 | if failed:
443 | print("\nFAILURES:")
444 | for n, _, d in failed: print(f" {n} — {d}")
445 | return 1 if failed else 0
446
447
448 | if __name__ == "__main__":
449 | cmd = sys.argv[1] if len(sys.argv) > 1 else "all"
450 | rc = 0
451 | if cmd in ("sync", "all"):
452 | sync()
453 | if cmd in ("check", "all"):
454 | rc = check_all()
455 | sys.exit(rc or 0)
456

## Product Build
Lotmark — Cost to Build the Product
Never estimated before. This is the product itself, not any one customer's deployment. Same three-point and Monte Carlo method as the rest of the workbook.
Ref | Module | Opt (PD) | Likely (PD) | Pess (PD) | Expected (PD) | Sigma (PD) | Note
Foundation
A1 | Discovery, domain model and architecture | 24 | 36 | 55 | 37 | 5.2 | The three traceability closures are architecture, not features.
A2 | Design system and UX across ~40 screens | 30 | 45 | 68 | 46 | 6.3
| Foundation subtotal | 54 | 81 | 123 | 83
Production
P1 | Project and production plan | 20 | 30 | 46 | 31 | 4.3 | ISO 17034 §7.2
P2 | Candidate material, processing steps, packaging | 16 | 24 | 38 | 25 | 3.7 | §7.4
P3 | Homogeneity study and statistics | 22 | 34 | 52 | 35 | 5 | §7.5 — produces u(bb)
P4 | Stability studies, short, long and ongoing | 24 | 36 | 55 | 37 | 5.2 | §7.6 — produces shelf life and transport class
P5 | Characterisation and interlaboratory comparison | 20 | 30 | 48 | 31 | 4.7 | §7.7 — produces u(char)
P6 | Property values and uncertainty budget engine | 26 | 38 | 58 | 39 | 5.3 | §7.8 — derived, never typed
P7 | Value authorisation workflow | 14 | 22 | 34 | 23 | 3.3 | §6.2 — non-subcontractable, SoD enforced
P8 | Lot register, supersession and expiry | 20 | 30 | 46 | 31 | 4.3 | §7.9
| Production subtotal | 162 | 244 | 377 | 252
Certification
C1 | Certificate generation from authorised values | 22 | 32 | 50 | 33 | 4.7 | ISO Guide 31
C2 | Template designer and versioning | 26 | 38 | 58 | 39 | 5.3 | The multi-tenant hinge
C3 | Registry, reissue, diff and holder list | 20 | 30 | 46 | 31 | 4.3 | Closure 2
| Certification subtotal | 68 | 100 | 154 | 103
Distribution
D1 | Catalogue and listing rules | 14 | 22 | 34 | 23 | 3.3
D2 | Entitlement engine and verification workflow | 18 | 26 | 40 | 27 | 3.7
D3 | Orders and lot allocation | 20 | 30 | 46 | 31 | 4.3 | Allocation at the line makes the holder list computable
D4 | Dispatch and cold chain | 22 | 32 | 50 | 33 | 4.7 | §7.10
D5 | Customer accounts and laboratory vault | 24 | 36 | 55 | 37 | 5.2 | The second product, built as a surface on the first
D6 | Public certificate retrieval API | 12 | 18 | 28 | 19 | 2.7 | Distribution strategy, not a feature
| Distribution subtotal | 110 | 164 | 253 | 170
Compliance
Q1 | ISO 17034 conformance engine and clause map | 24 | 36 | 55 | 37 | 5.2 | The reason a producer buys
Q2 | Audit ledger, hash chain, verify and export | 16 | 24 | 38 | 25 | 3.7 | §8.4
Q3 | Equipment, calibration and impact query | 16 | 24 | 38 | 25 | 3.7 | Closure 1
Q4 | Competence register, dated, enforced at signing | 14 | 20 | 32 | 21 | 3 | Closure 3 — §6.3
Q5 | Subcontractor register with forbidden-activity block | 10 | 15 | 24 | 16 | 2.3 | §6.2
Q6 | Complaints, nonconformity and CAPA | 18 | 26 | 40 | 27 | 3.7 | §8.6, §8.7
| Compliance subtotal | 98 | 145 | 227 | 151
Platform
X1 | Multi-tenancy, isolation and data residency | 30 | 45 | 70 | 47 | 6.7 | Government producers require in-country hosting
X2 | Identity, RBAC and segregation-of-duties engine | 24 | 36 | 55 | 37 | 5.2
X3 | Tenant settings, numbering series, storage classes | 14 | 22 | 34 | 23 | 3.3 | Existing series must continue unbroken
X4 | Integration framework: LIMS, ERP, courier, payment | 26 | 40 | 62 | 41 | 6 | Manual entry path ships first; integration is the upgrade
X5 | Analytics and MIS | 20 | 30 | 46 | 31 | 4.3
X6 | Notification service | 12 | 18 | 28 | 19 | 2.7
| Platform subtotal | 126 | 191 | 295 | 198
Field
F1 | Customer mobile: QR scan and vault | 24 | 36 | 55 | 37 | 5.2
F2 | Dispatch handheld | 18 | 26 | 40 | 27 | 3.7
| Field subtotal | 42 | 62 | 95 | 64
Quality assurance
QA1 | Test strategy and cases | 16 | 24 | 38 | 25 | 3.7
QA2 | Functional and regression | 40 | 60 | 92 | 62 | 8.7
QA3 | Automation | 30 | 45 | 68 | 46 | 6.3
QA4 | Performance | 12 | 18 | 28 | 19 | 2.7
QA5 | Accessibility | 14 | 20 | 32 | 21 | 3
QA6 | Security engineering and penetration test | 16 | 24 | 38 | 25 | 3.7
| Quality assurance subtotal | 128 | 191 | 296 | 198
Product management
PM1 | Product and delivery management | 50 | 75 | 115 | 78 | 10.8
PM2 | Documentation and standard operating procedures | 16 | 24 | 38 | 25 | 3.7
PM3 | Launch, onboarding and migration tooling | 14 | 22 | 34 | 23 | 3.3 | Producers arrive with a spreadsheet or a PDF list
| Product management subtotal | 80 | 121 | 187 | 126
| TOTAL BASE (P50 basis) | 868 | 1299 | 2007 | 1345
MONTE CARLO — 60,000 iterations, correlation 0.5, five product risks sampled inside the run
| P50 — even odds | 1557 | person-days |  |  |  | Never bid or budget this.
| P80 — RECOMMENDED BUILD BUDGET | 1676 | person-days |  |  |  | Same standard used for the IPC bid basis.
| P90 — conservative | 1737 | person-days |  |  |  | If the runway is fixed and cannot extend.
| Build cost at the blended rate | 2.54 | INR crore |  |  |  | Compare against the INR 5.62 crore a single bespoke customer build was priced at.
| The finding | The product costs less to build than one bespoke customer engagement was priced at. That is the whole argument for productising: the same money buys an asset that can be sold repeatedly rather than a deliverable that can be sold once. It also means the first customer can, in principle, fund the product.

## Market & Revenue
Market and Revenue Model
Moved here from the wireframe. The cost side and the revenue side of the same decision now live in one file.
COUNTED POPULATIONS — not estimated
Ref | Population | Count | Source | Confidence | Note
M1 | RM producers accredited under the ILAC MRA | 320 | ILAC Secretariat 2025 | authoritative | The producer TAM. Every prospect can be named.
M2 | Producers registered in COMAR | 220 | BAM COMAR guide | floor | Voluntary listing, so an undercount.
M3 | Certified reference materials listed in COMAR | 11000 | BAM COMAR guide | floor | About 50 per producer; the estate examined carries 1,341.
M4 | Laboratories accredited to ISO/IEC 17025 | 114600 | ILAC Secretariat 2025 | authoritative | The vault TAM, 358x the producer population.
MODEL A — THE PRODUCER PLATFORM
Ref | Step | Low | Base | High | Basis
A1 | Producer universe | 400 | 550 | 700 | M1 accredited plus unaccredited producers
A2 | Addressable share (carry enough SKUs to need a system) | 30% | 35% | 40% | WEAKEST INPUT. Nobody publishes SKU counts per producer.
A3 | Addressable producers | 120 | 193 | 280
A4 | Five-year penetration | 15% | 25% | 40% | Vertical SaaS into a listable population
A5 | Customers | 18 | 48 | 112
A6 | Annual contract value (INR lakh) | 25 | 50 | 92 | Benchmarked against mid-market LIMS
A7 | Annual recurring revenue (INR Cr) | 4.5 | 24 | 103.04
MODEL B — THE LABORATORY VAULT
Ref | Step | Low | Base | High | Basis
B1 | Accredited laboratory universe | 114600 | 114600 | 114600 | M4, an authoritative count
B2 | Addressable share (hold enough standards to care) | 30% | 40% | 50% | WEAKEST INPUT. Untested.
B3 | Addressable laboratories | 34380 | 45840 | 57300
B4 | Five-year penetration | 0.5% | 2% | 5% | Self-serve, low touch, seeded by producers
B5 | Customers | 172 | 917 | 2865
B6 | Annual contract value (INR lakh) | 1 | 2.5 | 5 | Per-laboratory subscription
B7 | Annual recurring revenue (INR Cr) | 1.72 | 22.925 | 143.25
THE CONTRADICTION THIS SHEET EXISTS TO SURFACE
| Base ACV assumed for a producer (INR lakh/yr) | 50
| Break-even licence for the largest plausible tenant | 28.1 |  |  | From Scenario E: above this, that customer is cheaper commissioning bespoke.
| Gap | 21.9 | INR lakh/yr |  | Positive means the assumed price exceeds what the biggest customer can justify.
| Reading it honestly | The producer market is listable but small, and the base annual contract value assumed here exceeds the break-even for the largest plausible tenant. Either the price is too high, or the largest government producers are not the segment the product is for. Two conversations with accredited producers would settle it, and would also replace the addressable share in both models — the weakest input in this entire workbook, and the one that moves the answer most.

## Product Sensitivity
Product Build — What Moves the Number
Same treatment the IPC estimate gets. Each row is a re-run of the simulation, not a multiplier.
Rank | Variable | Range tested | P80 low (PD) | P80 high (PD) | Swing (PD) | Reading
1 | Overall estimate accuracy | every module ±30% | 1251 | 2101 | 850 | Dominates: the estimate's own accuracy, not any single decision.
2 | Exogenous risks realised | none fire vs all fire | 1439 | 1825 | 386
3 | Multi-tenancy depth | row isolation vs per-tenant keys | 1620 | 1795 | 175
4 | Certificate templating | one format vs a designer | 1635 | 1770 | 135
5 | Correlation between modules | independent vs strongly coupled | 1639 | 1731 | 92
6 | Field applications | dropped vs both shipped | 1613 | 1705 | 92
| P80 baseline for comparison |  | 1675

## Product Funding
Product Build — Funding, Ramp and Cross-check
The IPC number is defended six ways. This gives the product number the same treatment.
MONTHLY PROFILE — 12-month build at P80
Ref | Line | M1 | M2 | M3 | M4 | M5 | M6 | Note
C1 | Ramp weight (relative) | 0.4 | 0.7 | 1 | 1.15 | 1.25 | 1.25 | Peaks mid-build, tapers into hardening.
C2 | Person-days | 60 | 105 | 150 | 172 | 187 | 187
C3 | FTE | 2.9 | 5 | 7.1 | 8.2 | 8.9 | 8.9
C4 | Spend (INR lakh) | 9.1 | 15.9 | 22.7 | 26 | 28.3 | 28.3
| Peak FTE | 8.9 | [5 empty] | First six months shown; the profile is symmetric thereafter.
| Total build cost (INR Cr) | 2.53
| Peak funding required before first revenue (INR Cr) | 2.53 | [5 empty] | No customer revenue during the build, so peak funding equals the whole build. That is the number to raise or absorb.
INDEPENDENT CROSS-CHECK — screen and entity count
Ref | Artefact | Count | PD each | Total (PD) |  |  |  | Basis
X1 | Application screens | 37 | 14 | 518 |  |  |  | Design, build, test, accessibility per screen
X2 | Domain entities with full lifecycle | 22 | 12 | 264 |  |  |  | Schema, validation, state machine, audit
X3 | Integration surfaces | 9 | 22 | 198 |  |  |  | LIMS, ERP, courier, payment, identity, e-invoicing
X4 | Statistical routines | 6 | 18 | 108 |  |  |  | ANOVA, regression, consensus, budget, tornado, holder list
X5 | Compliance artefacts | 8 | 26 | 208 |  |  |  | Clause map, validation pack, retention, residency
| Cross-check total (PD) |  |  | 1296
| Bottom-up P80 (PD) |  |  | 1675
| Divergence |  |  | -22.63% |  |  |  | Two methods built from different primitives. A divergence under about 20% is agreement; beyond that, reconcile before committing.

## Effort - Mobile & IPRS
Workstream A-G ¦ Mobile App for IPRS/IMPRS + Admin Console
Pink = scope the document omits. Green = scope found only by inspecting the live estate. Sigma = (Pess - Opt) / 6.
Ref | Workstream / Module | Source | Opt (PD) | Likely (PD) | Pess (PD) | Expected (PD) | Sigma (PD) | Notes
A | Discovery & Architecture
A1 | Requirements elaboration, SRS and traceability matrix | Doc A | 22 | 32 | 50 | 33 | 4.7 | 39 obligations, no acceptance criteria.
A2 | Solution architecture, domain model, integration contracts | Doc A | 18 | 28 | 45 | 29 | 4.5 | Must resolve catalogue ownership against the OpenCart estate.
| A subtotal |  | 40 | 60 | 95 | 62 | 6.5
B | Experience Design
B1 | Design system and accessible mobile UI kit | Doc A §7 | 18 | 26 | 40 | 27 | 3.7 | WCAG 2.1 AA assumed; Doc A omits the level.
B2 | Mobile screen design, ~55 screens, two platforms | Doc A | 24 | 36 | 52 | 37 | 4.7
B3 | Admin console design, ~40 screens, four roles | Doc A §6 | 18 | 28 | 42 | 29 | 4
| B subtotal |  | 60 | 90 | 134 | 93 | 7.2
C | Mobile Application (iOS + Android)
C1 | App foundation, navigation, state, mobile CI/CD | Doc A | 24 | 34 | 50 | 35 | 4.3
C2 | Registration, OTP, biometric, MFA, institutional onboarding | Doc A §1 | 20 | 30 | 45 | 31 | 4.2 | GSTIN validation assumed in scope.
C3 | IPRS/IMPRS catalogue, lot detail, CoA / LVS / SDS viewer | Doc A §2.1 | 28 | 40 | 58 | 41 | 5 | Verified 1,341 priced SKUs across the two published lists.
C4 | Publications and subscriptions, edition history, renewals | Doc A §2.2 | 15 | 22 | 34 | 23 | 3.2 | Overlaps the portal catalogue — see Unification.
C5 | Smart search, filters, predictive, voice, recommendations | Doc A §3.1 | 20 | 30 | 46 | 31 | 4.3
C6 | Cart, checkout and order lifecycle | NOT IN DOC | 30 | 45 | 68 | 46 | 6.3 | GAP: Doc A defines no ordering journey despite being a sales app.
C7 | Payment: gateway SDK, UPI, cards, netbanking, PO approval | Doc A §4 | 20 | 30 | 46 | 31 | 4.3 | PCI scope assumed SAQ-A via hosted fields.
C8 | Notifications: push, SMS, email, preference centre | Doc A §5.1 | 12 | 18 | 28 | 19 | 2.7
C9 | Feedback, support ticketing, FAQ, self-help | Doc A §5.3 | 14 | 20 | 30 | 21 | 2.7
C10 | Accessibility engineering to WCAG 2.1 AA, both platforms | Doc A §7 | 16 | 25 | 40 | 26 | 4
C11 | GIGW 3.0 mobile conformance and CERT-In cyber chapter | NOT IN DOC | 14 | 20 | 32 | 21 | 3 | GAP: GIGW 3.0's cybersecurity chapter explicitly covers mobile apps. Doc A never cites GIGW.
C12 | App hardening: pinning, root detection, obfuscation, cache | Doc A §7 | 13 | 20 | 32 | 21 | 3.2
C13 | Store submission, release engineering, phased rollout | Doc A | 8 | 12 | 20 | 13 | 2 | Doc A's simultaneous-release clause is not achievable through store review.
| C subtotal |  | 234 | 346 | 529 | 359 | 14.2
D | Admin Console (web)
D1 | Console foundation, four-role RBAC, audit instrumentation | Doc A §6 | 24 | 34 | 50 | 35 | 4.3
D2 | IPRS Admin: lots, batches, expiry, stock signals | Doc A §6 | 22 | 32 | 48 | 33 | 4.3
D3 | CoA and Lot Validity Statement generation engine | Doc A §2.1 | 16 | 24 | 38 | 25 | 3.7
D4 | Price-tier engine and government-organisation assignment | Doc A §4 | 16 | 24 | 38 | 25 | 3.7 | REDUCED from v1: IPC already publishes a two-tier price list at exactly 50%. This is tier assignment, not a discount engine.
D5 | Verification workflow: document review, approval, revalidation | Doc A §4 | 18 | 26 | 40 | 27 | 3.7 | This, not the arithmetic, is the real control.
D6 | Dispatch Admin: scheduling, couriers, slips, tracking | Doc A §6 | 27 | 40 | 60 | 41 | 5.5 | Cold-chain handling absent from Doc A — risk K11.
D7 | Order management console, refunds, cancellations | Doc A §4 | 17 | 25 | 38 | 26 | 3.5
D8 | User management and registration logs | Doc A §1 | 10 | 15 | 24 | 16 | 2.3
D9 | Notification console: templates, scheduling, delivery reports | Doc A §5.2 | 13 | 20 | 30 | 21 | 2.8
D10 | Feedback and ticket management, escalation | Doc A §5.4 | 13 | 20 | 30 | 21 | 2.8
D11 | Search analytics and demand reporting | Doc A §3.2 | 15 | 22 | 34 | 23 | 3.2
D12 | Reporting engine, role-scoped, PDF/Excel, scheduling | Doc A §6 | 24 | 35 | 52 | 36 | 4.7
D13 | Immutable audit log: append-only, hash-chained, exportable | Doc A | 17 | 25 | 40 | 26 | 3.8 | Required nine times with no technical means specified.
| D subtotal |  | 232 | 342 | 522 | 355 | 13.7
E | Platform & Integration
E1 | API platform: catalogue, lot, order, identity services | Doc A | 48 | 70 | 105 | 72 | 9.5
E2 | Document generation: CoA, LVS, GST invoice, dispatch slip | Doc A | 20 | 30 | 46 | 31 | 4.3
E3 | Payment gateway and settlement reconciliation | Doc A §4 | 8 | 12 | 20 | 13 | 2
E4 | Courier API integration and tracking webhooks | Doc A | 10 | 15 | 24 | 16 | 2.3
E5 | Tally / ERP posting, reconciliation, GST e-invoicing (IRN) | Doc A | 14 | 20 | 32 | 21 | 3 | IRN generation is unmentioned in Doc A but mandatory above threshold.
E6 | Pin-code serviceability API | Doc A | 3 | 5 | 9 | 5 | 1
E7 | SMS and email integration incl. TRAI DLT registration | Doc A | 8 | 12 | 20 | 13 | 2 | DLT is mandatory in India and unmentioned.
E8 | IP Online federation and SSO | Doc A | 17 | 25 | 40 | 26 | 3.8 | Verified target: iponline.ipc.gov.in is a separate live system.
E9 | LIMS / QC ingest to source Certificate of Analysis data | NOT IN DOC | 16 | 24 | 40 | 25 | 4 | GAP CONFIRMED: lot data is published today as a manually maintained PDF. There is no evident digital source for CoA content.
E10 | Five-lot history backfill and lot data structuring | NOT IN DOC | 8 | 14 | 24 | 15 | 2.7 | GAP: IPC publishes one previous lot; Doc A requires five.
E11 | Infrastructure, IaC, environments, CI/CD, observability, DR | Doc A §7 | 30 | 45 | 68 | 46 | 6.3 | RTO/RPO undefined in Doc A; Doc B values assumed.
E12 | Security engineering, CERT-In audit support, VAPT | Doc A §7 | 20 | 30 | 48 | 31 | 4.7
| E subtotal |  | 202 | 302 | 476 | 314 | 15.2
F | Quality Assurance
F1 | Test strategy, cases, RTM linkage | Doc A | 18 | 26 | 40 | 27 | 3.7
F2 | Functional and regression testing | Doc A | 45 | 68 | 100 | 70 | 9.2
F3 | Test automation: API, UI, device farm | Doc A | 35 | 52 | 78 | 54 | 7.2
F4 | Performance and load testing | Doc A | 14 | 20 | 32 | 21 | 3 | No volumetrics stated; thresholds must be agreed.
F5 | Accessibility conformance testing and remediation | Doc A §7 | 14 | 20 | 32 | 21 | 3
F6 | Security testing and two VAPT cycles | Doc A §7 | 18 | 26 | 40 | 27 | 3.7
F7 | UAT support and defect triage | Doc A | 20 | 30 | 46 | 31 | 4.3
| F subtotal |  | 164 | 242 | 368 | 251 | 14.2
G | Programme Management & Enablement
G1 | Programme and delivery management | — | 60 | 90 | 135 | 93 | 12.5
G2 | Business analysis and requirements governance | — | 25 | 38 | 56 | 39 | 5.2
G3 | Documentation: SRS, HLD, LLD, manuals, SOPs | — | 18 | 28 | 44 | 29 | 4.3
G4 | Training and train-the-trainer, four admin roles | — | 12 | 18 | 28 | 19 | 2.7
G5 | Go-live, cutover, eight-week hypercare | — | 20 | 30 | 48 | 31 | 4.7
| G subtotal |  | 135 | 204 | 311 | 211 | 15.2
| TOTAL BASE EFFORT (P50, before risk reserve) |  | 1067 | 1586 | 2435 | 1645 | 33.9

## Effort - Website
Workstream H-S ¦ Website Redesign, Replatform and Migration
Pink = scope the document omits. Green = scope found only by inspecting the live estate. Sigma = (Pess - Opt) / 6.
Ref | Workstream / Module | Source | Opt (PD) | Likely (PD) | Pess (PD) | Expected (PD) | Sigma (PD) | Notes
H | Discovery & Content Strategy
H1 | Discovery, workshops, information architecture, sitemap | Doc B §1.1 | 18 | 28 | 44 | 29 | 4.3
H2 | Content audit and migration plan | NOT IN DOC | 8 | 13 | 22 | 14 | 2.3 | GAP, but now scoped from the live estate rather than assumed.
| H subtotal |  | 26 | 41 | 66 | 43 | 4.9
I | Experience Design
I1 | GIGW 3.0 / DBIM design system, bilingual type and grid | Doc B §1.1 | 20 | 30 | 46 | 31 | 4.3 | 88 mandatory GIGW guidelines across four domains.
I2 | Template design, ~28 page templates | Doc B §1.3 | 28 | 42 | 62 | 43 | 5.7
I3 | Commerce and account journey design | Doc B §1.7 | 10 | 16 | 26 | 17 | 2.7
| I subtotal |  | 58 | 88 | 134 | 91 | 7.6
J | CMS Platform
J1 | CMS platform setup, hardening, environments | Doc B §1.2 | 16 | 24 | 38 | 25 | 3.7 | Replaces Joomla.
J2 | RBAC and editorial approval workflow | Doc B §1.2.1 | 14 | 20 | 32 | 21 | 3
J3 | Bilingual WYSIWYG authoring, spellcheck, media embed | Doc B §1.2.1 | 8 | 12 | 20 | 13 | 2
J4 | Scheduling, auto-publish, auto-expire, expiry alerts | Doc B §1.2.1 | 7 | 10 | 16 | 11 | 1.5
J5 | Backup, versioning, rollback, version compare | Doc B §1.2.1 | 8 | 12 | 20 | 13 | 2
J6 | Immutable CMS audit trail and exportable logs | Doc B §1.2.1 | 12 | 18 | 28 | 19 | 2.7
J7 | Archival engine: rules, retention, archive section, labelling | Doc B §1.2.4 | 14 | 20 | 32 | 21 | 3 | Live estate shows a 2023 G20 banner and a 2019 site map — the requirement is well founded.
| J subtotal |  | 79 | 116 | 186 | 123 | 7
K | Content, Multimedia & Facilities
K1 | Video platform integration, player, captions, transcripts | Doc B §1.2.2 | 18 | 28 | 44 | 29 | 4.3
K2 | Image wizard: gallery, resize, alt text, bulk upload | Doc B §1.2.2 | 10 | 16 | 26 | 17 | 2.7
K3 | Document management: versioning, indexing, secure download | Doc B §1.2.3 | 16 | 24 | 38 | 25 | 3.7
K4 | Event calendar, registration, reminders, archive | Doc B §1.2.3 | 20 | 30 | 46 | 31 | 4.3
K5 | FAQ and glossary modules | Doc B §1.2.3 | 12 | 18 | 28 | 19 | 2.7
K6 | Polls and visitor survey with analytics | Doc B §1.2.3 | 10 | 16 | 26 | 17 | 2.7
K7 | Public forum: threads, moderation, reputation, redressal | Doc B §1.2.3 | 30 | 45 | 68 | 46 | 6.3 | Largest CMS module; heaviest moderation risk.
K8 | Recruitment form, tracking, export, HR dashboard | Doc B §1.2.3 | 16 | 24 | 38 | 25 | 3.7
| K subtotal |  | 132 | 201 | 314 | 209 | 11.2
L | Frontend & Engagement
L1 | Templates, mega menu, breadcrumbs, sticky nav, cards | Doc B §1.3.1 | 34 | 50 | 74 | 51 | 6.7
L2 | Personalisation widgets, quick tiles, one-click downloads | Doc B §1.3.3 | 12 | 18 | 28 | 19 | 2.7
L3 | Bilingual framework and language toggle | Doc B §1.1 | 10 | 15 | 26 | 16 | 2.7 | REDUCED from v1: a Hindi site already exists at /hi/.
L4 | Accessibility engineering to WCAG 2.1 AA | Doc B §1.1 | 26 | 38 | 58 | 39 | 5.3
| L subtotal |  | 82 | 121 | 186 | 125 | 9.4
M | Search & AI Layer
M1 | Search platform, indexing, multilingual facets, relevance | Doc B §1.3.2 | 22 | 32 | 50 | 33 | 4.7
M2 | Semantic / vector search and recommendations | Doc B §1.1 | 18 | 28 | 44 | 29 | 4.3
M3 | Voice search and text-to-speech / speech-to-text | Doc B §1.1 | 13 | 20 | 32 | 21 | 3.2
M4 | Chatbot assistant: retrieval, guardrails, escalation | Doc B §1.1 | 30 | 45 | 70 | 47 | 6.7 | Regulatory Q&A on drug alerts demands strict grounding.
M5 | AI auto-tagging and document classification | Doc B §1.1 | 16 | 24 | 38 | 25 | 3.7
M6 | AI moderation: spam, misuse, fraud detection | Doc B §1.1 | 12 | 18 | 30 | 19 | 3
M7 | AI governance: evaluation harness, accuracy testing, HITL | NOT IN DOC | 12 | 18 | 30 | 19 | 3 | GAP: seven AI features mandated with no accuracy or safety criteria.
| M subtotal |  | 123 | 185 | 294 | 193 | 11.3
N | E-Commerce (replatform)
N1 | Catalogue, categories, filters, bulk upload, versioning | Doc B §1.7.1 | 20 | 30 | 46 | 31 | 4.3
N2 | Catalogue data onboarding: 1,341 SKUs, lots, two price tiers | NEW | 16 | 25 | 42 | 26 | 4.3 | NEW: verified 702 IPRS + 639 IMPRS, currently maintained as PDFs.
N3 | Cart, checkout, address, shipping, tax, persistence, reorder | Doc B §1.7.2 | 24 | 35 | 52 | 36 | 4.7
N4 | Payment gateway, multi-currency, retries, reconciliation | Doc B §1.7.3 | 14 | 20 | 32 | 21 | 3
N5 | Order management, notifications, refunds, reports | Doc B §1.7.4 | 20 | 30 | 46 | 31 | 4.3
N6 | Customer accounts, history, invoices, subscriptions, tracking | Doc B §1.7.5 | 17 | 25 | 38 | 26 | 3.5
N7 | Promotions, discount codes, scheduling, banners | Doc B §1.7.6 | 12 | 18 | 28 | 19 | 2.7
N8 | Sales analytics, funnels, dashboards | Doc B §1.7.8 | 15 | 22 | 34 | 23 | 3.2
N9 | OpenCart data migration: products, customers, order history | NEW | 22 | 34 | 55 | 36 | 5.5 | NEW: the existing shop is live OpenCart. Neither document mentions migrating its data.
| N subtotal |  | 160 | 239 | 373 | 249 | 12.1
O | Analytics, Communication & Integration
O1 | Visitor analytics, event and journey tracking | Doc B §1.4.1 | 14 | 20 | 32 | 21 | 3
O2 | Heatmaps, funnel and behavioural analytics | Doc B §1.4.3 | 10 | 16 | 26 | 17 | 2.7
O3 | MIS dashboard: widgets, drill-down, scheduled reports | Doc B §1.4.4 | 24 | 35 | 52 | 36 | 4.7
O4 | DPDP consent management and Consent Manager integration | Doc B §1.4.5 | 18 | 28 | 44 | 29 | 4.3 | EXPANDED: Rules notified 13 Nov 2025; full compliance due 13 May 2027.
O5 | Transactional and promotional SMS/email, bilingual, analytics | Doc B §1.5 | 20 | 30 | 46 | 31 | 4.3
O6 | IP Online / PvPI integration and SSO across IPC portals | Doc B §1.6 | 24 | 35 | 52 | 36 | 4.7
| O subtotal |  | 110 | 164 | 252 | 170 | 9.9
P | Content Migration
P1 | Migration tooling and mapping, Joomla to target | NOT IN DOC | 16 | 24 | 40 | 25 | 4 | GAP, now scoped: ~137 English menu pages plus Hindi mirror.
P2 | Article and document migration, ~1,500 items, plus QA | NOT IN DOC | 22 | 34 | 55 | 36 | 5.5 | GAP, now scoped: Joomla article IDs run past 1,500.
P3 | Hindi coverage completion and bilingual QA | Doc B §1.1 | 10 | 15 | 26 | 16 | 2.7 | REDUCED: Hindi site already exists.
P4 | URL redirect mapping and SEO preservation | NOT IN DOC | 8 | 12 | 20 | 13 | 2 | GAP: omitting this loses inbound links at cutover.
| P subtotal |  | 56 | 85 | 141 | 90 | 7.6
Q | Infrastructure, Security & Certification
Q1 | NIC / MeitY hosting provisioning, IaC, environments | Doc B §3.1 | 20 | 30 | 46 | 31 | 4.3
Q2 | DR site, replication, failover, drill runbooks | Doc B §3.3 | 18 | 26 | 40 | 27 | 3.7 | RTO under 4h, RPO under 15min.
Q3 | Monitoring, IDPS, alerting, SOC handover | Doc B §2.3 | 12 | 18 | 28 | 19 | 2.7
Q4 | Security engineering and two VAPT cycles | Doc B §2.4 | 20 | 30 | 48 | 31 | 4.7
Q5 | GIGW 3.0 conformance and STQC CQW certification support | Doc B §1.1 | 18 | 28 | 44 | 29 | 4.3 | EXPANDED: 88 mandatory guidelines; CQW involves document review plus frontend and backend testing.
| Q subtotal |  | 88 | 132 | 206 | 137 | 8.9
R | Quality Assurance
R1 | Test strategy, cases, RTM across 152 obligations | Doc B | 16 | 24 | 38 | 25 | 3.7
R2 | Functional and regression testing | Doc B | 42 | 62 | 94 | 64 | 8.7
R3 | Test automation | Doc B | 28 | 42 | 64 | 43 | 6
R4 | Performance and load testing | Doc B §3.2 | 12 | 18 | 30 | 19 | 3 | Stated sizing is current traffic, not a peak-concurrency basis.
R5 | Accessibility conformance testing and remediation | Doc B §1.1 | 16 | 24 | 38 | 25 | 3.7
R6 | Bilingual content and cross-browser testing | Doc B §1.1 | 14 | 20 | 32 | 21 | 3
R7 | UAT support and defect triage | Doc B | 18 | 28 | 44 | 29 | 4.3
| R subtotal |  | 146 | 218 | 340 | 226 | 13.2
S | Programme Management & Enablement
S1 | Programme and delivery management | — | 55 | 82 | 124 | 85 | 11.5
S2 | Business analysis and content governance | — | 22 | 34 | 52 | 35 | 5
S3 | Documentation and standard operating procedures | — | 16 | 24 | 38 | 25 | 3.7
S4 | Training and train-the-trainer | — | 12 | 18 | 28 | 19 | 2.7
S5 | Go-live, cutover, hypercare | — | 18 | 28 | 44 | 29 | 4.3
| S subtotal |  | 123 | 186 | 286 | 193 | 14
| TOTAL BASE EFFORT (P50, before risk reserve) |  | 1183 | 1776 | 2778 | 1849 | 35

## Monte Carlo
Confidence — Monte Carlo Simulation
100,000 iterations. Beta-PERT marginals on every module, correlated through a Gaussian copula, with exogenous risk events sampled inside the same run. Replaces the v2 P80-plus-EMV method.
WHY THIS REPLACES THE v2 METHOD
| Composition error | v2 added an expected value to a P80 and labelled the sum a P80. A mean plus a percentile is neither. On this distribution the v2 figure of 3,623 PD actually sits at about P81.
| Distribution shape | v2 implied a normal spread. Task durations are bounded below and right-skewed; a normal understates the upper tail and permits negative durations. This run uses Beta-PERT, derived from the same optimistic / likely / pessimistic values already in the model.
| Correlation | v2 multiplied sigma by 3.5, a factor chosen by hand. Here correlation is an explicit parameter with its effect shown across four values, so the assumption is visible and testable rather than buried.
| Double counting | v2's register charged 135 PD of expected value for requirement volatility — which is exactly what the optimistic-to-pessimistic spread on all 122 modules already encodes. It is removed, and six further risks are reduced to their marginal exposure beyond the module pessimistic.
| Savings realisation | v2 treated the unification saving as certain. Here it is sampled at 70 to 110 per cent of nominal, since savings under-deliver more often than they over-deliver.
SIMULATION PARAMETERS
| Iterations | 100,000
| Modules sampled | 122
| Marginal distribution | Beta-PERT from O / M / P
| Dependence | Gaussian copula, single common factor
| Correlation used for headline | 0.5
| Exogenous risk events | 13
| Endogenous risks removed | K10 (requirement volatility)
| Unification saving | 524 PD, now computed from source modules, sampled 70–110%
| Random seed | 20260818 (reproducible)
SENSITIVITY TO THE CORRELATION ASSUMPTION
| Correlation | P50 (PD) | P70 (PD) | P80 (PD) | P90 (PD) | P95 (PD) | Reading
| rho = 0.0 | 3446 | 3574 | 3619 | 3670 | 3708 | Independent modules. Unrealistic — one team, one client, one set of ambiguities.
| rho = 0.3 | 3431 | 3572 | 3652 | 3756 | 3838 | Weak common cause. Plausible for a portfolio of unrelated projects.
| rho = 0.5 | 3424 | 3605 | 3714 | 3861 | 3984 | RECOMMENDED. Single accountable team on a single programme with shared requirement risk.
| rho = 0.7 | 3417 | 3654 | 3797 | 3994 | 4154 | Strong common cause. Appropriate if requirements remain unfrozen at award.
RECOMMENDED BASIS
| P50 — even odds | 3424 | person-days |  |  |  | Half of comparable programmes finish inside this. Never bid it.
| P80 — RECOMMENDED BID BASIS | 3714 | person-days |  |  |  | Standard commercial basis for a fixed-price government contract.
| P90 — conservative | 3861 | person-days |  |  |  | Use where liquidated damages bite hard or the schedule cannot move.
| P80 with K1 resolved pre-award | 3500 | person-days |  |  |  | Asking one clarification question before pricing is worth 216 PD.
| Change against the v3 figure of 3,608 PD | 106 |  |  |  |  | Moved because the unification saving is no longer 635 PD hardcoded. Computed from the modules it actually reduces, it is 524 PD — so the earlier figure over-claimed the saving and understated the effort.
DISTRIBUTION (rho = 0.5)
| Bucket midpoint (PD) | Iterations (count)
| 2092 | 5
| 2183 | 5
| 2274 | 48
| 2365 | 155
| 2456 | 350
| 2547 | 786
| 2638 | 1501
| 2729 | 2590
| 2820 | 3921
| 2911 | 5495
| 3002 | 7225
| 3093 | 8474
| 3184 | 9563
| 3274 | 10350
| 3365 | 10296
| 3456 | 9685
| 3547 | 8343
| 3638 | 6899
| 3729 | 5328
| 3820 | 3591
| 3911 | 2417
| 4002 | 1486
| 4093 | 809
| 4184 | 408
| 4275 | 186
| 4366 | 55
| 4457 | 22
| 4548 | 7

## Scenario C Model
Scenario C — Phase 1 Release, Modelled
Replaces the 0.62x multiplier. Each build module is tagged to a phase; QA and programme management scale with the phase-1 build share.
Ref | Module | Expected (PD) | Phase | In phase 1 (PD) | Rationale where deferred
A1 | Requirements elaboration, SRS and traceability matrix | 33 | Phase 1 | 33
A2 | Solution architecture, domain model, integration contracts | 29 | Phase 1 | 29
B1 | Design system and accessible mobile UI kit | 27 | Phase 1 | 27
B2 | Mobile screen design, ~55 screens, two platforms | 37 | Phase 2 | 0 | Mobile design deferred with the app.
B3 | Admin console design, ~40 screens, four roles | 29 | Phase 1 | 29
C1 | App foundation, navigation, state, mobile CI/CD | 35 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C2 | Registration, OTP, biometric, MFA, institutional onboarding | 31 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C3 | IPRS/IMPRS catalogue, lot detail, CoA / LVS / SDS viewer | 41 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C4 | Publications and subscriptions, edition history, renewals | 23 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C5 | Smart search, filters, predictive, voice, recommendations | 31 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C6 | Cart, checkout and order lifecycle | 46 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C7 | Payment: gateway SDK, UPI, cards, netbanking, PO approval | 31 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C8 | Notifications: push, SMS, email, preference centre | 19 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C9 | Feedback, support ticketing, FAQ, self-help | 21 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C10 | Accessibility engineering to WCAG 2.1 AA, both platforms | 26 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C11 | GIGW 3.0 mobile conformance and CERT-In cyber chapter | 21 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C12 | App hardening: pinning, root detection, obfuscation, cache | 21 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
C13 | Store submission, release engineering, phased rollout | 13 | Phase 2 | 0 | Mobile app deferred; the portal carries commerce in phase 1.
D1 | Console foundation, four-role RBAC, audit instrumentation | 35 | Phase 1 | 35
D2 | IPRS Admin: lots, batches, expiry, stock signals | 33 | Phase 1 | 33
D3 | CoA and Lot Validity Statement generation engine | 25 | Phase 1 | 25
D4 | Price-tier engine and government-organisation assignment | 25 | Phase 1 | 25
D5 | Verification workflow: document review, approval, revalidation | 27 | Phase 1 | 27
D6 | Dispatch Admin: scheduling, couriers, slips, tracking | 41 | Phase 1 | 41
D7 | Order management console, refunds, cancellations | 26 | Phase 1 | 26
D8 | User management and registration logs | 16 | Phase 1 | 16
D9 | Notification console: templates, scheduling, delivery reports | 21 | Phase 1 | 21
D10 | Feedback and ticket management, escalation | 21 | Phase 1 | 21
D11 | Search analytics and demand reporting | 23 | Phase 1 | 23
D12 | Reporting engine, role-scoped, PDF/Excel, scheduling | 36 | Phase 1 | 36
D13 | Immutable audit log: append-only, hash-chained, exportable | 26 | Phase 1 | 26
E1 | API platform: catalogue, lot, order, identity services | 72 | Phase 1 | 72
E2 | Document generation: CoA, LVS, GST invoice, dispatch slip | 31 | Phase 1 | 31
E3 | Payment gateway and settlement reconciliation | 13 | Phase 1 | 13
E4 | Courier API integration and tracking webhooks | 16 | Phase 1 | 16
E5 | Tally / ERP posting, reconciliation, GST e-invoicing (IRN) | 21 | Phase 1 | 21
E6 | Pin-code serviceability API | 5 | Phase 1 | 5
E7 | SMS and email integration incl. TRAI DLT registration | 13 | Phase 1 | 13
E8 | IP Online federation and SSO | 26 | Phase 1 | 26
E9 | LIMS / QC ingest to source Certificate of Analysis data | 25 | Phase 1 | 25
E10 | Five-lot history backfill and lot data structuring | 15 | Phase 1 | 15
E11 | Infrastructure, IaC, environments, CI/CD, observability, DR | 46 | Phase 1 | 46
E12 | Security engineering, CERT-In audit support, VAPT | 31 | Phase 1 | 31
H1 | Discovery, workshops, information architecture, sitemap | 29 | Phase 1 | 29
H2 | Content audit and migration plan | 14 | Phase 1 | 14
I1 | GIGW 3.0 / DBIM design system, bilingual type and grid | 31 | Phase 1 | 31
I2 | Template design, ~28 page templates | 43 | Phase 1 | 43
I3 | Commerce and account journey design | 17 | Phase 1 | 17
J1 | CMS platform setup, hardening, environments | 25 | Phase 1 | 25
J2 | RBAC and editorial approval workflow | 21 | Phase 1 | 21
J3 | Bilingual WYSIWYG authoring, spellcheck, media embed | 13 | Phase 1 | 13
J4 | Scheduling, auto-publish, auto-expire, expiry alerts | 11 | Phase 1 | 11
J5 | Backup, versioning, rollback, version compare | 13 | Phase 1 | 13
J6 | Immutable CMS audit trail and exportable logs | 19 | Phase 1 | 19
J7 | Archival engine: rules, retention, archive section, labelling | 21 | Phase 1 | 21
K1 | Video platform integration, player, captions, transcripts | 29 | Phase 1 | 29
K2 | Image wizard: gallery, resize, alt text, bulk upload | 17 | Phase 1 | 17
K3 | Document management: versioning, indexing, secure download | 25 | Phase 1 | 25
K4 | Event calendar, registration, reminders, archive | 31 | Phase 1 | 31
K5 | FAQ and glossary modules | 19 | Phase 1 | 19
K6 | Polls and visitor survey with analytics | 17 | Phase 2 | 0 | Community features deferred.
K7 | Public forum: threads, moderation, reputation, redressal | 46 | Phase 2 | 0 | Community features deferred.
K8 | Recruitment form, tracking, export, HR dashboard | 25 | Phase 1 | 25
L1 | Templates, mega menu, breadcrumbs, sticky nav, cards | 51 | Phase 1 | 51
L2 | Personalisation widgets, quick tiles, one-click downloads | 19 | Phase 2 | 0 | Personalisation deferred.
L3 | Bilingual framework and language toggle | 16 | Phase 1 | 16
L4 | Accessibility engineering to WCAG 2.1 AA | 39 | Phase 1 | 39
M1 | Search platform, indexing, multilingual facets, relevance | 33 | Phase 1 | 33
M2 | Semantic / vector search and recommendations | 29 | Phase 2 | 0 | AI layer deferred; keyword and facet search ship first.
M3 | Voice search and text-to-speech / speech-to-text | 21 | Phase 2 | 0 | AI layer deferred; keyword and facet search ship first.
M4 | Chatbot assistant: retrieval, guardrails, escalation | 47 | Phase 2 | 0 | AI layer deferred; keyword and facet search ship first.
M5 | AI auto-tagging and document classification | 25 | Phase 2 | 0 | AI layer deferred; keyword and facet search ship first.
M6 | AI moderation: spam, misuse, fraud detection | 19 | Phase 2 | 0 | AI layer deferred; keyword and facet search ship first.
M7 | AI governance: evaluation harness, accuracy testing, HITL | 19 | Phase 2 | 0 | AI layer deferred; keyword and facet search ship first.
N1 | Catalogue, categories, filters, bulk upload, versioning | 31 | Phase 1 | 31
N2 | Catalogue data onboarding: 1,341 SKUs, lots, two price tiers | 26 | Phase 1 | 26
N3 | Cart, checkout, address, shipping, tax, persistence, reorder | 36 | Phase 1 | 36
N4 | Payment gateway, multi-currency, retries, reconciliation | 21 | Phase 1 | 21
N5 | Order management, notifications, refunds, reports | 31 | Phase 1 | 31
N6 | Customer accounts, history, invoices, subscriptions, tracking | 26 | Phase 1 | 26
N7 | Promotions, discount codes, scheduling, banners | 19 | Phase 1 | 19
N8 | Sales analytics, funnels, dashboards | 23 | Phase 1 | 23
N9 | OpenCart data migration: products, customers, order history | 36 | Phase 1 | 36
O1 | Visitor analytics, event and journey tracking | 21 | Phase 1 | 21
O2 | Heatmaps, funnel and behavioural analytics | 17 | Phase 1 | 17
O3 | MIS dashboard: widgets, drill-down, scheduled reports | 36 | Phase 1 | 36
O4 | DPDP consent management and Consent Manager integration | 29 | Phase 1 | 29
O5 | Transactional and promotional SMS/email, bilingual, analytics | 31 | Phase 1 | 31
O6 | IP Online / PvPI integration and SSO across IPC portals | 36 | Phase 1 | 36
P1 | Migration tooling and mapping, Joomla to target | 25 | Phase 1 | 25
P2 | Article and document migration, ~1,500 items, plus QA | 36 | Phase 1 | 36
P3 | Hindi coverage completion and bilingual QA | 16 | Phase 1 | 16
P4 | URL redirect mapping and SEO preservation | 13 | Phase 1 | 13
Q1 | NIC / MeitY hosting provisioning, IaC, environments | 31 | Phase 1 | 31
Q2 | DR site, replication, failover, drill runbooks | 27 | Phase 1 | 27
Q3 | Monitoring, IDPS, alerting, SOC handover | 19 | Phase 1 | 19
Q4 | Security engineering and two VAPT cycles | 31 | Phase 1 | 31
Q5 | GIGW 3.0 conformance and STQC CQW certification support | 29 | Phase 1 | 29
| Build subtotal | 2613 |  | 1975
| Phase 1 share of build | 75.58%
| QA workstreams F and R | 477
| Programme workstreams G and S | 404
| Scaled QA and programme | 666
| SCENARIO C TOTAL (P50 basis) | 2641
Previously this row was Scenario B multiplied by 0.62. It is now the sum of the modules that actually ship first.

## Scenario D Model
Scenario D — Replatform, Modelled
Replaces the 0.58x multiplier. Every module carries a disposition factor: what fraction survives if the live Joomla and OpenCart estate is upgraded rather than replaced.
Ref | Module | Expected (PD) | Factor (0–1, dimensionless) | Retained (PD) | Why the factor is not 1.00
A1 | Requirements elaboration, SRS and traceability matrix | 33 | 1 | 33
A2 | Solution architecture, domain model, integration contracts | 29 | 1 | 29
B1 | Design system and accessible mobile UI kit | 27 | 1 | 27
B2 | Mobile screen design, ~55 screens, two platforms | 37 | 1 | 37
B3 | Admin console design, ~40 screens, four roles | 29 | 1 | 29
C1 | App foundation, navigation, state, mobile CI/CD | 35 | 1 | 35
C2 | Registration, OTP, biometric, MFA, institutional onboarding | 31 | 1 | 31
C3 | IPRS/IMPRS catalogue, lot detail, CoA / LVS / SDS viewer | 41 | 1 | 41
C4 | Publications and subscriptions, edition history, renewals | 23 | 1 | 23
C5 | Smart search, filters, predictive, voice, recommendations | 31 | 1 | 31
C6 | Cart, checkout and order lifecycle | 46 | 1 | 46
C7 | Payment: gateway SDK, UPI, cards, netbanking, PO approval | 31 | 1 | 31
C8 | Notifications: push, SMS, email, preference centre | 19 | 1 | 19
C9 | Feedback, support ticketing, FAQ, self-help | 21 | 1 | 21
C10 | Accessibility engineering to WCAG 2.1 AA, both platforms | 26 | 1 | 26
C11 | GIGW 3.0 mobile conformance and CERT-In cyber chapter | 21 | 1 | 21
C12 | App hardening: pinning, root detection, obfuscation, cache | 21 | 1 | 21
C13 | Store submission, release engineering, phased rollout | 13 | 1 | 13
D1 | Console foundation, four-role RBAC, audit instrumentation | 35 | 1 | 35
D2 | IPRS Admin: lots, batches, expiry, stock signals | 33 | 1 | 33
D3 | CoA and Lot Validity Statement generation engine | 25 | 1 | 25
D4 | Price-tier engine and government-organisation assignment | 25 | 1 | 25
D5 | Verification workflow: document review, approval, revalidation | 27 | 1 | 27
D6 | Dispatch Admin: scheduling, couriers, slips, tracking | 41 | 1 | 41
D7 | Order management console, refunds, cancellations | 26 | 1 | 26
D8 | User management and registration logs | 16 | 1 | 16
D9 | Notification console: templates, scheduling, delivery reports | 21 | 1 | 21
D10 | Feedback and ticket management, escalation | 21 | 1 | 21
D11 | Search analytics and demand reporting | 23 | 1 | 23
D12 | Reporting engine, role-scoped, PDF/Excel, scheduling | 36 | 1 | 36
D13 | Immutable audit log: append-only, hash-chained, exportable | 26 | 1 | 26
E1 | API platform: catalogue, lot, order, identity services | 72 | 1 | 72
E2 | Document generation: CoA, LVS, GST invoice, dispatch slip | 31 | 1 | 31
E3 | Payment gateway and settlement reconciliation | 13 | 1 | 13
E4 | Courier API integration and tracking webhooks | 16 | 1 | 16
E5 | Tally / ERP posting, reconciliation, GST e-invoicing (IRN) | 21 | 1 | 21
E6 | Pin-code serviceability API | 5 | 1 | 5
E7 | SMS and email integration incl. TRAI DLT registration | 13 | 1 | 13
E8 | IP Online federation and SSO | 26 | 1 | 26
E9 | LIMS / QC ingest to source Certificate of Analysis data | 25 | 1 | 25
E10 | Five-lot history backfill and lot data structuring | 15 | 1 | 15
E11 | Infrastructure, IaC, environments, CI/CD, observability, DR | 46 | 1 | 46
E12 | Security engineering, CERT-In audit support, VAPT | 31 | 1 | 31
H1 | Discovery, workshops, information architecture, sitemap | 29 | 1 | 29
H2 | Content audit and migration plan | 14 | 0.5 | 7 | Existing platform covers part of this.
I1 | GIGW 3.0 / DBIM design system, bilingual type and grid | 31 | 1 | 31
I2 | Template design, ~28 page templates | 43 | 1 | 43 | Full redesign is the point of the exercise and survives intact.
I3 | Commerce and account journey design | 17 | 1 | 17
J1 | CMS platform setup, hardening, environments | 25 | 0.45 | 11 | Joomla is upgraded in place rather than replaced by a new CMS.
J2 | RBAC and editorial approval workflow | 21 | 0.7 | 15 | Existing platform covers part of this.
J3 | Bilingual WYSIWYG authoring, spellcheck, media embed | 13 | 0.7 | 9 | Existing platform covers part of this.
J4 | Scheduling, auto-publish, auto-expire, expiry alerts | 11 | 0.7 | 8 | Existing platform covers part of this.
J5 | Backup, versioning, rollback, version compare | 13 | 0.7 | 9 | Existing platform covers part of this.
J6 | Immutable CMS audit trail and exportable logs | 19 | 0.85 | 16 | Existing platform covers part of this.
J7 | Archival engine: rules, retention, archive section, labelling | 21 | 0.7 | 15 | Existing platform covers part of this.
K1 | Video platform integration, player, captions, transcripts | 29 | 1 | 29
K2 | Image wizard: gallery, resize, alt text, bulk upload | 17 | 0.6 | 10 | Existing platform covers part of this.
K3 | Document management: versioning, indexing, secure download | 25 | 0.75 | 19 | Existing platform covers part of this.
K4 | Event calendar, registration, reminders, archive | 31 | 1 | 31
K5 | FAQ and glossary modules | 19 | 0.6 | 11 | Existing platform covers part of this.
K6 | Polls and visitor survey with analytics | 17 | 1 | 17
K7 | Public forum: threads, moderation, reputation, redressal | 46 | 1 | 46
K8 | Recruitment form, tracking, export, HR dashboard | 25 | 0.55 | 14 | Existing platform covers part of this.
L1 | Templates, mega menu, breadcrumbs, sticky nav, cards | 51 | 0.85 | 43 | Existing platform covers part of this.
L2 | Personalisation widgets, quick tiles, one-click downloads | 19 | 1 | 19
L3 | Bilingual framework and language toggle | 16 | 1 | 16
L4 | Accessibility engineering to WCAG 2.1 AA | 39 | 1 | 39
M1 | Search platform, indexing, multilingual facets, relevance | 33 | 1 | 33
M2 | Semantic / vector search and recommendations | 29 | 1 | 29
M3 | Voice search and text-to-speech / speech-to-text | 21 | 1 | 21
M4 | Chatbot assistant: retrieval, guardrails, escalation | 47 | 1 | 47
M5 | AI auto-tagging and document classification | 25 | 1 | 25
M6 | AI moderation: spam, misuse, fraud detection | 19 | 1 | 19
M7 | AI governance: evaluation harness, accuracy testing, HITL | 19 | 1 | 19
N1 | Catalogue, categories, filters, bulk upload, versioning | 31 | 0.35 | 11 | OpenCart already holds the catalogue; this becomes remodelling, not building.
N2 | Catalogue data onboarding: 1,341 SKUs, lots, two price tiers | 26 | 1 | 26
N3 | Cart, checkout, address, shipping, tax, persistence, reorder | 36 | 0.3 | 11 | Cart and checkout exist and work today.
N4 | Payment gateway, multi-currency, retries, reconciliation | 21 | 0.35 | 7 | Payment integration is live.
N5 | Order management, notifications, refunds, reports | 31 | 0.4 | 12 | Order management exists.
N6 | Customer accounts, history, invoices, subscriptions, tracking | 26 | 0.35 | 9 | Customer accounts exist.
N7 | Promotions, discount codes, scheduling, banners | 19 | 0.3 | 6 | Existing platform covers part of this.
N8 | Sales analytics, funnels, dashboards | 23 | 0.6 | 14 | Existing platform covers part of this.
N9 | OpenCart data migration: products, customers, order history | 36 | 0.15 | 5 | No migration needed if the engine is retained.
O1 | Visitor analytics, event and journey tracking | 21 | 0.7 | 15 | Existing platform covers part of this.
O2 | Heatmaps, funnel and behavioural analytics | 17 | 0.8 | 14 | Existing platform covers part of this.
O3 | MIS dashboard: widgets, drill-down, scheduled reports | 36 | 1 | 36
O4 | DPDP consent management and Consent Manager integration | 29 | 1 | 29
O5 | Transactional and promotional SMS/email, bilingual, analytics | 31 | 1 | 31
O6 | IP Online / PvPI integration and SSO across IPC portals | 36 | 1 | 36
P1 | Migration tooling and mapping, Joomla to target | 25 | 0.25 | 6 | No CMS change, so no cross-platform migration tooling.
P2 | Article and document migration, ~1,500 items, plus QA | 36 | 0.2 | 7 | Content stays in place.
P3 | Hindi coverage completion and bilingual QA | 16 | 0.6 | 10 | Existing platform covers part of this.
P4 | URL redirect mapping and SEO preservation | 13 | 0.2 | 3 | URLs are largely unchanged, so redirect mapping collapses.
Q1 | NIC / MeitY hosting provisioning, IaC, environments | 31 | 1 | 31
Q2 | DR site, replication, failover, drill runbooks | 27 | 1 | 27
Q3 | Monitoring, IDPS, alerting, SOC handover | 19 | 1 | 19
Q4 | Security engineering and two VAPT cycles | 31 | 1 | 31
Q5 | GIGW 3.0 conformance and STQC CQW certification support | 29 | 1 | 29
| Build subtotal | 2613 |  | 2305
| Retained share of build | 88.21%
| QA and programme, scaled | 777
| SCENARIO D TOTAL (P50 basis) | 3082
| Caveat | Modelled, but not validated. Nobody has opened the OpenCart installation to check its version, customisation depth or upgrade path, and a heavily forked instance can cost more to upgrade than to replace. This scenario is now defensible enough to discuss; it is not yet defensible enough to bid.

## Scenario E Model
Scenario E — IPC Adopts the Product
The scenario the workbook never had. Each IPC module carries a factor: what fraction survives once Lotmark supplies the core.
Ref | IPC module | Expected (PD) | Factor (0–1, dimensionless) | Surviving (PD) | What the product displaces
A1 | Requirements elaboration, SRS and traceability matrix | 33 | 1 | 33
A2 | Solution architecture, domain model, integration contracts | 29 | 1 | 29
B1 | Design system and accessible mobile UI kit | 27 | 1 | 27
B2 | Mobile screen design, ~55 screens, two platforms | 37 | 1 | 37
B3 | Admin console design, ~40 screens, four roles | 29 | 1 | 29
C1 | App foundation, navigation, state, mobile CI/CD | 35 | 1 | 35
C2 | Registration, OTP, biometric, MFA, institutional onboarding | 31 | 1 | 31
C3 | IPRS/IMPRS catalogue, lot detail, CoA / LVS / SDS viewer | 41 | 0.3 | 12 | Partly supplied by the product.
C4 | Publications and subscriptions, edition history, renewals | 23 | 0.3 | 7 | Partly supplied by the product.
C5 | Smart search, filters, predictive, voice, recommendations | 31 | 1 | 31
C6 | Cart, checkout and order lifecycle | 46 | 1 | 46
C7 | Payment: gateway SDK, UPI, cards, netbanking, PO approval | 31 | 1 | 31
C8 | Notifications: push, SMS, email, preference centre | 19 | 1 | 19
C9 | Feedback, support ticketing, FAQ, self-help | 21 | 1 | 21
C10 | Accessibility engineering to WCAG 2.1 AA, both platforms | 26 | 1 | 26
C11 | GIGW 3.0 mobile conformance and CERT-In cyber chapter | 21 | 1 | 21
C12 | App hardening: pinning, root detection, obfuscation, cache | 21 | 1 | 21
C13 | Store submission, release engineering, phased rollout | 13 | 1 | 13
D1 | Console foundation, four-role RBAC, audit instrumentation | 35 | 0.3 | 11 | Partly supplied by the product.
D2 | IPRS Admin: lots, batches, expiry, stock signals | 33 | 0.12 | 4 | Lot register is core product.
D3 | CoA and Lot Validity Statement generation engine | 25 | 0.1 | 3 | Certificate engine is core product.
D4 | Price-tier engine and government-organisation assignment | 25 | 0.15 | 4 | Price-tier engine is core product.
D5 | Verification workflow: document review, approval, revalidation | 27 | 0.15 | 4 | Verification workflow is core product.
D6 | Dispatch Admin: scheduling, couriers, slips, tracking | 41 | 0.15 | 6 | Dispatch and cold chain are core product.
D7 | Order management console, refunds, cancellations | 26 | 0.12 | 3 | Partly supplied by the product.
D8 | User management and registration logs | 16 | 0.3 | 5 | Partly supplied by the product.
D9 | Notification console: templates, scheduling, delivery reports | 21 | 0.3 | 6 | Partly supplied by the product.
D10 | Feedback and ticket management, escalation | 21 | 0.35 | 7 | Partly supplied by the product.
D11 | Search analytics and demand reporting | 23 | 0.2 | 5 | Partly supplied by the product.
D12 | Reporting engine, role-scoped, PDF/Excel, scheduling | 36 | 0.2 | 7 | Partly supplied by the product.
D13 | Immutable audit log: append-only, hash-chained, exportable | 26 | 0.08 | 2 | Audit ledger is core product.
E1 | API platform: catalogue, lot, order, identity services | 72 | 0.35 | 25 | Product supplies the API platform; tenant integrations remain.
E2 | Document generation: CoA, LVS, GST invoice, dispatch slip | 31 | 0.12 | 4 | Partly supplied by the product.
E3 | Payment gateway and settlement reconciliation | 13 | 0.3 | 4 | Partly supplied by the product.
E4 | Courier API integration and tracking webhooks | 16 | 0.3 | 5 | Partly supplied by the product.
E5 | Tally / ERP posting, reconciliation, GST e-invoicing (IRN) | 21 | 0.45 | 9 | Partly supplied by the product.
E6 | Pin-code serviceability API | 5 | 1 | 5
E7 | SMS and email integration incl. TRAI DLT registration | 13 | 0.35 | 5 | Partly supplied by the product.
E8 | IP Online federation and SSO | 26 | 1 | 26
E9 | LIMS / QC ingest to source Certificate of Analysis data | 25 | 0.2 | 5 | Product ships a manual QC entry path.
E10 | Five-lot history backfill and lot data structuring | 15 | 0.15 | 2 | Partly supplied by the product.
E11 | Infrastructure, IaC, environments, CI/CD, observability, DR | 46 | 1 | 46
E12 | Security engineering, CERT-In audit support, VAPT | 31 | 1 | 31
H1 | Discovery, workshops, information architecture, sitemap | 29 | 1 | 29
H2 | Content audit and migration plan | 14 | 1 | 14
I1 | GIGW 3.0 / DBIM design system, bilingual type and grid | 31 | 1 | 31
I2 | Template design, ~28 page templates | 43 | 1 | 43
I3 | Commerce and account journey design | 17 | 1 | 17
J1 | CMS platform setup, hardening, environments | 25 | 1 | 25
J2 | RBAC and editorial approval workflow | 21 | 1 | 21
J3 | Bilingual WYSIWYG authoring, spellcheck, media embed | 13 | 1 | 13
J4 | Scheduling, auto-publish, auto-expire, expiry alerts | 11 | 1 | 11
J5 | Backup, versioning, rollback, version compare | 13 | 1 | 13
J6 | Immutable CMS audit trail and exportable logs | 19 | 1 | 19
J7 | Archival engine: rules, retention, archive section, labelling | 21 | 1 | 21
K1 | Video platform integration, player, captions, transcripts | 29 | 1 | 29
K2 | Image wizard: gallery, resize, alt text, bulk upload | 17 | 1 | 17
K3 | Document management: versioning, indexing, secure download | 25 | 1 | 25
K4 | Event calendar, registration, reminders, archive | 31 | 1 | 31
K5 | FAQ and glossary modules | 19 | 1 | 19
K6 | Polls and visitor survey with analytics | 17 | 1 | 17
K7 | Public forum: threads, moderation, reputation, redressal | 46 | 1 | 46
K8 | Recruitment form, tracking, export, HR dashboard | 25 | 1 | 25
L1 | Templates, mega menu, breadcrumbs, sticky nav, cards | 51 | 1 | 51
L2 | Personalisation widgets, quick tiles, one-click downloads | 19 | 1 | 19
L3 | Bilingual framework and language toggle | 16 | 1 | 16
L4 | Accessibility engineering to WCAG 2.1 AA | 39 | 1 | 39
M1 | Search platform, indexing, multilingual facets, relevance | 33 | 1 | 33
M2 | Semantic / vector search and recommendations | 29 | 1 | 29
M3 | Voice search and text-to-speech / speech-to-text | 21 | 1 | 21
M4 | Chatbot assistant: retrieval, guardrails, escalation | 47 | 1 | 47
M5 | AI auto-tagging and document classification | 25 | 1 | 25
M6 | AI moderation: spam, misuse, fraud detection | 19 | 1 | 19
M7 | AI governance: evaluation harness, accuracy testing, HITL | 19 | 1 | 19
N1 | Catalogue, categories, filters, bulk upload, versioning | 31 | 0.15 | 5 | Catalogue is core product.
N2 | Catalogue data onboarding: 1,341 SKUs, lots, two price tiers | 26 | 0.55 | 14 | Data still has to be onboarded, but into a product schema rather than a new build.
N3 | Cart, checkout, address, shipping, tax, persistence, reorder | 36 | 0.15 | 5 | Cart and checkout are core product.
N4 | Payment gateway, multi-currency, retries, reconciliation | 21 | 0.2 | 4 | Partly supplied by the product.
N5 | Order management, notifications, refunds, reports | 31 | 0.15 | 5 | Order management is core product.
N6 | Customer accounts, history, invoices, subscriptions, tracking | 26 | 0.15 | 4 | Partly supplied by the product.
N7 | Promotions, discount codes, scheduling, banners | 19 | 0.2 | 4 | Partly supplied by the product.
N8 | Sales analytics, funnels, dashboards | 23 | 0.25 | 6 | Partly supplied by the product.
N9 | OpenCart data migration: products, customers, order history | 36 | 0.6 | 22 | OpenCart migration still required, into the product.
O1 | Visitor analytics, event and journey tracking | 21 | 1 | 21
O2 | Heatmaps, funnel and behavioural analytics | 17 | 1 | 17
O3 | MIS dashboard: widgets, drill-down, scheduled reports | 36 | 0.4 | 14 | Partly supplied by the product.
O4 | DPDP consent management and Consent Manager integration | 29 | 1 | 29
O5 | Transactional and promotional SMS/email, bilingual, analytics | 31 | 1 | 31
O6 | IP Online / PvPI integration and SSO across IPC portals | 36 | 1 | 36
P1 | Migration tooling and mapping, Joomla to target | 25 | 1 | 25
P2 | Article and document migration, ~1,500 items, plus QA | 36 | 1 | 36
P3 | Hindi coverage completion and bilingual QA | 16 | 1 | 16
P4 | URL redirect mapping and SEO preservation | 13 | 1 | 13
Q1 | NIC / MeitY hosting provisioning, IaC, environments | 31 | 1 | 31
Q2 | DR site, replication, failover, drill runbooks | 27 | 1 | 27
Q3 | Monitoring, IDPS, alerting, SOC handover | 19 | 0.45 | 9 | Product carries monitoring; NIC-specific work remains.
Q4 | Security engineering and two VAPT cycles | 31 | 1 | 31
Q5 | GIGW 3.0 conformance and STQC CQW certification support | 29 | 1 | 29
| Build subtotal | 2613 |  | 1921
| Surviving share of build | 73.52%
| QA and programme, scaled | 648
| SCENARIO E EFFORT (P50 basis) | 2569
| PLUS: product licence, per year | 60 | INR lakh / yr |  | Priced against the producer-platform model: IPC is a large tenant at 1,341 SKUs.
| Licence over five years | 3 | INR crore
| What IPC still pays for regardless of route | The portal and CMS, bilingual content, GIGW and STQC certification, content and OpenCart data migration, NIC hosting and DR, the AI layer, the mobile app shell, and PvPI integration. None of that is product scope, which is exactly why the core-versus-commodity boundary matters commercially and not just architecturally.
ADOPT VERSUS BUILD — the decision
| Scenario B — bespoke unified build | 5.6193 | INR crore
| Scenario E — build portion | 4.2167 | INR crore
| Scenario E — licence over five years | 3 | INR crore
| Scenario E — all in over five years | 7.2167 | INR crore
| BREAK-EVEN LICENCE | 28.1 | INR lakh / yr |  | Above this annual licence, IPC is cheaper commissioning a bespoke build. Below it, adopting wins.
| Reading it honestly | Adopting the product removes only about a quarter of IPC's build, because most of what IPC needs — the portal and CMS, bilingual content, migration, GIGW and STQC certification, NIC hosting, the AI layer and the mobile shell — was never product scope. At the sixty lakh a year assumed above, adoption costs MORE over five years than a bespoke build. The product has to price under the break-even for IPC to prefer it, and that figure is below the base annual contract value used in the market model — so either the market model prices too high, or IPC is not the customer the product is priced for.

## Independent Estimate
Second Method — COCOMO II Post-Architecture
Genuinely independent of the module breakdown. Size comes from counted artefacts; every coefficient is Boehm's published calibration, not a rate chosen to agree.
WHY THIS REPLACES THE TRIANGULATION SHEET
| The problem | The previous sheet used a per-obligation rate and a per-screen rate that were within 3% and 10% of the values needed to reproduce the bottom-up answer. They were calibrated to agree, so the convergence corroborated nothing. It has been deleted rather than patched.
| The replacement | Function-point sizing from counted artefacts, backfired to source lines, then Boehm's COCOMO II effort equation. Nothing in this chain reads the module estimates, so it is free to disagree — and it does.
STEP 1 — FUNCTION POINT COUNT
| Component | Count (items) | FP weight (dimensionless) | Points (unadjusted FP)
| Internal logical files (data entities) | 30 | 12 | 360
| External interface files (integrations) | 13 | 7 | 91
| External inputs (forms and actions) | 55 | 4 | 220
| External outputs (documents, reports, dashboards) | 35 | 5 | 175
| External inquiries (searches and lookups) | 25 | 4 | 100
| Unadjusted function points |  |  | 946
| Value adjustment factor |  |  | 1.19 | 0.65 + 0.01 x 54 across the 14 general system characteristics.
| Adjusted function points |  |  | 1126
| Source lines per function point |  |  | 46 | Typical backfire ratio for a modern web and services stack.
| Size (KSLOC) |  |  | 51.8
STEP 2 — COCOMO II PARAMETERS
| Scale factors | Rating | Value
| PREC precedentedness | Nominal | 3.72
| FLEX development flexibility | Low | 4.05
| RESL risk resolution | Low | 5.65
| TEAM cohesion | Nominal | 3.29
| PMAT process maturity | High | 3.12
| Sum of scale factors |  | 19.83
| Exponent E = 0.91 + 0.01 x SF |  | 1.1083
| Product of the 17 effort multipliers |  | 1.012 |  | RELY, DATA, CPLX, RUSE and DOCU raise it; ACAP, PCAP, PLEX, LTEX, TOOL and SITE lower it; PCON is Low because of the 16-month attrition exposure.
STEP 3 — RESULT
| Effort (person-months) = 2.94 x KSLOC^E x EM |  | 236
| Person-days per person-month |  | 19
| Software construction effort |  | 4484
| Plus inception and requirements at 7% |  | 314
| Plus non-code workstreams from the bottom-up |  | 284 |  | Content and catalogue migration, hosting, certification and training. COCOMO sizes code, not these.
| COCOMO II LIKE-FOR-LIKE TOTAL |  | 5082
| Bottom-up P50 (simulation) |  | 3426
| Divergence |  | 48.34% |  | A real second opinion is allowed to disagree. Read the note below before deciding which to trust.
| How to read the gap | If COCOMO reads high, the likely causes are that the backfire ratio overstates a configuration-heavy build (much of this system is CMS and commerce configuration, not bespoke code) and that the function-point count treats configured features as if they were written from scratch. If COCOMO reads low, the bottom-up is probably carrying coordination and governance overhead that the parametric model prices more cheaply. Either way the two should be reconciled explicitly before a bid, and the honest position is that a single-method estimate was never safe.
RECONCILIATION — what would make the two methods agree?
| Backfire ratio at which COCOMO equals the bottom-up |  | 31.4 |  | Against the 46 used above. The whole 48% divergence rests on this one input.
| Backfire ratio (SLOC per FP) | COCOMO total (PD) | vs bottom-up (%) |  | Reading
| 25 | 2728 | -20.37% |  | Very high reuse; mostly configuration.
| 31 | 3386 | -1.163% |  | Configuration-heavy CMS and commerce build. Reconciles the two methods.
| 35 | 3833 | 11.87% |  | Mixed configuration and bespoke.
| 40 | 4399 | 28.39% |  | Mostly bespoke, modern framework.
| 46 | 5088 | 48.52% |  | Used above. Assumes largely bespoke code.
| 55 | 6140 | 79.23% |  | Bespoke, lower-level language.
| Verdict | The two methods are not really 48% apart on effort — they are apart on one assumption about how much of this system is written versus configured. At 31 source lines per function point they agree exactly, and 31 is a defensible ratio for a build that is largely CMS and commerce configuration. At 46, which assumes bespoke code throughout, COCOMO reads 5,086 PD. The bottom-up implicitly assumes the configuration-heavy world. That assumption should be stated in the bid and tested at architecture, because if the build turns out to be more bespoke than assumed, the parametric model says the exposure is roughly 1,600 person-days.

## Unification Savings
Unified Platform vs Two Independent Builds
Each saving is now a percentage of the specific modules it reduces, computed live. The guard column flags any saving that exceeds its own source.
Ref | Duplicated capability | Source modules | Source (PD) | Reduction (%) | Saving (PD) | Guard | Rationale
U1 | Single identity provider and SSO | E8, O6 | 62 | 42% | 26 | ok | One IdP serves app, console and portal.
U2 | One catalogue and commerce core, two front ends | C4, N1, N3, N4, N5, N6 | 168 | 62% | 104 | ok | Both documents sell the same publications.
U3 | Single payment integration | E3, N4 | 34 | 55% | 19 | ok | One merchant account, one PCI scope.
U4 | Shared notification and communication service | E7, D9, O5 | 65 | 52% | 34 | ok | One template store, one DLT registration.
U5 | Shared immutable audit-log subsystem | D13, J6 | 45 | 55% | 25 | ok | Required by both; build once.
U6 | Shared analytics and MIS layer | D11, D12, O1, O2, O3 | 133 | 35% | 47 | ok | One MIS with role-scoped views.
U7 | Shared infrastructure, DR and monitoring | E11, Q1, Q2, Q3 | 123 | 36% | 44 | ok | One hosting footprint, one DR site.
U8 | Shared design system and accessibility | B1, I1, C10, L4 | 123 | 25% | 31 | ok | One accessible library, certified once.
U9 | Single programme office | G1, G2, S1, S2 | 252 | 29% | 73 | ok | One PMO, one change board.
U10 | Single certification cycle | C11, E12, Q4, Q5 | 112 | 33% | 37 | ok | One CQW submission covering both surfaces.
U11 | Shared QA framework and automation | F1, F2, F3, R1, R2, R3 | 283 | 19% | 54 | ok | One automation framework and test-data factory.
U12 | Single data-migration pipeline | N2, N9, P1, P2 | 123 | 24% | 30 | ok | One extraction and load toolchain.
| TOTAL |  | 1523 |  | 524 | ok

## Risk Register (reclassified)
Risk Register — Endogenous vs Exogenous
Only exogenous risks enter the simulation. Endogenous ones are already carried by the module optimistic-to-pessimistic spread, and charging them again was double counting.
Ref | Risk | Class | Probability (0–1) | Marginal impact (PD) | EMV (PD) | Basis for the classification
K1 | Commerce scope not reconciled before award | Exogenous | 55% | 320 | 176 | A scope change, not estimation variance. No module range contemplates running two order ledgers.
K2 | No LIMS or QC source for CoA data | Exogenous | 70% | 35 | 24 | E9 sizes building the ingest. This is the marginal cost of a manual QC console if no source exists at all.
K3 | Content volume beyond the counted baseline | Exogenous | 35% | 30 | 10 | Reduced from 55: P1/P2 pessimistic already absorbs ordinary volume swing. Marginal only.
K4 | NIC / MeitY onboarding lead time | Exogenous | 60% | 55 | 33 | Schedule slip converts to extended PMO cost, which no module carries.
K5 | STQC or CERT-In findings needing a third cycle | Exogenous | 45% | 40 | 18 | Reduced from 60: Q4/Q5 already budget two cycles. Marginal is the third.
K6 | App store rejection cycles | Exogenous | 35% | 15 | 5 | Outside the build estimate entirely.
K7 | Hindi coverage incomplete at cutover | Exogenous | 40% | 15 | 6 | Reduced from 25: P3 range covers ordinary shortfall.
K8 | DPDP 13 May 2027 date missed, remediation needed | Exogenous | 50% | 40 | 20 | Statutory date, not an estimation question.
K11 | Cold-chain workflow required but unscoped | Exogenous | 45% | 22 | 10 | Pure scope addition; absent from every module.
K12 | Tier approval revalidation | Exogenous | 30% | 5 | 2 | Reduced from 10: D5 now explicitly covers revalidation.
K13 | OpenCart data migration harder than mapped | Exogenous | 65% | 25 | 16 | Reduced from 40: N9 range covers ordinary difficulty. Marginal only.
K14 | Attrition and re-ramp over 16 months | Exogenous | 80% | 150 | 120 | Modules estimate productive effort, not replacement and re-ramp. Genuinely outside.
K15 | Inherited release-hygiene remediation | Exogenous | 50% | 12 | 6 | Observed on the live estate.
K10 | Requirement volatility across 191 obligations | Endogenous | 75% | 180 | 0 | REMOVED FROM THE SIMULATION. This is precisely what the optimistic-to-pessimistic spread on every module encodes. Counting it again was double-counting worth 135 PD of expected value.
K9 | PCI scope escalates to full DSS | Exogenous | 15% | 0 | 0 | Cost-only exposure of INR 280 lakh; carried on the cost side, not in person-days.
| Expected value of exogenous risk |  |  |  | 447
| Note | This total is shown for reference only. It is NOT added to a percentile — the simulation samples these events inside each iteration, so their effect is already in every figure on the Monte Carlo sheet. v2's register totalled 621 PD; removing the double-counted volatility risk and reducing six others to their marginal exposure brings it to 447 PD.

## Sensitivity
Tornado — Derived by Simulation
Each variable was swung and the whole Monte Carlo re-run at 25,000 iterations. The figures below are the resulting shift in P80, not hand-entered constants.
Rank | Variable | P80 low case (PD) | P80 high case (PD) | Swing (PD) | What the swing means
1 | Requirement volatility (module spreads +/-30%) | 2891 | 4538 | 1646 | Acceptance criteria agreed in F0 move this to the low case.
2 | Unification savings realised vs not | 3716 | 4218 | 503 | The entire case for one platform instead of two.
3 | Commerce scope reconciled before award | 3499 | 3821 | 322 | The largest single lever, and it is answered by a question, not by engineering.
4 | AI layer scope (workstream M) | 3595 | 3821 | 226 | Seven AI features with no accuracy criteria. Fixing thresholds pre-award is worth more than any other AI decision.
5 | Content and catalogue migration (P, N2, N9) | 3652 | 3811 | 159 | Narrowed in v2 by counting the estate; still material.
6 | Mobile: cross-platform vs two native codebases | 3714 | 3849 | 135 | A single technology decision.
7 | Attrition and re-ramp | 3644 | 3741 | 97 | Longer schedules cost more than the day rate implies.
8 | Forum and engagement scope (K6, K7) | 3661 | 3740 | 79 | Deferrable to phase 2 with no impact on commerce.
9 | CoA source data / LIMS availability | 3692 | 3736 | 44 | If no QC source exists a manual console must be built.
10 | Certification remediation cycles | 3701 | 3733 | 32 | Two cycles are budgeted; this is the third.

## Team & Rate Card
Role Mix and Blended Rate
Offshore India delivery.
Ref | Role | Share of effort (%) | Rate (INR / person-day) | Weighted (INR/PD) | Note
R1 | Programme Director | 3% | 32000 | 960
R2 | Solution Architect | 5% | 26000 | 1300
R3 | Tech Lead | 8% | 20000 | 1600 | Two leads: platform and experience.
R4 | Business Analyst | 7% | 14000 | 980 | Owns the 191-obligation matrix.
R5 | UX / UI Designer | 7% | 15000 | 1050 | Includes accessibility specialist time.
R6 | Senior Engineer | 22% | 16000 | 3520
R7 | Engineer | 26% | 11000 | 2860
R8 | QA Lead | 4% | 15000 | 600
R9 | QA Engineer | 12% | 9500 | 1140
R10 | DevOps / SRE | 4% | 17000 | 680 | NIC/MeitY provisioning, DR automation.
R11 | Security Engineer | 2% | 22000 | 440 | GIGW, CQW and CERT-In readiness.
| Blended rate (mid-tier) | 100% |  | 15130
VENDOR TIER
Ref | Tier | Multiplier (x, dimensionless) | Effective rate (INR/PD) |  | Note
T1 | Boutique / specialist | 0.72 | 10894 |  | Lower rate, higher certification risk.
T2 | Mid-tier SI | 1 | 15130 |  | Baseline for all headline numbers.
T3 | Tier-1 SI | 1.4 | 21182 |  | Established NIC / STQC track record.

## Scenarios & Cost
Scenarios, Build Cost and Unit Economics
INR. Crore = 10,000,000.
Ref | Scenario | Effort (PD) | Boutique Cr | Mid-tier Cr | Tier-1 Cr | What it is
S-A | Two independent builds, as documented | 4220 | 4.5973 | 6.3849 | 8.9388 | MODELLED. The same simulation run with no unification saving realised — which is what two independent builds means. Previously this was a ratio taken from a superseded sheet, and restructuring the savings sheet silently broke it so that Scenario A read the same as Scenario B.
S-B | Unified platform, two front ends | 3714 | 4.046 | 5.6193 | 7.867 | RECOMMENDED. One catalogue, one identity, one audit ledger.
S-C | Unified, phase 1 release only | 2865 | 3.1211 | 4.3347 | 6.0686 | MODELLED. Sum of the modules that ship first, scaled from P50 to the P80 bid basis.
S-D | Replatform the existing estate, do not rebuild | 3343 | 3.6419 | 5.058 | 7.0811 | MODELLED. Module-level replatform disposition, scaled to P80. Not yet validated against the actual OpenCart install.
S-E | IPC adopts the product (Lotmark tenant) | 2787 | 3.0362 | 4.2167 | 5.9034 | NEW. Product supplies the core; IPC pays for configuration, migration, the portal layer, certification and hosting. Add the licence separately.
PASS-THROUGH AND THIRD-PARTY (INR lakh)
Ref | Item | Low (INR lakh) | Base (INR lakh) | High (INR lakh) | Type | Note
P1 | STQC Certified Quality Website certification | 8 | 12 | 18 | One-time | 88 mandatory GIGW guidelines assessed.
P2 | CERT-In empanelled security audit, 2 systems x 2 cycles | 12 | 18 | 28 | One-time
P3 | Hosting: NIC/MeitY primary plus DR (36 months) | 45 | 72 | 110 | Recurring | 99.9% SLA, RTO 4h, RPO 15min.
P4 | Video streaming platform (36 months) | 15 | 24 | 40 | Recurring | Required by Doc B; platform not named.
P5 | Payment gateway setup and annual | 3 | 6 | 10 | Recurring | Excludes TDR.
P6 | SMS / DLT and transactional email (36 months) | 8 | 14 | 24 | Recurring
P7 | AI inference, vector store, moderation (36 months) | 20 | 38 | 70 | Recurring | Seven AI features.
P8 | APM, logging, WAF, CDN (36 months) | 12 | 20 | 34 | Recurring | Needed to evidence the SLA.
P9 | Developer accounts, code signing, TLS | 1 | 2 | 4 | One-time | Store accounts must be owned by IPC.
P10 | Hindi coverage completion | 8 | 14 | 26 | One-time | REDUCED: a Hindi site already exists.
P11 | Third-party accessibility audit, two cycles | 5 | 8 | 14 | One-time
P12 | Load-test tooling and device farm | 4 | 7 | 12 | One-time
P13 | DPDP Consent Manager registration and integration | 4 | 8 | 15 | Recurring | NEW: Consent Manager registration opened 13 Nov 2026.
| Pass-through total | 145 | 243 | 405
| of which one-time |  | 61
| of which recurring over 36 months |  | 182
| Annual run-rate |  | 60.6667
FIVE-YEAR TCO — SCENARIO B, MID-TIER (INR crore)
| AMC as % of build per annum | 16% | L1-L3 support, patching, CERT-In advisories, minor enhancements.
Ref | Cost line | Year 0 (INR Cr) | Year 1 (INR Cr) | Year 2 (INR Cr) | Year 3 (INR Cr) | Years 4-5 (INR Cr)
T1 | Build effort | 5.6193
T2 | One-time pass-through | 0.61
T3 | Hosting, licences, AI run-rate |  | 0.60667 | 0.60667 | 0.60667 | 1.2133
T4 | AMC and application support |  | 0.89909 | 0.89909 | 0.89909 | 1.7982
| Total by period | 6.2293 | 1.5058 | 1.5058 | 1.5058 | 3.0115
| FIVE-YEAR TCO | 13.758
UNIT ECONOMICS — the number an evaluation committee computes first
| IPRS SKUs in catalogue | 702 | Counted from the published list, 24/06/2026.
| IMPRS SKUs in catalogue | 639 | Counted from the published list, 24/06/2026.
| Orders per year — BANDED, still unverified | 9000 | Replaced a single point guess with the band below. IPC can settle this from the existing OpenCart order table in minutes; until then, quote the range, never the point.
| Estimated monthly visitors — RETRACTED, UNVERIFIED | 0 | RETRACTED 18 Aug 2026. The earlier 88,000 was derived by dividing the gap between two visitor-counter readings (4,561,263 and 4,570,022) by three days — but those three days came from the pages' own Last-Modified dates, not from the read times. Both pages were fetched minutes apart, so the two readings cannot both be live and the inference is void. Cumulative average since about 2017 suggests nearer 42,000/month, which would make Doc B's 100,000 a growth allowance rather than current traffic — the opposite of what was claimed. REPLACE with IPC's analytics export or server logs before using any traffic-derived argument.
| Five-year cost per order | 3057.3424 | INR per order across five years. Compare against average order value before defending this programme on efficiency grounds.
| Five-year cost per catalogue SKU maintained | 102595.3835 | CORRECTED 18 Aug 2026. The previous formula divided by C42+C43, where C42 is a blank section header — so the denominator was 702 (IPRS only) instead of 1,341. The published figure of INR 1.92 lakh was overstated by 91%.
ORDER-VOLUME SENSITIVITY (replaces the point assumption)
| Scenario | Orders per year (count) | Orders over 5 years (count) | Cost per order (INR)
| Low — current shop is lightly used | 4000 | 20000 | 6879.0205
| Base — planning assumption | 9000 | 45000 | 3057.3424
| High — mobile app materially lifts demand | 18000 | 90000 | 1528.6712
| Break-even at INR 1,000 per order | 27516 |  | 1000 | Annual order volume required for the platform to cost under INR 1,000 per order.
The five-year cost per order swings by roughly four times across this band, which is why it must not be quoted from a single assumption. The cost per SKU maintained is the more stable and more honest unit for this platform.

## Price & Commercials
From Cost to Price
v1 stopped at cost. This is the commercial wrapper.
| Build cost, Scenario B mid-tier (INR crore) | 5.6193
| Target gross margin | 28% | Typical for Indian government fixed-price delivery.
| Price before tax | 7.8046
| GST on services | 18% | Verify the applicable rate and whether IPC can claim input credit as an autonomous body.
| QUOTED PRICE INCLUSIVE OF GST | 9.2094
MILESTONE BILLING AND CASH FLOW
Ref | Milestone | Month (M1–M16) | Share of price (%) | Value (INR Cr) | Trigger / exit criterion
M1 | Mobilisation and signed SRS | M2 | 10% | 0.78046 | Requirements matrix signed by IPC.
M2 | Architecture and design system approved | M4 | 10% | 0.78046 | HLD approved; unified catalogue design agreed.
M3 | Core platform in integrated test | M7 | 15% | 1.1707 | Identity, catalogue, order and audit services demonstrable.
M4 | Portal feature-complete in UAT | M10 | 15% | 1.1707 | All CMS and commerce features in UAT.
M5 | Migration complete and verified | M11 | 10% | 0.78046 | Content and OpenCart data migrated; redirects verified.
M6 | Portal live with clean VAPT | M12 | 15% | 1.1707 | Live on NIC/MeitY; DR failover proven; CERT-In report clean.
M7 | STQC CQW certificate issued | M13 | 5% | 0.39023 | Certificate in hand.
M8 | Apps published to both stores | M14 | 10% | 0.78046 | Live on App Store and Play Store.
M9 | Hypercare complete and handover | M16 | 10% | 0.78046 | Steady-state AMC transition signed off.
| Total |  | 100% | 7.8046
| Peak negative cash position (approx.) | -1.35 | Roughly 24% of build cost is carried before M3 clears. Working capital, not profit.
GUARANTEES AND PENALTY EXPOSURE
Ref | Item | Rate (%) | Value (INR Cr) |  | Note
C1 | Earnest money deposit | 2% | 0.15609 |  | Refundable, but blocks working capital through evaluation.
C2 | Performance bank guarantee | 10% | 0.78046 |  | Typically 10% of contract value for the full term plus claim period.
C3 | Liquidated damages cap | 10% | 0.78046 |  | Usually 0.5% per week of delay, capped at 10%. This is the schedule risk in rupees.
C4 | Bank guarantee carrying cost per annum | 1.5% | 0.011707 |  | Commission on the PBG value; a real cost, routinely forgotten in pricing.
| Margin after a full LD hit | 18% | If the LD cap is fully drawn, this is what is left. Test it before committing to the schedule.

## Timeline
Programme Timeline — Scenario B
Effort curve ties to the recommended figure on the Confidence sheet.
Ref | Phase | Start | End | Duration (months) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | Exit criterion
F0 | Mobilisation, discovery, requirements | M1 | M2 | 2 | [16 empty] | Signed SRS and 191-row matrix | bar: M1 to M2
F1 | Architecture, design system, platform foundation | M2 | M4 | 3 | [16 empty] | Approved HLD, DPDP design baseline | bar: M2 to M4
F2 | Core platform: identity, catalogue, order, audit | M3 | M7 | 5 | [16 empty] | Services in integrated test | bar: M3 to M7
F3 | Portal build: CMS, templates, facilities, forum | M4 | M10 | 7 | [16 empty] | Feature-complete in UAT | bar: M4 to M10
F4 | Mobile app and admin console build | M5 | M12 | 8 | [16 empty] | Feature-complete on internal track | bar: M5 to M12
F5 | Integrations, AI layer, MIS analytics | M7 | M12 | 6 | [16 empty] | Integration contracts signed off | bar: M7 to M12
F6 | Content and OpenCart data migration | M8 | M11 | 4 | [16 empty] | Migration verified, redirects live | bar: M8 to M11
F7 | QA, VAPT, GIGW conformance, STQC CQW | M9 | M14 | 6 | [16 empty] | Clean VAPT, CQW certificate | bar: M9 to M14
F8 | UAT, pilot, government-lab onboarding | M11 | M14 | 4 | [16 empty] | IPC sign-off on both surfaces | bar: M11 to M14
F9 | Portal go-live and cutover | M12 | M12 | 1 | [16 empty] | Live on NIC/MeitY, DR proven | bar: M12
F10 | Store submission and app go-live | M13 | M14 | 2 | [16 empty] | Published on both stores | bar: M13 to M14
F11 | Hypercare and transition to AMC | M14 | M16 | 3 | [16 empty] | Steady-state handover | bar: M14 to M16
| Ramp weight (relative, dimensionless) |  |  |  | 20 | 38 | 56 | 71 | 84 | 92 | 97 | 99 | 97 | 92 | 84 | 74 | 56 | 37 | 22 | 15
| Person-days in month |  |  | 3713 | 72 | 136 | 201 | 255 | 302 | 330 | 348 | 356 | 348 | 330 | 302 | 266 | 201 | 133 | 79 | 54
| Average FTE |  |  |  | 3.4 | 6.5 | 9.6 | 12.1 | 14.4 | 15.7 | 16.6 | 17 | 16.6 | 15.7 | 14.4 | 12.7 | 9.6 | 6.3 | 3.8 | 2.6
| Peak FTE |  |  | 17
| Average FTE |  |  | 11.1
DPDP full-compliance date of 13 May 2027 falls inside this window on any realistic start. Design to it from F1 rather than remediating at F7.
Staffed to the P80 bid basis so the schedule and the commercial figure agree. Planning to P50 and holding the difference as reserve is the alternative convention; it lowers peak FTE but requires the reserve to be governed explicitly.