## Read Me
Stage 1 · Timeline, milestones and payments
Indian Pharmacopoeia Commission — ipc.gov.in onto the Gov.In CMS Platform and DBIM. Basis date 2026-09-01. Generated from the effort model, not typed by hand: run Estimation/model/build_schedule.py to regenerate after any change.
WHAT THIS COSTS
Scope | Stage 1 only — remediate the live site, and produce the signed inventory and redirect map. It does NOT buy the migration.
Contract value | INR 2,388,000 excluding GST · INR 2,817,840 inclusive at 18%
Effort basis | 179 person-days at P80. Bidding P50 is even odds and nobody should quote it.
Duration | 24 weeks (5.5 months), 6 four-week periods
Team | 8 named people, 1.55 average FTE, peak near 3. Two roles carry 68% of the effort.
HOW TO READ IT
Timeline | Gantt by week. Bar colour is the phase. Milestone weeks are marked on the header row.
Milestones & Payments | Six milestones, each with an exit criterion that is checkable rather than a matter of opinion, and the evidence that closes it.
Cash Flow | Billing against cost incurred, with a four-week payment lag. The peak negative position is working capital, not profit.
Resource Plan | Person-days and FTE by role and period, derived from each package's own role mix.
Work Packages | The 25 packages, their three-point estimates and their scheduled weeks.
Commercial Terms | EMD, PBG, LD and retention, at IPC's own revealed rates from its last IT bid.
UNITS
PD — person-day | One person for one day. 21 PD make one person-month; 20 PD make one four-week period at 5 days a week.
P80 | Four engagements in five finish at or below this effort. The standard commercial basis for a fixed-price government contract.
INR lakh | One hundred thousand rupees. Payment values are given in full rupees so they can be transcribed into a purchase order.
FTE | Full-time equivalent. Period person-days divided by 20.
TWO THINGS TO SETTLE BEFORE SIGNING
Supplier tier | This price assumes a boutique or specialist supplier. IPC's own last IT tender (GEM/2026/B/7781379, 13-07-2026) demanded ISO 9001, ISO 27000 and CMMI Level 3 — a bar that excludes that tier. At mid-tier rates the same scope is roughly INR 33 lakh. Resolve the category before bidding, not at evaluation.
Performance guarantee term | IPC's revealed ePBG was 5% held for 60 months. On a 24-week assignment that is a five-year guarantee against a six-month job. Negotiate the term, not only the rate.
WHAT MOVED IN THE SCHEDULE | Phase 2 starts in week 3, in parallel with Phase 1 rather than after it. The 302-to-404 behaviour measured on 2026-09-01 is a usable existence oracle, so the inventory is not blocked on the 404 fix — which removes roughly six weeks from the plan's original sequencing.

## Timeline
Stage 1 timeline
24 weeks. Bars are scheduled weeks; ◆ marks a milestone. Phase 2 runs alongside Phase 1 rather than after it — see Read Me.
Ref | Work package | Phase | PD (P80) | Start | End | W1 | M1 | W3 | W4 | W5 | W6 | W7 | M2 | W9 | W10 | W11 | M3 | W13 | W14 | W15 | M4 | W17 | W18 | W19 | M5 | W21 | W22 | W23 | M6
0.1 | Correct the brief; re-issue the objective in writing | 0 · Mandate and decisions | 4.6 | 1 | 3
0.2 | Gov.In CMS intake via the MoHFW CIO route | 0 · Mandate and decisions | 7.8 | 2 | 12
0.4 | registry.gov.in control and DNS readiness | 0 · Mandate and decisions | 3 | 4 | 7
0.5 | Security-audit route settled in writing | 0 · Mandate and decisions | 3 | 5 | 9
0.6 | Redirect-capability determination (pivotal) | 0 · Mandate and decisions | 4.8 | 3 | 7
0.8 | DBIM logo lockup 3A/3B determination | 0 · Mandate and decisions | 1.5 | 6 | 10
0.9 | Destination status-code behaviour proven; origin status layer designed | 0 · Mandate and decisions | 6.2 | 4 | 9
1.1 | Real HTTP 404: error-document status, not a 302 to a 200 page | 1 · Emergency remediation | 4.7 | 3 | 6
1.2 | Charset: header says iso-8859-1 over 389 Hindi pages; header wins | 1 · Emergency remediation | 6.2 | 3 | 7
1.4 | GIGW policy pages and portal links (DBIM mandates no india.gov.in link) | 1 · Emergency remediation | 3 | 5 | 8
1.6 | robots.txt and a stopgap sitemap | 1 · Emergency remediation | 1.5 | 6 | 7
1.7 | CSP hardening on the live site | 1 · Emergency remediation | 6.4 | 4 | 8
1.8 | lang="hi" across 389 Hindi pages; close the joomla.xml version disclosure | 1 · Emergency remediation | 3.2 | 5 | 8
2.1 | Joomla database extraction and reconciliation | 2 · Inventory and redirect map | 6.4 | 3 | 7
2.2 | Live crawl with the two-signal validator | 2 · Inventory and redirect map | 7.5 | 3 | 6
2.3 | Wayback / CommonCrawl orphan recovery | 2 · Inventory and redirect map | 4.8 | 5 | 8
2.4 | Search Console traffic overlay | 2 · Inventory and redirect map | 3 | 6 | 9
2.5 | Union of four sources into one authoritative register | 2 · Inventory and redirect map | 4.8 | 8 | 11
2.6 | Triage facilitation — keep / archive / retire | 2 · Inventory and redirect map | 15.1 | 10 | 19
2.7 | PDF estate inventory and disposition (~2,758 documents) | 2 · Inventory and redirect map | 12.6 | 11 | 18
2.8 | Redirect map — ~1,727 distinct source paths; rows exceed paths | 2 · Inventory and redirect map | 24.2 | 13 | 20
2.9 | Hindi pairing by hreflang; bilingual gap quantified | 2 · Inventory and redirect map | 4.8 | 9 | 13
P.1a | Programme and delivery management — Stage 1 | P · Programme management | 19.2 | 1 | 24
P.2a | Business analysis and content governance — Stage 1 | P · Programme management | 11.9 | 2 | 22
P.3a | Documentation, SOPs and the Stage 2 cost baseline | P · Programme management | 9.1 | 18 | 24
| TOTAL |  | 179
Phase key
Mandate and decisions
Emergency remediation
Inventory and redirect map
Programme management

## Milestones & Payments
Milestones and payment schedule
Every milestone is paid against a checkable exit criterion, not against a date. A milestone that cannot be failed is not a milestone.
Ref | Week | Milestone | Share | Value ex-GST (INR) | GST (INR) | Payable inc-GST (INR) | Cumulative ex-GST (INR)
M1 | 2 | Mobilisation and inception report | 10% | 238800 | 42984 | 281784 | 238800
M2 | 8 | Live site remediated | 20% | 477600 | 85968 | 563568 | 716400
M3 | 12 | Platform decision pack | 15% | 358200 | 64476 | 422676 | 1074600
M4 | 16 | Draft inventory: the union register | 20% | 477600 | 85968 | 563568 | 1552200
M5 | 20 | Signed disposition register and redirect map | 25% | 597000 | 107460 | 704460 | 2149200
M6 | 24 | Stage 2 cost baseline and handover | 10% | 238800 | 42984 | 281784 | 2388000
|  | TOTAL | 100% | 2388000 | 429840 | 2817840
EXIT CRITERIA — what has to be true before each invoice is raised
M1 · Week 2 · Mobilisation and inception report
Exit criterion | Team named and on site. Inception report accepted: scope, RACI, access list, and the written re-statement of the objective as adopting DBIM and the Gov.In CMS Platform rather than 'moving to india.gov.in'.
Evidence | Signed inception report; access requests lodged for the Joomla database, Search Console and registry.gov.in.
M2 · Week 8 · Live site remediated
Exit criterion | A missing path returns a genuine HTTP 404 under both a browser and a bare user agent. Header charset is UTF-8 and Devanagari renders. All 389 Hindi pages declare lang="hi". CSP no longer carries a wildcard with unsafe-inline and unsafe-eval. robots.txt published. joomla.xml no longer publicly readable.
Evidence | Automated assertion suite, run in front of the client, with before-and-after captures. Every item destination-independent.
M3 · Week 12 · Platform decision pack
Exit criterion | Written intake position from the MoHFW CIO, or a signed decision to take the DBIM-aligned rebuild instead. Redirect capability and destination status-code behaviour proven and documented, with the origin status-layer design if needed. Audit route settled in writing. S3WaaS ruled in or out on the record. DBIM logo lockup determined. registry.gov.in control confirmed.
Evidence | Decision pack with one signed page per question, each with a named owner and a date.
M4 · Week 16 · Draft inventory: the union register
Exit criterion | One register unioning the Joomla database, a live two-signal crawl, Wayback and Common Crawl orphans, and Search Console traffic. Every URL appears exactly once, live-validated, with language tree, template and title. Hindi paired by hreflang, never by URL transformation.
Evidence | Register delivered as a checked-in dataset with the crawl and validation code that produced it, so the client can re-run it.
M5 · Week 20 · Signed disposition register and redirect map
Exit criterion | Every verified URL carries a keep / archive / retire disposition signed by a named IPC content owner, including explicit dispositions for PvPI, the news archive, the legacy paths and the PDF estate. Redirect map complete: one decided row per surviving source path, with Hindi rows byte-verified through the real toolchain.
Evidence | Signed CSV. Automated check that every source path resolves to exactly one row and no destination is unreachable.
M6 · Week 24 · Stage 2 cost baseline and handover
Exit criterion | Stage 2 re-costed from the delivered register rather than from estimate, with quantities, rates and a three-point spread. Operating documentation and SOPs handed over. Recurring obligations listed with named owners.
Evidence | Stage 2 baseline document plus the re-runnable model. This is the deliverable that makes Stage 2 procurable.

## Cash Flow
Cash flow
Cost is incurred as effort is spent; cash arrives 4 weeks after a milestone is certified. Government payment against a certified milestone conventionally runs 30 days. Modelled as a four-week lag between billing and receipt; it is where the working capital goes.
Period | Weeks | PD spent | Cost incurred (INR) | Billed inc-GST (INR) | Cash received (INR) | Cumulative cost (INR) | Cumulative received (INR) | Net position (INR)
P1 | W1–W4 | 27.7 | 299050.8623 | 281784 | 0 | 299050.8623 | 0 | -299050.8623
P2 | W5–W8 | 55.4 | 598510.8201 | 563568 | 281784 | 897561.6824 | 281784 | -615777.6824
P3 | W9–W12 | 26.3 | 284535.4531 | 422676 | 563568 | 1182097.1356 | 845352 | -336745.1356
P4 | W13–W16 | 30.8 | 333109.3883 | 563568 | 422676 | 1515206.5238 | 1268028 | -247178.5238
P5 | W17–W20 | 29.2 | 314833.0787 | 704460 | 563568 | 1830039.6025 | 1831596 | 1556.3975
P6 | W21–W24 | 9.6 | 103160.3975 | 281784 | 704460 | 1933200 | 2536056 | 602856
P7 | W25–W28 (after close) | 0 | 0 | 0 | 281784 | 1933200 | 2817840 | 884640
Blended rate used |  |  | 10800 | INR per person-day, an output of the role mix in the packages
Peak negative position |  |  | -615777.6824 | The working capital the supplier carries. Not profit, and not recoverable from margin
Peak as share of contract |  |  | -25.79% | Ask for a mobilisation advance if this is uncomfortable

## Resource Plan
Resource plan
Person-days and full-time equivalents by role and four-week period, derived from each package's own role mix. One period = 20 working days.
Ref | Role | INR/PD | Total PD | P1 PD | P2 PD | P3 PD | P4 PD | P5 PD | P6 PD | P1 FTE | P2 FTE | P3 FTE | P4 FTE | P5 FTE | P6 FTE
ME | Migration Engineer | 12000 | 65.9913 | 10.9193 | 26.7198 | 4.5407 | 10.4064 | 10.794 | 2.611 | 0.54597 | 1.336 | 0.22703 | 0.52032 | 0.5397 | 0.13055
BA | Content Strategist / Business Analyst | 13000 | 55.2078 | 2.4648 | 7.1611 | 11.9371 | 15.6485 | 14.254 | 3.7424 | 0.12324 | 0.35805 | 0.59685 | 0.78242 | 0.7127 | 0.18712
EL | Engagement Lead / Programme Manager | 22000 | 29.7229 | 6.9992 | 5.3236 | 5.6937 | 4.4047 | 4.1032 | 3.1985 | 0.34996 | 0.26618 | 0.28468 | 0.22024 | 0.20516 | 0.15992
SA | Solution Architect — Gov.In CMS / DBIM | 24000 | 12.4169 | 4.5524 | 5.6411 | 2.2234 | 0 | 0 | 0 | 0.22762 | 0.28206 | 0.11117 | 0 | 0 | 0
SE | Security Engineer | 20000 | 7.1052 | 1.0646 | 5.6247 | 0.4158 | 0 | 0 | 0 | 0.053232 | 0.28124 | 0.02079 | 0 | 0 | 0
QA | QA Engineer | 9500 | 3.8724 | 1.6895 | 2.183 | 0 | 0 | 0 | 0 | 0.084474 | 0.10915 | 0 | 0 | 0 | 0
CO | Content Operations / Editorial support | 7500 | 3.4041 | 0 | 1.485 | 1.5353 | 0.38382 | 0 | 0 | 0 | 0.07425 | 0.076763 | 0.019191 | 0 | 0
AX | Accessibility Specialist | 15000 | 1.2794 | 0 | 1.2794 | 0 | 0 | 0 | 0 | 0 | 0.063969 | 0 | 0 | 0 | 0
| TOTAL |  | 179 | 27.6899 | 55.4177 | 26.3459 | 30.8435 | 29.1512 | 9.5519 | 1.3845 | 2.7709 | 1.3173 | 1.5422 | 1.4576 | 0.47759
| Peak FTE in any period |  | 2.7709
| Average FTE across the assignment |  | 1.4917
The curve is deliberately front-loaded, not badly levelled. Weeks 5-8 are a remediation sprint on the live site - three people for four weeks - because that work is destination-independent and every week it waits is a week of indexed junk and a failing charset. After it lands the team settles to roughly 1.5 FTE for the inventory, then tapers to closeout. A boutique can staff that shape; a large firm's bench cannot, which is another reason the tier question in Read Me matters.
Client effort, tracked and never billed: 40–70 person-days of IPC subject-matter time for triage sign-off. 60–80% of a content audit is client-side and cannot be bought. An under-resourced client is a schedule risk that first presents as a cost saving.

## Work Packages
Work packages
Three-point estimates. Expected = (O + 4M + P) / 6. The P80 column scales the expected value by 1.371 to the bid basis, which is where the risk reserve lives.
Ref | Phase | Work package | O | M | P | Expected | P80 (×1.37) | Weeks
0.1 | 0 · Mandate and decisions | Correct the brief; re-issue the objective in writing | 2 | 3 | 6 | 3.3333 | 4.5692 | W1–W3
0.2 | 0 · Mandate and decisions | Gov.In CMS intake via the MoHFW CIO route | 3 | 5 | 11 | 5.6667 | 7.7677 | W2–W12
0.4 | 0 · Mandate and decisions | registry.gov.in control and DNS readiness | 1 | 2 | 4 | 2.1667 | 2.97 | W4–W7
0.5 | 0 · Mandate and decisions | Security-audit route settled in writing | 1 | 2 | 4 | 2.1667 | 2.97 | W5–W9
0.6 | 0 · Mandate and decisions | Redirect-capability determination (pivotal) | 2 | 3 | 7 | 3.5 | 4.7977 | W3–W7
0.8 | 0 · Mandate and decisions | DBIM logo lockup 3A/3B determination | 0.5 | 1 | 2 | 1.0833 | 1.485 | W6–W10
0.9 | 0 · Mandate and decisions | Destination status-code behaviour proven; origin status layer designed | 2 | 4 | 9 | 4.5 | 6.1685 | W4–W9
1.1 | 1 · Emergency remediation | Real HTTP 404: error-document status, not a 302 to a 200 page | 1.5 | 3 | 7 | 3.4167 | 4.6835 | W3–W6
1.2 | 1 · Emergency remediation | Charset: header says iso-8859-1 over 389 Hindi pages; header wins | 2 | 4 | 9 | 4.5 | 6.1685 | W3–W7
1.4 | 1 · Emergency remediation | GIGW policy pages and portal links (DBIM mandates no india.gov.in link) | 1 | 2 | 4 | 2.1667 | 2.97 | W5–W8
1.6 | 1 · Emergency remediation | robots.txt and a stopgap sitemap | 0.5 | 1 | 2 | 1.0833 | 1.485 | W6–W7
1.7 | 1 · Emergency remediation | CSP hardening on the live site | 2 | 4 | 10 | 4.6667 | 6.3969 | W4–W8
1.8 | 1 · Emergency remediation | lang="hi" across 389 Hindi pages; close the joomla.xml version disclosure | 1 | 2 | 5 | 2.3333 | 3.1985 | W5–W8
2.1 | 2 · Inventory and redirect map | Joomla database extraction and reconciliation | 2 | 4 | 10 | 4.6667 | 6.3969 | W3–W7
2.2 | 2 · Inventory and redirect map | Live crawl with the two-signal validator | 3 | 5 | 10 | 5.5 | 7.5392 | W3–W6
2.3 | 2 · Inventory and redirect map | Wayback / CommonCrawl orphan recovery | 2 | 3 | 7 | 3.5 | 4.7977 | W5–W8
2.4 | 2 · Inventory and redirect map | Search Console traffic overlay | 1 | 2 | 4 | 2.1667 | 2.97 | W6–W9
2.5 | 2 · Inventory and redirect map | Union of four sources into one authoritative register | 2 | 3 | 7 | 3.5 | 4.7977 | W8–W11
2.6 | 2 · Inventory and redirect map | Triage facilitation — keep / archive / retire | 6 | 10 | 20 | 11 | 15.0785 | W10–W19
2.7 | 2 · Inventory and redirect map | PDF estate inventory and disposition (~2,758 documents) | 5 | 8 | 18 | 9.1667 | 12.5654 | W11–W18
2.8 | 2 · Inventory and redirect map | Redirect map — ~1,727 distinct source paths; rows exceed paths | 10 | 16 | 32 | 17.6667 | 24.217 | W13–W20
2.9 | 2 · Inventory and redirect map | Hindi pairing by hreflang; bilingual gap quantified | 2 | 3 | 7 | 3.5 | 4.7977 | W9–W13
P.1a | P · Programme management | Programme and delivery management — Stage 1 | 8 | 13 | 24 | 14 | 19.1908 | W1–W24
P.2a | P · Programme management | Business analysis and content governance — Stage 1 | 5 | 8 | 15 | 8.6667 | 11.88 | W2–W22
P.3a | P · Programme management | Documentation, SOPs and the Stage 2 cost baseline | 4 | 6 | 12 | 6.6667 | 9.1385 | W18–W24
|  | TOTAL | 69.5 | 117 | 246 | 130.5833 | 179

## Commercial Terms
Commercial terms
Rates are IPC's own, revealed on GEM/2026/B/7781379 dated 13-07-2026, rather than convention. Where they are harsher than the GeM default, that is noted.
Item | Rate | Value (INR) | Note
Earnest money deposit | 4% | 95520 | IPC's own revealed rate on GEM/2026/B/7781379 (13-07-2026), against a GeM recommendation of 1%. Refundable, but it blocks working capital through evaluation.
Performance bank guarantee | 5% | 119400 | IPC's revealed rate, held 60 months on its last IT bid. For a 5.5-month assignment, negotiate the term down — a 60-month PBG on a 24-week engagement is a real and avoidable carrying cost.
PBG carrying cost per annum | 1.5% | 1791 | Bank commission. Routinely forgotten in pricing.
Liquidated damages cap | 10% | 238800 | Convention is 0.5% per week of delay capped at 10%. This is the schedule risk expressed in rupees.
Retention against M6 | 10% | 238800 | M6 is itself 10% and is the natural retention. Do not stack a further retention on top of it.
Contract value ex-GST |  | 2388000
GST at 18% |  | 429840
Contract value inclusive of GST |  | 2817840
Verify whether IPC can claim input tax credit as an autonomous body under MoHFW. If it cannot, GST is a real cost to the buyer rather than a pass-through, and it changes which side of INR 30 lakh this contract sits on.